## Current Task
Sr/No. | Task | Status | Remarks/progress
1 | Taatools - installation on MAR4DEV1 | Completed | PTF applied and tested working fine for DLTOLDSPLF
1a | Taatools - installation on BUSDEP V7R5 | Completed | Called TAATOOLS help desk and fixed the problem by installing V7R5
2 | Follow up dbu license pending payment | Compeled | Edward reply it takes 30 days we have to ask vendor to provide temp key once expired on Jul 15
5 | LOMS migration USA to Canada project - Estimate etc | Target completeion Date is 30-June-2027
| -DASD collection | WIP | Edward/Patrick first meeting completed 7/27
| - List of all libraries and their sized | completed | Partially completed only selective libraries sized ahs been provided
| -List of all Third parties licenses/vendors | wip | identify 3rd party software by comparing libraries and their status
-List of user profiles
-Authroity lists
| -IFS folders | completed
| -ROBOT jobs for SUNRISE & COSMOS | Completed | Need to identify sunrise and canadian jobs
| - Presentation for new LPARs, Required Disk Space, Memory | Completed | waiting from Tracey
| - ServiceExpress inputs and cost estimation | WIP | waiting from Tracey
| - GitHub | Completd
Target to complete 25-Sep-2026
7 | French Tranlsation sFTP testing in MARDEV1 SDLTRANS - definition is working - tested SDLTRANS - auto scan tesging SDLTRNSAUT- auto scan is working - tested | Completed | SDLTRANS defination has been created and tested / Directory Scan is created SDLTRANS <- Directory scan has been created and testing SDLTRNSAUT <- autoscan created and testing
8 | French Tranlsation sFTP testing in BUSDEP SDLTRANS French translation PUT DropShp SDLTRANSGT French Translation GET SDLTRANS1 French translation PUT Retails | WIP | SDLTRANS defination has been created SDLTRANS SDLTRNSAUT
9 | Reconfigure primary DNS server to 10.19.246.9 and secondary to 10.18.4.9 on BUSDEP | WIP
9a | Reconfigure primary DNS server to 10.18.4.9 and secondary to 10.19.246.9 on BUSDEPHA | Completed
9b | Reconfigure primary DNS server to 10.18.4.9 and secondary to 10.19.246.9 on MAR4DEV1 | Completed
10 | Spool file deletion issue PTF applied and delete 24455 out of 73245 spool files deleted from QPRINT/QGPL | WIP | New program to delete all spools files which no qualify retenion policy
| QEZJOB |  |  | mireion JE
12 | spool file | WIP | /table of spools working
13 | purge | WIP
14 | TG menu | WIP
15 | ROBOT Fortra (GUI version check from FORTA host/client how to install |  | Next step to install Robot Consol in GUI and Robot Network

## Completed Task List
Sr/No. | Task | Status | Remarks/progress
1 | Taatools - installation on MAR4DEV1 | Completed | PTF applied and tested working fine for DLTOLDSPLF
1a | Taatools - installation on BUSDEP V7R5 | Completed | Called TAATOOLS help desk and fixed the problem by installing V7R5
2 | Follow up dbu license pending payment | Compeled | Edward reply it takes 30 days we have to ask vendor to provide temp key once expired on Jul 15
4 | Dayone job investigation - disabled on start of the month | Completed | ITT tool (system profile Q) found program in SYSSRC/QCLLESRC/PCU100CL
6 | Delete Manish jobs waiting for MSGW | Completed | Ended all four jobs with MSGW
6a | 8TB space increase in MAR4DEV1 | Completed
8 | Incident ticket check from Masoud / Joseph and other team members to support | Compelted | SN ticket has been submitted to get access to DL BUSDEP_APPSUPT
9 | DC followup for MAR4DEV1 and BUSDEP | Completed | CSR has been created and sent to Network team | The latest IBM PTFs are causing issues with the tools
10 | Data mirror - mimix talk with SE | Completed | CR to create SN last week of Jul - SSL cert applied on Jul 31
11 | SSL certifcate BUSDEPHA (required IPL) (CHG0035368 approved | Completed | CR to create SN First week of Aug
11a | SSL certifcate BUSDEP (required IPL) CHG0035369 approved | Completed | Certificate has been applied on Aug 4'2026 will be confrimed after IPL
10 | Spool file deletion issue PTF applied and delete 24455 out of 73245 spool files deleted from QPRINT/QGPL |  | Marked Completed | The latest IBM PTFs are causing issues with the tools
We have a patch to fix the issue.
|  | <= MAR4DEV1 |  | PATCH:
We have a patch for this problem. A description of the problem, the patch, and instructions on are this page.
Marked Completed
<= BUSDEP
3 | Patrick Townsend - Create new definition for French translation and Test | Completed | Ticket has been opened for assistance PRE-00912026 | Robot ALERT ID-000079788 SYSSUPTEMA BUSDEP
5 | Delete Manish jobs waiting for MSGW | Completed | Ended all four jobs with MSGW
7 | Incident ticket check from Masoud / Joseph and other team members to support | Compelted | SN ticket has been submitted to get access to DL BUSDEP_APPSUPT
3a | ROBOT ALert issue relate to PT (BELLTXN) | Completed | Increase the interval and getting less messages
3b | Follow up with IBM sFTP issue 1P | Completed
3c | Learn ROBOT Alert | Completed | Case opened with HELP CASE=00108200022 | Robto alert on phone/email/pager/sms
8 | Work with SE to get Speed/CPU/JOBS/SPACE monitoring tool | Completed |  | Create to CHG ticket
| COSMOS user-id access and learning | Completed
| ROBOT job jobs listing and extaction | Completed
| SUNRISE user-id access and learning | Completed
| SUNRISE task asked by Patrick | Completed