## Sheet1
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
1 | Sunday | 8:00AM | 9:00AM |  |  | Start POS FTPs services for a sample test store only ( 49 or 91 or 448 stores) Andriy will provide new instructions/steps | Before GO Validation | Alain Miron / Joyal | Alain / Joyal to confirm stores
2 |  |  |  |  | BUSDEPHA | Vendor Software Verification
3 | [5 empty] | · Verify Client Access / ACS functions |  | Manish
4 | [5 empty] | · Verify DBU functions |  | Masoud
5 | [5 empty] | · Verify IMAIL functions |  | Masoud/Manish
6 | [5 empty] | Verify SNDDST and SNDSMTPEMM email functions |  | Manish
7 | Sunday | 8:00AM | 9:00AM |  |  | · Verify MARKMAGIC to be able to print Forms/labels - New version to be tested using menu option for PDF format printing | Before GO Validation | Masoud / Stanley / Manish
8 | [5 empty] | · Verify TAATOOL functions |  | Manish
9 | [5 empty] | · Verify ROBOT Schedule, Alert and Robot Console functions |  | Manish
10 | [5 empty] | · Verify IMPLEMENTER functions to promote code from MAR4DEV1 |  | Masoud/Manish
11 |  |  | ` |  |  | · Verify NetIQ Pentasafe functions |  | Manish
12 | [5 empty] | · Verify AS2 OpenText Liaison functions (Peter to test) | Before GO Validation | Peter / Stephen
13 | [5 empty] | · Verify Gentran functions (Peter to test) | Before GO Validation | Peter / Stephen
14 | [5 empty] | · Verify Patrick TownSend functions (with Dennis and Supreem, Martin is the contact ) |  | Manish
15 |  |  |  |  | BUSDEPHA | Network Verification
16 | Sunday | 8:00AM | 9:00AM |  |  | · Verify store connection (store #49, 91 and 448) from Bell and TELUS Network as well as checkpoint / ISR routers | Before GO Validation | Helpdesk / Bart / Haran
17 | [5 empty] | Store 49, Telus MPLS (Montreal) |  | Mustapha Medani GM 438-832-1509
18 | [5 empty] | Store 91, Bell MPLS (Nova Scotia) |  | Leanne Candelora at 902 565-1652 (cell #)
19 | [5 empty] | Store 448, Broadband (Toronto) |  | Joshua Cere Service mgr 905 246 2141 Frank Caruso General Manager Store 448 Dani phone # 289 407 1647 for May 11 2025
20 | [5 empty] | · Verify FC99 and FC351 FC connection on Monday due to FC not available on Weekends |  | FC users
21 | [5 empty] | · Verify Mini-DDC (317) connection ( Converted to TCPIP printing from SNADS ) |  | Patrick / Ashes
22 | [5 empty] | · Verify Client Access using DR_xx sessions. Use 3 stores with different networks |  | Manish / Masoud / HelpDesk /Wayne
23 | Sunday | 8:00AM | 9:00AM |  |  | · Verify store scanner functions (store #49,91,448). Start QPGMR sbs for the test of QPADEVxxxx device and then turn it off after validation | Before GO Validation | Store Associate / Help Desk / Haran / Manish |  | Mukesh
24 | [5 empty] | · Verify home office and VPN connections |  | Bart
25 |  |  |  |  | BUSDEPHA | JDA Basic Functions
26 | [5 empty] | · Verify BRMS Backup functions |  | Manish / Midrange
27 | Sunday | 8:00AM | 9:00AM |  |  | · Verify DDM, APPC, ICF file connections with Sunrise and Sunbeam. Need a CR for iSeries Engineering team support | Before GO Validation | Manish / Patrick / iSeries Team US
28 | [5 empty] | · Verify Emmergency profile check out tool works |  | Masoud / Manish
29 | Sunday | 8:00AM | 9:00AM |  |  | · Verify Printer testing to store xxx | Before GO Validation | Masoud
30 | [5 empty] | · Verify Printer testing at home office |  | Masoud
31 | [5 empty] | · Verify FTP using port 21 (Various Contacts) |  | Masoud
32 | [5 empty] | · Verify RightFax Connection : Move a test fax spool file called REPORT from SECMANISH outputq to QGPL/PULSE output queue. Call MIKE Gee to confirm if he received the FAX. |  | Manish / Michael Gee (US)
33 |  |  |  |  | BUSDEPHA | JDA Critical Functions
34 | [5 empty] | · Verify JDA MMS basic functions |  | Masoud / Zoya
35 | [5 empty] | · Verify User JDA MMS Menu function via Navigating the JDA MMS menu, access different screens without making any updates. |  | Masoud / Zoya
44 | [5 empty] | · Verify Salesforce order processing |  | Masoud / Ken
37 | [5 empty] | · Verify AS2 Proxy sever connection |  | Peter / Stephen
38 | [5 empty] | · Verify EDI connection |  | Peter / Stephen
39 | [5 empty] | · send 997 to external, one through AS2, one thrugh VAN
36 | [5 empty] | Verify STRPATHR function ( this should work on BUSDEPHA ) |  | Manish
40 | [5 empty] | · Verify JDA E3 ASR/AWR connection |  | Sarika / Mark Scuse
41 | Sunday | 8:00AM | 9:00AM |  |  | · Verify Price File FTP to CPC via Patrick Townsend. | Before GO Validation | Manish / Jun Ling / Carol | use dummy file to test
42 | [5 empty] | Put the trigger file in IFS using a menu option on MENIOD optin 26 | Before GO Validation
43 | [5 empty] | From PT, Run the BELLPRI ftp defination and Scan Dir to ACTIVE so file will be picked up and FTPed | Before GO Validation
45 | Sunday |  |  |  |  | · Verify FTP from BUSDEPHA to Access Via using Store 448 as test store, VIABATC, Uses scanner to request a print signage |  | Sonja / Stanley / Store associate
46 | Sunday | 8:00AM | 9:00AM |  |  | · Verify BOPIS inventory count / MLS Webservices | Before GO Validation | Manish / Stuti / Amit / Jitendra (US Team) | mlsuspport@staples.com
47 | [5 empty] | Goto Staples.ca, serarch for sku# 15083 for BICPEN, select my store as Red Mapel Richmod Hills which is store nuber 155, check the in stock quantity displayed
48 | [5 empty] | Select * from mmbuslib/Invbal where istore = 155 AND INUMBR = '15083'
49 | [5 empty] | Check the On Hand quantity displayed from SQL and see if matches with in Stock qty
51 | Sunday | 8:00AM | 9:00AM |  |  | Verify ODBC connection from Sequel 16 to BUSDEPHA server | Before GO Validation | Kevin Bo
52 | Sunday | 8:00AM | 9:00AM |  |  | Verify ODBC connection from Sequel 05 to BUSDEPHA server | Before GO Validation | Kevin Bo
50 | Sunday | 8:00AM | 9:00AM |  |  | Verify AUTOBOT for ASR AWR test |  | Sonia Team / Anthony / Brian
53 | Sunday | 8:00AM | 9:00AM |  |  | Verify BUSDEPHA to Manhattan: Resend: Receipt, Verification, ShipConfirm, Adjustment, InventorySynch to confirm |  | Zoya / Ding / Peter to check file for Inventorysync
54 | Sunday | 8:00AM | 9:00AM |  |  | · Verify POS connectivity from Store (Price Download), Price file to be deleted after test is over - Andriy will provide new instructions/steps | Before GO Validation | Masoud / Joyal
55 | Sunday | 8:00AM | 9:00AM |  |  | · Verify POS connectivity from Store (Sales Upload), store # 49,91,448) to be used - Andriy will provide new instructions/steps | Before GO Validation | Masoud / Joyal
56 | Sunday | 8:00AM | 9:00AM |  |  | STRTCPSVR SERVER(QHTTPSVR) | Before GO Validation | Manish
57 | Sunday | 8:00AM | 9:00AM |  |  | Verify EAIONLINE web service - Kiosk order, one more service to be provided by Rachael | Before GO Validation | Carol / Rachael
58 | Sunday | 8:00AM | 9:00AM |  |  | Verify EAIRETAIL web service - EasyApp, PO inquiry by PO Number to get response Only | Before GO Validation | Store Associate / Haran
59 | Sunday | 8:00AM | 9:00AM |  |  | Verify ECP web service - ECP Sync (from ETS to BUSDEPHA) | Before GO Validation | Yajun
60 | Sunday | 8:00AM | 9:00AM |  |  | ENDTCPSVR SERVER(QHTTPSVR) | Before GO Validation
61 | [5 empty] | Verify DATASCAN FTP |  | Manish
62 | [5 empty] | Very DenisSupreme |  | Manish
63 |  |  |  |  | BUSDEPHA | GO NOGO decision |  | Edward / Test Team / Business
`
47 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Kiosk Order ( Solution Builder ) | Before GO Validation | Carol / Joseph / Dowlath
48 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Online SalesPosting, Return and Refund (via EAI) | Before GO Validation | Joseph / Dowlath / Anson | Need to stop actual hellboy posting during roleswap
49 | Sunday | 8:00AM | 9:00AM |  |  | Ding / Anson will post an open transaction to validate the connection | Before GO Validation
50 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Store Return, Refund (via EAI) , | Before GO Validation | Joseph / Dowlath / Anson
51 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - BINQTY (from BUSDEPHA to POS) , | Before GO Validation | Yajun / Joseph / Dowlath
52 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - INVAUD (from BUSDEPHA to CMIS) | Before GO Validation | Yajun / Joseph / Dowlath
53 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - ECP Sync (from ETS to BUSDEPHA) | Before GO Validation | Yajun / Joseph / Dowlath
54 | Sunday | 8:00AM | 9:00AM |  |  | http://BUSDEPHA:10021/web/services/ECPCaseStoreUpdService/ECPCaseStoreUpd | Before GO Validation
53 | Sunday | 8:00AM | 9:00AM |  |  | Verify IWS Web Service - HBT ( Host Based Tax ) ( via EAI ) | Before GO Validation | Joseph / Dowlath via Postman | Need resource from Alain
54 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Inventory Lookup (for CPC), | Before GO Validation | Joseph / Dowlath via Postman | similar to step 4.17 for same resource to do
55 | Sunday | 8:00AM | 9:00AM |  |  | http://BUSDEPHA.staples.com:8088/ws/WSIVS10/OnHand/15/934103/0/0 | Before GO Validation
56 | Sunday | 8:00AM | 9:00AM |  |  | Verify IWS Web Service - Inventory Lookup (for POS), Can be tested from Postman | Before GO Validation | Alain / Haran / Joyal | Need resource from Alain, Chris to follow up with Tong