## Main Plan
SWITCH
Step # | System | Activity | Section and Pages in RunBook | Excel Tab Name | Status | Start Date | Day | Estimated Start Time (EDT) | Estimated End Time (EDT) | Original Estimate Duration HH:MM | Actual Start Time | Actual End Time | Responsibility | Comments/Notes
Preparation Steps Immediately Prior to Switch
|  | Manish - CR is created a week in advance and fully approved. Ensure that all vendor perm keys are available for both BUSDEP and BUSDEPHA Bart - no network activities Nasser/Stanley - no applications role out Stanley - Sunrise is shutdown for Maintenance.(could impact connectivity testing) Stanley - change management meeting to ensure nothing else is running that weekend. Stanely - Ensure that no store physical inventory on role swap weekend BOPIS - BOPIS can not be stopped due to US uses the same interface. POS/CopyPrint/SalesForce Team - Inform teams to stop putting sales, copy and print and sales force data to BUSDEP at 11:30 PM saturday nite. Nasser/Stanley/Curtis: Move the Consignment Conversion date to next weekend to avoid delay on Sunday. Nasser to send email to Curtis. Users Submitted Jobs: Users needs to be asked to stop submiting scheduled jobs as they can not be replicated to HA due to MIMIX limitation Helpdesk : Send email comminication to all AS400 users about BUSDEP outage due to DR roleswap. Digital Team: Post comminication on Staples.ca re BOPIS not available due to BUSDEP DR Roleswap. | [10 empty] | Staples
| BUSDEP | P0- Preparation for Planned Switch Mimix Audit_Verification and Remediation Health Check of Mimix before the Role Swap Validation Mimix is Ready to be Role Swaped. Capture ROBOT Jobs, Patrick Town Send Active Recrods, JOBSCD entries and Robot jobs runs from 3:00AM to 11:00AM on Sunday, Validate 3rd party license on BUSDEPHA | P0 Steps 1-10 | P0-Preparation for Planned Switch |  | June 3 to June 7 2024 | Mon- Fri | [5 empty] | Mid-Range/Staples
| BUSDEP | Hold VRM jobs CCL_WKLY, VRM_WKRPT, VRM_INVOIC and VRM_WKND from the RBO. They to be run on BUSDEP once live. |  |  |  | June 3 to June 7 2024 | Mon- Fri | [5 empty] | Naser / Stanley
| BUSDEP | Hold SUNDAY2 job since it will be run manually using DO. |  |  |  | June 3 to June 7 2024 | Mon- Fri
| BUSDEP | OMIT SYSSTRSBS job since we are not starting any subsystem after DAY_CLS_RN job completes for this weekend. SYSSTRSBS is a react job to DAY_CLS_RN job. |  |  |  | June 3 to June 7 2024 | Mon- Fri
| BUSDEP | Cancel or Omit Sunday Backup Job as follows: (1) To skip Sunday backup job PRODSUDP ( Job # 312), comment out RBTBCHUPD JOBNUMBER(312) SCHEDULE(*DO) command from SUNDAY1 job that runs on 11:59PM on Sat night. PRODSUDP submits PROD1 and PROD2 job that reaches a syncpoint and sets the flag CHKPOINT to complete to start SUNDAY2 job. (2) Run SUNDAY2 job manually using DO. (3) SUNDAY2 will submit DAY_CLS_RN (4) DAY_CLS_RN job will submit CONSGN_CNV job (5) You must wait till this CONSGN_CNV job complete on BUSDEP. (6) CCL_WKLY, VRM_WKRPT, VRM_INVOIC and VRM_WKND jobs are dependent on CONSGN_CNV job and to be released on BUSDEPHA by Nasser after go live . |  |  |  | 2024-06-07 | Fri | [5 empty] | Staples
| BUSDEPHA | Cancel BUSDEPHA weekly backup BHA_WEEKLY from WRKJOBSCDE ( this caused 1 hr delay in this DR test ) |  |  | complete | 2024-06-07 | Fri | [5 empty] | MIDRANGE | 06/09/24 omited
| BUSDEPHA | Allocate CPU and MEMORY from MAR4DEV1 to BUSDEPHA LPAR to match with BUSDEP |  |  |  | 2024-06-07 | Fri | [5 empty] | MIDRANGE
|  | Confirm SVC file ftped to PC application folder |  |  |  | 2024-06-08 | Sat | 20:30 | 0:00 |  |  |  | Stanley
1 |  | Stop all POS FTPs services |  |  |  | 2024-06-08 | Sat | 23:30 | 0:00 |  |  |  | Alain Miron / Joyal | 905-716-3377
2 |  | Stop all FC Sales Feed |  |  |  | 2024-06-08 | Sat | 23:30 | 0:00 |  |  |  | Devop team / Jerry
3 |  | Stop all Salesforce orders feed |  |  |  | 2024-06-08 | Sat | 23:30 | 0:00 |  |  |  | Ken
4 |  | Stop all Copy and Print orders |  |  |  | 2024-06-08 | Sat | 23:30 | 0:00 |  |  |  | Bonny / Carol
5 |  | Stop Zuora Transactions/ Allstate / TSS |  |  |  | 2024-06-08 | Sat | 23:30 | 0:00 |  |  |  | Kevin Liang (Bo) / Jamie
6 |  | Stop Inventory Sync from Manhanton WMS |  |  |  | 2024-06-08 | Sat | 23:30 | 0:00 |  |  |  | Karthik / Edward to send email
7 | BUSDEP | Run SUNDAY2 job manually using DO at 12:15AM after SUNDAY1 is completed without the Sunday Backup job PRODSUDP (Job # 312). SUNDAY2 will submit DAY_CLS_RUN and many other jobs. And must wait till all completes. |  |  |  | 2024-06-09 | Sun | 0:15 | 2:00 |  |  |  | Manish/Stanley
8 | BUSDEP | STOP/INACTIVE ROBOT at 2AM to ensure that no more batch jobs are submitted after 2AM. . |  |  |  | 2024-06-09 | Sun | 2:00 | 2:00 |  |  |  | Staples- Manish and Stanley
9 | BUSDEP | Ensure that no jobs are running in any batch subsystems (1) Stanley to HOLD REACTIVE jobs RBRBL_LNDC and RBRPL_SUGQ reactive jobs submitted in QWEEKEND jobq. (2) Ensure that CONSGN_CNV job is completed on BUSDEP (3) Cancel VRINCOME job in QBATCH job queue that is submitted from CONSGN_CNV job. (4) Put any other job on HOLD in all job queue if not needed to run on BUSDEP |  |  |  | 2024-06-09 | Sun | 2:15 | 2:30 | 0:30 |  |  | Staples- Stanley
10 | BUSDEP | P1 - BUSDEP SHUTDOWN (Quiese Systems) (Business applications, User interfaces, external comm interfaces) (Mimix remains active) | P1- Step 11 | P1-BUSDEP Shutdown |  | 2024-06-09 | Sun | 2:30 | 3:00 | 0:30 | 2:40 |  | Staples- Manish
11 | BUSDEPHA | P1 - BUSDEPHA SHUTDOWN (Quiese Systems) (Business applications, User interfaces, external comm interfaces - ensure nothing is running) (Mimix remains active) | P1-Step 12 | P1-BUSDEPHA Shutdown |  | 2024-06-09 | Sun | 2:30 | 3:00 | 0:30 |  |  | Staples- Manish
12 | BUSDEPHA | Confirm that all Latent Transactions applied on BUSDEPHA |  |  |  | 2024-06-09 | Sun | 2:30 | 3:15 | 0:45 |  |  | Mid-Range
13 | BOTH | P1-Preparation for Planned Role Swap - Green Screen Validate Mimix if Ready for Role Swap/Audit Verification | P1-Step 1-10 | N/A |  | 2024-06-09 | Sun | 3:15 | 4:00 | 0:45 |  |  | Mid-Range
14 | BUSDEP | P1 - Backup for Robot Schedule on BUSDEP (Send from BUSDEP to BUSDEPHA) ( Send BRMS data to BUSDEPHA) | P1-Step 13 | N/A |  | 2024-06-09 | Sun | 3:00 | 3:15 | 0:15 |  |  | Mid-Range | Will be send from BUSDEP to BUSDEPHA
15 | BUSDEPHA | P1 - Initiate Role Swap from BUSDEPHA | P1-Step 14-17 | N/A |  | 2024-06-09 | Sun | 3:15 | 4:00 | 0:45 | 6:00AM | 6:05AM | Mid-Range
16 | BUSDEPHA | P1 - Restore Robot Schedule on BUSDEPHA (only if required) | P1-Step 18 | N/A |  | 2024-06-09 | Sun | 4:00 | 4:00 | 0:00 |  |  | Mid-Range | Only executed if required.
17 | Network | P1 - Switch DNS and Network | P1-Step 19 | P1-Switch DNS and Network |  | 2024-06-09 | Sun | 4:00 | 4:15 | 0:15 |  | 6:20AM | Staples- call Wayne if early | Wayne Glen / Jerry Wang
18 | BUSDEPHA | P1 - BUSDEPHA Startup Assumes the Production Role and Startup of Application Environment and Readiness for Testing | P1-Step 20 | P1-BUSDEPHA Startup |  | 2024-06-09 | Sun | 4:15 | 7:30 | 3:15 | 6.35AM | 7.35AM | Staples-Manish | In Robot Scheduler
19 | BUSDEPHA | P1 - BUSDEPHA Validation IT Testing, Application Test by Selected users. Start all held FTP services(POS/SalesForce/FC Feed/Copy and print). Only validate items marked as Before GO Validation in Status column. At this point, BUSDEPHA in the production role | P1-Step 21 | P1-BUSDEP Validataion |  | 2024-06-09 | Sun | 7:30 | 8:30 | 1:00 |  |  | Staples-Endusers | Decide on what needs to validate from Business side ????
20 | BOTH | P1-Go NoGo Decision Checkpoint -Decision to accept BUSDEPHA in the Production Role | P1-Step 22 | N/A |  | 2024-06-09 | Sun | 8:30 | 8:45 | 0:15 |  |  | Mid-Range/Staples
21 |  | If NO GO Decision, then continue with steps in Switchback Plan below. | P1-Step 23 |  |  | 2024-06-09 | Sun
22 |  | If GO Decision, then continue with steps below. | P1-Step 24 | N/A |  | 2024-06-09 | Sun
23 | BUSDEPHA | P1-BUSDEPHA GO LIVE - Allow all business and stores to sign on, Start PT and Robot, Run 12AM to GO LIVE jobs that did not run, Put Robot back to original schedule | P1-Step 24 | P1-BUSDEPHA GO LIVE |  | 2024-06-09 | Sun | 8:45 | 10:45 | 2:00 |  |  | Mid-Range/Staples
24 | BUSDEPHA | P2- Planned Switch Step 2 Synchronization ( Start Replication from BUSDEPHA to BUSDEP) Transactions are sent to BUSDEP. | P2-Steps 1 to 4 | N/A |  | 2024-06-09 | Sun | 10:45 | 11:15 | 0:30 |  |  | Midrange
25 | BUSDEPHA | Monitor system and resolve any reported issues. This ends P1-Planned Switch. | P2-Step 25 | N/A |  | 2024-06-09 | Sun | 11:15 | 11:30 | 0:15 |  |  | Mid-range / Staples
SWITCHBACK
Step # | System | Activity | Section and Pages in RunBook | Excel Tab Name | Status | Start Date | Day | Estimated Start Time (EDT) | Estimated End Time (EDT) | Original Estimate Duration HH:MM | Actual Start Time | Actual End Time | Responsibility | Comments/Notes
Preparation Steps Immediately Prior to Switchback
|  | Manish - CR is created a week in advance and fully approved. Ensure that all vendor perm keys are available for both BUSDEP and BUSDEPHA Bart - no network activities Nasser/Stanley - no applications role out Stanley - Sunrise is shutdown for Maintenance.(could impact connectivity testing) Stanley - change management meeting to ensure nothing else is running that weekend. Stanely - Ensure that no store physical inventory on role swap weekend BOPIS - BOPIS can not be stopped due to US uses the same interface. POS/CopyPrint/SalesForce Team - Inform teams to stop putting sales, copy and print and sales force data to BUSDEP at 11:30 PM saturday nite. Nasser/Stanley/Curtis: Move the Consignment Conversion date to next weekend to avoid delay on Sunday. Nasser to send email to Curtis. Users Submitted Jobs: Users needs to be asked to stop submiting scheduled jobs as they can not be replicated to HA due to MIMIX limitation Helpdesk : Send email comminication to all AS400 users about BUSDEP outage due to DR roleswap. Digital Team: Post comminication on Staples.ca re BOPIS not available due to BUSDEP DR Roleswap. | [10 empty] | Staples
| BUSDEPHA | P0- Preparation for Switchback Mimix Audit_Verification and Remediation Health Check of Mimix before the Role Swap Validation Mimix is Ready to be Role Swaped. Capture ROBOT Jobs, Patrick Town Send Active Recrods, JOBSCD entries and Robot jobs runs from 3:00AM to 11:00AM on Sunday, Validate 3rd party license on BUSDEP | P0 Steps 1-9 | P3-Preparation for Switchback |  | June 17 to June 21 2024 | Mon- Fri | [5 empty] | Mid-Range/Staples | June 9,10 and 11 preparation
| BUSDEPHA | Hold VRM jobs CCL_WKLY, VRM_WKRPT, VRM_INVOIC and VRM_WKND from the RBO. They to be run on BUSDEP once live. |  |  |  | June 17 to June 21 2024 | Mon- Fri | [5 empty] | Naser
| BUSDEPHA | Hold SUNDAY2 job since it will be run manually using DO. |  |  |  | June 17 to June 21 2024 | Mon- Fri | [5 empty] | Manish
| BUSDEPHA | OMIT SYSSTRSBS job since we are not starting any subsystem after DAY_CLS_RN job completes for this weekend. SYSSTRSBS is a react job to DAY_CLS_RN job. |  |  |  | June 17 to June 21 2024 | Mon- Fri | [5 empty] | Manish
| BUSDEPHA | Cancel or Omit Sunday Backup Job as follows: (1) To skip Sunday backup job PRODSUDP ( Job # 312), comment out RBTBCHUPD JOBNUMBER(312) SCHEDULE(*DO) command from SUNDAY1 job that runs on 11:59PM on Sat night. PRODSUDP submits PROD1 and PROD2 job that reaches a syncpoint and sets the flag CHKPOINT to complete to start SUNDAY2 job. (2) Run SUNDAY2 job manually using DO. (3) SUNDAY2 will submit DAY_CLS_RN (4) DAY_CLS_RN job will submit CONSGN_CNV job (5) You must wait till this CONSGN_CNV job complete on BUSDEP. (6) CCL_WKLY, VRM_WKRPT, VRM_INVOIC and VRM_WKND jobs are dependent on CONSGN_CNV job and to be released on BUSDEP by Nasser after go live . |  |  |  | 2024-06-21 | Fri | [5 empty] | Staples
| BUSDEP | Cancel weekly backup BHA_WEEKLY from WRKJOBSCDE ( this caused 1 hr delay in this DR test ) |  |  |  | 2024-06-21 | Fri | [5 empty] | MIDRANGE
| BUSDEP | Allocate CPU and MEMORY back from BUSDEPHA to MAR4DEV1 LPAR to match with original BUSDEP |  |  |  | 2024-06-21 | Fri | [5 empty] | MIDRANGE
|  | Confirm SVC file ftped to PC application folder |  |  |  | 2024-06-22 | Sat | 20:30 | 0:00 |  |  |  | Stanley
1 |  | Stop all POS FTPs services |  |  |  | 2024-06-22 | Sat | 23:30 | 0:00 |  |  |  | Alain Miron / Joyal | 905-716-3377
2 |  | Stop all FC Sales Feed |  |  |  | 2024-06-22 | Sat | 23:30 | 0:00 |  |  |  | Devop team / Jerry / Satvika
3 |  | Stop all Salesforce orders feed | no confirmation needed |  |  | 2024-06-22 | Sat | 23:30 | 0:00 |  |  |  | Ken
4 |  | Stop all Copy and Print orders | no confirmation needed |  |  | 2024-06-22 | Sat | 23:30 | 0:00 |  |  |  | Bonny / Carol
5 |  | Stop Zuora Transactions/ Allstate / TSS | no confirmation needed |  |  | 2024-06-22 | Sat | 23:30 | 0:00 |  |  |  | Kevin Liang (Bo) / Jamie
6 |  | Stop Inventory Sync from Manhanton WMS |  |  |  | 2024-06-22 | Sat | 23:30 | 0:00 |  |  |  | Karthik / Edward to send email
7 | BUSDEPHA | Run SUNDAY2 job manually using DO at 12:15AM after SUNDAY1 is completed without the Sunday Backup job PRODSUDP (Job # 312). SUNDAY2 will submit DAY_CLS_RUN and many other jobs. And must wait till all completes. |  |  |  | 2024-06-23 | Sun | 0:15 | 2:00 |  |  |  | Manish/Stanley
8 | BUSDEPHA | STOP/INACTIVE ROBOT at 2AM to ensure that no more batch jobs are submitted after 2AM. . |  |  |  | 2024-06-23 | Sun | 2:00 | 2:00 |  |  |  | Staples- Manish and Stanley
9 | BUSDEPHA | Ensure that no jobs are running in any batch subsystems (1) Stanley to HOLD REACTIVE jobs RBRBL_LNDC and RBRPL_SUGQ reactive jobs submitted in QWEEKEND jobq. (2) Ensure that CONSGN_CNV job is completed (3) Cancel VRINCOME job in QBATCH job queue that is submitted from CONSGN_CNV job. (4) Put any other job on HOLD in all job queue if not needed to run |  |  |  | 2024-06-23 | Sun | 2:00 | 2:30 | 0:30 |  |  | Staples- Stanley
10 | BUSDEPHA | P3 - BUSDEPHA SHUTDOWN Switchback (Quiese Systems) (Business applications, User interfaces, external comm interfaces) (Mimix remains active) | P3-Step 12 | P3-BUSDEPHA Shutdown Switchback |  | 2024-06-23 | Sun | 2:30 | 3:00 | 0:30 | 2:10 | 3:10 | Staples- Manish
11 | BUSDEP | P3 - BUSDEP SHUTDOWN Switchback (Quiese Systems) (Business applications, User interfaces, external comm interfaces - ensure nothing is running) (Mimix remains active) | P3-Step 13 | P3-BUSDEP Shutdown Switchback |  | 2024-06-23 | Sun | 2:30 | 3:00 | 0:30 | 2:10 | 3:10 | Staples- Manish
12 | BUSDEPHA | Confirm that all Latent Transactions applied on BUSDEP |  |  |  | 2024-06-23 | Sun | 2:30 | 3:15 | 0:45 |  |  | Mid-Range
13 | BOTH | P3 -Preparation for Planned Role Swap Switch back Green Screen Validate Mimix if Ready for Role Swap/Audit Verification | P3-Step 1-11 | N/A |  | 2024-06-23 | Sun | 3:15 | 4:00 | 0:45 |  |  | Mid-Range
14 | BUSDEPHA | P3 - Backup for Robot Schedule on BUSDEPHA (Send from BUSDEPHA to BUSDEP) ( Send BRMS data to BUSDEP) | P3-Step 14 | N/A |  | 2024-06-23 | Sun | 3:00 | 3:15 | 0:15 |  |  | Mid-Range | Will be send from BUSDEP to BUSDEPHA
15 | BUSDEPHA | P3 - Initiate Role Swap back from BUSDEPHA | P3-Step 15-18 | N/A |  | 2024-06-23 | Sun | 3:15 | 4:00 | 0:45 |  |  | Mid-Range
16 | BUSDEP | P3 - Restore Robot Schedule on BUSDEP (only if required) | P3-Step 19 | N/A |  | 2024-06-23 | Sun | 4:00 | 4:00 | 0:00 |  |  | Mid-Range | Only executed if required.
17 | Network | P3 - DNS and Network Switchback | P3-Step 20 | P3-DNS and Network Switchback |  | 2024-06-23 | Sun | 4:00 | 4:15 | 0:15 | 4:00am | 4.30AM | Staples- call Wayne if early | Wayne Glen / Jerry Wang
18 | BUSDEP | P3 - BUSDEP Startup Switchback Startup HA Environment and Readiness for Replication. | P3-Step 21 | P3-BUSDEPHA Startup Switchback |  | 2024-06-23 | Sun | 4:15 | 7:30 | 3:15 | 4:30 | 6:00AM | Staples-Manish | In Robot Scheduler
19 | BUSDEP | P3 - BUSDEP Validation IT Testing, Application Test by Selected users. Start all held FTP services(POS/SalesForce/FC Feed/Copy and print). Only validate items marked as Before GO Validation in Status column. At this point, BUSDEP in the production role | P3-Step 22 | P3 - BUSDEP Validation Switchback |  | 2024-06-23 | Sun | 7:30 | 8:30 | 1:00 |  |  | Staples-Endusers | Decide on what needs to validate from Business side ????
20 | BOTH | P3-Go NoGo Decision Checkpoint -Decision to return to BUSDEP in original Production Role | P3-Step 23 | N/A |  | 2024-06-23 | Sun | 8:30 | 8:45 | 0:15 |  |  | Mid-Range/Staples
21 |  | If NO GO Decision, then continue with steps 4 to 16 in Switch Plan above | P3-Step 24 |  |  | 2024-06-23 | Sun
22 |  | If GO Decision, then continue with steps below | P3-Step 25 | N/A |  | 2024-06-23 | Sun
23 | BUSDEP | P3-BUSDEP GO LIVE - Allow all business and stores to sign on, Start PT and Robot, Run 3AM to Go LIVE AM job that did not run, Put Robot back to original schedule | P3-Step 25 | P3-BUSDEP GO LIVE |  | 2024-06-23 | Sun | 8:45 | 10:45 | 2:00 |  |  | Mid-Range/Staples
24 | BUSDEP | P3- Planned Switch Step 3 Synchronization ( Start Replication from BUSDEP to BUSDEPHA) Transaction are sent to BUSDEPHA | P3-Step 26 | N/A |  | 2024-06-23 | Sun | 10:45 | 11:15 | 0:30 |  |  | Midrange
25 | BUSDEP | Monitor system and resolve any reported issues. This ends P3 - Planned Switchback | P3-Step 27 | N/A |  | 2024-06-23 | Sun | 11:15 | 11:30 | 0:15 |  |  | Mid-range / Staples

## P0 PREPERATION FOR SWICH
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
[5 empty] | BUSDEPHA | Apply or Verify vendor software license keys as follows: ( Turn off MIMIX replication if needed for some products due to file lock on BUSDEPHA )
ROBOT SCHEDULE
· ADDLIBLE ROBOTLIB
· CALL RBT240
· Press F11 to cut/paste the license code in the License Code field and press Enter to save the license keys.
[6 empty] | ZUVD184EE7C94W5X63KWY6YW1AV6L03S68BZ6WYF+ZUJ59BCUXKZNE9BRVDGS6XGEB3G*FHGXAG | Completed - not replicated
ROBOT ALERT
· ADDLIBLE RBTALRLIB
· CALL RBA250
· Press F11 to cut/paste the license code in the License Code field for appropriate lpar as below and press Enter to save the license keys
[6 empty] | NCSA393A44WEAW0IQKUDVQV+AV+Q7Q7EQSF0QNSFH9N6AULG67SRMGUIYRH9WVJ9QFE9FNHC3X9 | Completed - not replicated
ROBOT CONSOLE
· ADDLIBLE RBTCONLIB
· CALL RBC245
· Press F11 to cut/paste the license code in the License Code field for appropriate lpar as below and press Enter to save the license keys
[6 empty] | ZKM6589E90SHII2P8B0EQ8Q4G0T8QBG38ZY88EEP7IDWGN4X1SD7HAN5FZ0F6TSFAK3F+23KSKF | Completed - not replicated
IMAIL
· These codes are for IMAIL30 product and same code were applied for IMAIL product as well.
· ADDLIBLE IMAIL ( for BUSDEP and BUSDPHA )
· ADDLIBLE IMAIL30 ( only on MAR4DEV1 )
· Type REGISTER and press Enter
· From the Module Registration Screen, Cut Paste keys for IMAIL and IMAIL30 products on appropriate lpars as follows:
· Press F10 to update
[6 empty] | IMAIL: 3Z;18XgCXgG1Pigp6GG7CC1P07pxgP;X7Vg3CT29CCTc | Completed - not replicated
[6 empty] | IMAIL30: 3Z;18XgCXgG1Pigp6GG7CC1P07pxgP;X7Vg3CT29CCTc | Completed - not replicated
DBU11
· ADDLIBLE DBU11
· Type DBUSEC and copy and paste the bolded key below.
· Press Enter
[6 empty] | 1909F0 DD8A29 2C7301 5103 | Completed - not replicated
IMPLEMENTOR
· ADDLIBLE IMPRCV
· Cut Past keys as follows for appropriate lpar
· Cut and past this entire line from command line
[6 empty] | RESET SECSTR(00062900 70900400 04804102 60669999 64895395 19900034) LIB(IMPRCV) | Completed, Can not view the keys but says *SAME
MARKMAGIC Ver 10
· Sign on as QSECOFR
· Enter command MRKMAG100/SETMMPRM
· Press F8 to enter key information
BUSDEPHA
*PERM RUN Labels Prod: MM100 Mod: 42A S/N: 7888CD0 Proc: P20
[6 empty] | Exp 99/99/99 LPAR: 3 Users: 999999 Ptrs: 999999 Key: C4C80 B5CD2 F5426 4C501 | Completed - not replicated
*PERM Opt-PDF Prod: MM100 Mod: 42A S/N: 7888CD0 Proc: P20
[6 empty] | Exp 99/99/99 LPAR: 3 Users: 999999 Ptrs: 999999 Key: D6968 7222B 68BF4 79501 | Completed - not replicated
OPENTEXT
· ADDLIBLE ZMODLIB10
· Type setzmlic copy and paste your license codes
[6 empty] | nuBridges EDIIP . . . . . . . . . . . . 9999 Jx/3/zIktLwI | Completed. does not display the key but says PERM
[6 empty] | nuBridges HTTP Client . . . . . . . . . 9999 AADz/+lbCXcM | Completed. does not display the key but says PERM
GENTRAN
· MAR4DEV1 keys were used on BUSDEPHA box due to it is serial number-based keys
· ADDLIBLE G3X5PGM
· ADDLIBLE G3X5DTA
· Type EXTEND and F4 prompt and input the following
Extension Code for your Product
[6 empty] | Extension Code . . . . . . . . . . 8 49 99C AD 99878920 | Completed. Can not validate keys due to blank fields, applied HA keys. Call vendor to display keys
For FTP enter ACTFTP and F4 prompt and input the following Activation Code
[6 empty] | Activation Code. . . . . . . . . . 7 990 989D A988C9 42 | Completed. Can not validate keys due to blank fields, applied HA keys. Call vendor to display keys
TAATOOLS
· MAR4DEV1 keys were used on BUSDEPHA box due to it is serial number-based keys
· ADDLIBLE TAATOOL
[6 empty] | · Type CHGTAAKEY and press Enter | Completed.Not Replicated
[6 empty] | · The key information should be entered as: | Address: Staples were not changed from BUSDEP. Busdep has Staples
[6 empty] | Key value 59 1E 44 79 63 55 7A 43 5D 9D A5 FE 90 B7 0D 94 15 9B BA 1F 76 00 D4 E6 29 2B 82 D1 56 34 | Can not validate keys due to blank fields, applied HA keys, call vendor to display keys
[6 empty] | Position 01 02 03 04 05 06 07 08 09 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 | Can not validate keys due to blank fields, applied HA keys, call vendor to display keys
PSAudit and PSSecure
· Sign on as QSECOFR.
· Addlible PSCOMMON
· PSMENU
· Take option 80 Enter Access Codes
· Enter below PERM Keys Provided by Tony from Micro Foucs
[6 empty] | EWEPQ RWEPW TWEPE 8DB8C 03DS8 PPCPW | Completed. Not replicated, Correct HA Keys applied, only shows CPU updated and no errors
PATRICK TOWNSEND
· ADDLIBLE ALLFTM100
· GO AMMAIN
· Take Option 1 : Installation
· Take Option 2: Enter FTP Manager perm code AND Take Option 4: Enter PGP Option perm code
· Cut Paste keys as follows for appropriate menu option and lpar, Press Enter to save the keys.
[6 empty] | FTP Manager Code: 3A64BDB728574DA41D9A0BB7F1B73216 | Completed. Not replicated.
[6 empty] | PGP Option Code: 0F65A93535EE7E2B41ED1709D505D339 | Completed. Not replicated.
PGP C9 Keys
[6 empty] | Download the PGP C9 Files from email sent by Kris for BUSDEPHA on 2020/12/15 (BUSDEPHA TSPGP_License - 7888CD0.003.txt) | Upload this PGP license file to BUSDEPHA in /PGM IFS folder
FTP the file to the /PGP on the IFS from C: drive location where PGP C9 file is downloaded.
Start-> Run->FTP BUSDEPHA
[6 empty] | USERID (your user ID) | BUSDEPHA key file should look as below
[6 empty] | Password (your password) | Browse : /pgp/TSPGP_License.txt
[6 empty] | BINARY | Record : 1 of 2 by 18 Column : 1 132 by 131
[6 empty] | cd /PGP | Control :
lcd c:\
[6 empty] | put TSPGP_License.txt | ....+....1....+....2....+....3....+....4....+....5....+....6....+....7....+....8....+....9....+....0....+....1....+....2....+....3.
[6 empty] | quit | ************Beginning of data**************
[6 empty] | · Go to the main menu: | 2L7sU6ReTz06QcUqPtXAbCb5RC3DIYZ9vp8dBFg6yQIQfJ4+UP13eB+fyi0r46LHUNUl0Pqu2x5WA/K+gKYf5anNxfZ3xZpizPCAJQWrZlJdDfQ7mx5vd3f7JVtxpnKHUNUl
[6 empty] | · ADDLIBLE ALLFTM100 | 0Pqu2x5WA/K+gKYf5fJwjCJtk8x+birHw/yciPia4fihYpoHkDO2JbYx72I4SesB4/3o6UfK4EAxlZzFhpJI83q4VL8db8nEssePAqE=
[6 empty] | · GO AMMAIN | ************End of Data********************
· Option 1 for installation
· Option 12 to install PGP Command line 9 license
· Make the following changes:
[6 empty] | PGP License File: /pgp/TSPGP_License.txt | Can not validate due to blank screen |  | HA keys was FTPed to /PGP folder IFS folder
[6 empty] | (If you receive an error message when trying to install the license, try pressing F10 after the license file.) | Completed. Not replicated
Customer Name: See Below
Email: See Below
(Please reference the above screenshot to verify the customer name and email. This is case-sensitive and must be entered exactly as in the screenshot.)
Press Enter
It will say PGP License installed at the command line.
[5 empty] | BUSDEP | Check that BUSDEPHA has the matching HOST Table Entries as BUSDEP. MIDRANGE to replicate QUSRSYS/QATOCHOST. |  | MIDRANGE
[5 empty] | BUSDEP | Check that BUSDEPHA has the matching WRKDIRE entries as BUSDEP
[5 empty] | BUSDEP | Capture all ROBOT Scheduler jobs list using ROBOT GUI as follows
Click on RBT Scheduler 13 GUI Icon on desktop
From the top menu, click on Job Schedule List (Icon in Red color just above the name column )
Right click on one of job displayed
From the Drop menu, select Select All to highlight all jobs in Yelllow color
Right Click again on highlighted job and select Copy to Clipboard
Select Yes for Include the Header screen pop up
All records will be copied to Clipboard and ready to be pasted in Excel
Paste all records in this excel at the bottom
(See the list at bottom on this Excel)
[5 empty] | BUSDEP | Run a query SECMANISH/RBTOVRRIDE to to create an output file called RBTOVRRIDE |  | This lis contains all jobs that do not have any override code and will be used to put the job status from HOLD to RELEASE in tab P1 BUSDEPHA GO LIVE
(See the tab ROBOT job with no override )
[5 empty] | BUSDEP | Capture all Patrick Townsend Active Jobs listing running these SQL statements |  | This list contains only ACTIVE PT Records
[5 empty] | FTP Definitions | SELECT * FROM allftm100/anftpd WHERE fdstat='1' ORDER BY fdname
[5 empty] | Scan DIR | SELECT DRNAME, DRDESC, DRSTAT FROM allftm100/anDIRS WHERE drstat='1' ORDER BY drname
[5 empty] | Auto Scan | SELECT * FROM allftm100/anscan WHERE scstat='1' ORDER BY scname
[6 empty] | Update SEMANISH/QSQLSRC(DRUPDPTSTS) member with only active PT records using this list created. |  | This SECMANISH/QSQLSRC(DRUPDPTSTS) meber contains SQL statements that will be run using SECMANISH/QCLSRC(DRUPDPTSTS) in P1 BUSDEPHA GO LIVE tab
(See the list at bottom of this Excel)
[5 empty] | BUSDEP | Capture all IBM WRKJOBSCDE Entries that on SCD
[5 empty] | BUSDEP | On BUSDEP, Run a query SECMANISH/SUNJOBS using WRKQRY to create a SECMANISH/SUNJOBS file to list all Sunday jobs | Not being done now due to Stanley has a schedule to run missed Sunday jpn during DR swith hours
Download SUNJOBS file in SUNJOB_LATEST tab and sort by Sched_Run_time_1
Copy 4am to 10AM jobs from SUNJOB_LATEST tab to tab Vlookup ( in Red )
Copy 4am to 10AM jobs from ALL SUNDAY JOBS NEW to tab vlookup ( in Blue)
Find the new added jobs using vlookup in green, =N/A jobs in Vlookup tab here ( in Green )
Copy these new jobs from SUNJOB_LATEST to ALL_SUNDAY JOBS NEW to proper row loacation ( in Red )
Decide on action to take on new added jobs via DO or Skip, talk to Nasser and Stanley for action
Copy these final list of 4 am to 10am jobs with action column to DOJOBS UPLOAD
Upload DOJOBS UPLOAD to BUSDEP in DOJOBS file
These MISSED jobs to be run ON HA after switch since they were mised on BUSDEP between 4am to 10 AM while switching the role.
CL to run is SECMANISH/DRDOJOBS in tab P1 BUSDEPHA Go LIVE
BUSDEP Robot Scheduler Jobs List before Switch ( Original State ) |  |  |  |  | As of May 31,2023
Type | Name | Override(SCHOVR) | Reactive | Schedule Code | Attributes | Description | Time | M T W TH F ST SN | Application | Group Name
Group | @BU_RLS | HOLD | REACT |  |  | Error Recovery | 0:00 | Y Y Y Y Y . . | BACKUP | @BU_RLS
Command | @CLR_IFSPT | HOLD |  |  |  | H*Clear IFS Transfer Fldr | 0:00 | . . . . . . . | BD-APPLICA
Command | @SALESTEMP | HOLD |  |  |  | Sales Posting-On Demand | 0:00 | . . . . . . . | APPLN
Group | @SALESWDAY |  | REACT |  |  | Sales Process WeekDay | 0:00 | Y Y Y Y Y . . | SALESAUDIT | @SALESWDA1
Group | @SALESWEND |  | REACT |  |  | Sales Process WeekEnd | 0:00 | . . . . . Y Y | SALESAUDIT | @SALESWEND
Command | AGILENCETL | HOLD |  |  |  | **On Demand Agilence TLOG | 0:00 | . . . . . . . | BUSDEP
Command | AIRM_WEEK | HOLD | REACT |  |  | H*Send Wkly Feed AIRMILES | 0:00 | Y . . . . . .
Command | ARRECYCLE |  |  |  |  | Recycle Active Reasoning | 0:00 | . . . . . . .
Command | CKPURGE |  | REACT |  |  | Check Resource RBPURGE_DH | 0:00 | . . . . . . . | RBC
Command | CPC_PRC_OD | HOLD |  |  |  | On Demand-Clone CPC_PRICE | 0:00 | . . . . . . . | BD-APPLICA
Command | DAILY_BU | HOLD |  |  | GroupMember | H*Daily backup STRBKUBRM | 0:00 | . Y Y Y Y . . | BACKUP
Command | DRSHUTDOWN | HOLD |  |  |  | H*BUSDEP SHUTDOWN FOR DR | 0:00 | . . . . . . .
Command | DRSTARTSYS | HOLD |  |  |  | H*BUSDEP START UP FOR DR | 0:00 | . . . . . . .
Command | EM_EP_AUD |  |  |  |  | Eml Qtrly Emg Prf Requstr | 0:00 | . . . . . . . | BDAPPS
Command | EXTSLSB1OD | HOLD |  |  |  | H*BLD Ext Sls-1 On Demand | 0:00 | . . . . . . . | BDAPPS
Command | E3_EXTRACT | HOLD |  |  |  | On Demand-Ext E3 SLS Data | 0:00 | . . . . . . . | LEARN
Command | F100906001 | [5 empty] | 0:00 | . . . . . . .
Command | F100906001 | [5 empty] | 0:00 | . . . . . . .
Command | HBT_DWNDOD | HOLD |  |  |  | H*FTP HBT-On Demand/Hold | 0:00 | . . . . . . . | HBT_DWND
Command | HJQ_OLORD1 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #1 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD2 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #2 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD3 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #3 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD4 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #4 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD5 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #5 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD6 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #6 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD7 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #7 | 0:00 | . . . . . . . | BD_APP
Command | HLDSDI_JB1 |  |  |  | GroupMember | Hold QBSDI_JB1 job queue | 0:00 | . . . . . . . | SDI
Command | HLDSDI_UPL |  |  |  | GroupMember | Hold QBSDI_UPL job queue | 0:00 | . . . . . . . | SDI
Command | JDA |  | REACT |  |  | Unrestrict JDA | 0:00 | . . . . . . Y
Command | MPOS0330RS | HOLD |  |  |  | H*Rsnd Full PLU-MPOS-330 | 0:00 | . . . . . . . | BDAPPLN
Command | OF_EML_RC |  | REACT |  |  | Outstndng Reconcil Vari | 0:00 | . . . . . . . | BUSDEP
Command | PCU000MP | HOLD | REACT |  |  | Profile Cleanup Utility. | 0:00 | . . . . . . . | IT
Command | PLNSLS_NEW | HOLD |  |  |  | H*FTP WK SL New-On Demand | 0:00 | . . . . . . . | BDAPPS
Command | PRODMODP |  | REACT |  |  | Daily Monday Backup | 0:00 | Y . . . . . . | BRMS
Command | PRODSOX2DP |  | REACT |  |  | PRODSOX to RPT2WEB | 0:00 | Y Y Y Y Y Y Y | 400 ANALST
Command | PRODSUDP |  |  |  |  | Daily Sunday Backup | 0:00 | . . . . . . Y | BRMS
Command | PURGE_DHD | HOLD | REACT |  |  | H*Purge DHD Delivery Ord | 0:00 | . . . . . . . | TRANSFER
Command | RBL_LNDCT2 |  | REACT |  |  | Rebuild Store Landed Cost | 0:00 | . . . . . . Y
Command | RBTBLDFCT |  |  |  |  | Forecast build | 0:00 | . . . . . . .
Command | RBT34501 |  |  |  |  | Work Schedule by Time Sch | 0:00 | . . . . . . . | ROBOT
Command | RBT34502 |  |  |  |  | Weekly Work Schedule by C | 0:00 | . . . . . . . | ROBOT
Command | RBT34701 |  |  |  |  | Report Distribution by Da | 0:00 | . . . . . . . | ROBOT
Command | RBT34702 |  |  |  |  | Report Distribution by Re | 0:00 | . . . . . . . | ROBOT
Command | REP00006 | [5 empty] | 0:00 | . . . . . . . | REP
Command | REP29701No |  |  |  |  | Report Archive Status rep | 0:00 | . . . . . . . | REP
Command | RJQ_OLORD1 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #1 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD2 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #2 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD3 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #3 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD4 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #4 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD5 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #5 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD6 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #6 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD7 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #7 | 0:00 | . . . . . . . | BD_APP
Command | RLSSDI_JB1 |  |  |  | GroupMember | Release QBSDI_JB1 jobq | 0:00 | . . . . . . . | SDI
Command | RLSSDI_UPL |  |  |  | GroupMember | Release QBSDI_UPL jobq | 0:00 | . . . . . . . | SDI
Command | RPL_SUGQTY |  | REACT |  |  | CALCULATION OF ORDER QTY. | 0:00 | . . . . . . Y | LEARN
Command | R000000022 |  |  |  |  | Check Resource RBHBT_DWND | 0:00 | . . . . . . . | RBC
Command | R000000029 |  |  |  |  | Check Resource BRMSSBS | 0:00 | . . . . . . . | BUSDEP
Command | R000000042 |  |  |  |  | Check Resource QINTER | 0:00 | . . . . . . . | BUSDEP
Command | R000000158 |  |  |  |  | Check Resource BRMSJOBQ | 0:00 | . . . . . . . | BUSDEP
Command | R000000233 |  |  |  |  | Check Resource SCAN_DIRS | 0:00 | . . . . . . . | TOWNSEND
Program | SDI860CL |  |  |  | GroupMember | Set PNDSALFIL *dtaara | 0:00 | . . . . . . . | SALESAUDIT
Program | SDI865CL |  |  |  | GroupMember | Submit SALESsssss jobs | 0:00 | . . . . . . . | SALESAUDIT
Command | SUNDAY2 |  | REACT |  |  | Post Sync-Point Jobs +HBT | 0:00 | . . . . . . Y
Command | SYSAUDALOB | HOLD |  |  |  | ALLOBJ user audit report | 0:00 | . . . . . . .
Command | SYSBKUREST | HOLD |  |  |  | Restrict system no bkup | 0:00 | . . . . . . .
Command | SYSBKU2 |  |  |  |  | Bring system up | 0:00 | . . . . . . .
Command | SYSBKU2YE | HOLD |  |  |  | H*Bring system up | 0:00 | . . . . . . .
Command | SYSCCCAUTH | HOLD |  | EVERY |  | Run Agent resetauth.sh | 0:00 | Y Y Y Y Y Y Y
Command | SYSCHKCTL |  |  |  | GroupMember | Check Controllers | 0:00 | . . . . . . . | BUSDEP
Command | SYSCHKJOB |  |  |  | GroupMember | Check Critial Jobs | 0:00 | . . . . . . . | BUSDEP
Command | SYSCHKJOBQ |  |  |  | GroupMember | Check Resource JOBQ | 0:00 | . . . . . . . | BUSDEP
Command | SYSCHKLIN |  |  |  | GroupMember | Check Com Lines | 0:00 | . . . . . . . | BUSDEP
Command | SYSCHKSBS |  |  |  | GroupMember | Check Subsystems | 0:00 | . . . . . . . | BUSDEP
Command | SYSE3LIBS | HOLD |  |  |  | E3 libraries save | 0:00 | . . . . . . . | BRMS
Command | SYSFLTREC | HOLD |  |  |  | Collect BRMS flight recs | 0:00 | . . . . . . .
Command | SYSJOBTST |  |  |  |  | test | 0:00 | . . . . . . .
Command | SYSMAFSBMM |  | REACT |  |  | Submit Final monthly jobs | 0:00 | . . . . . . Y
Command | SYSMAFSBMW |  | REACT |  |  | Submit Final weekly jobs | 0:00 | . . . . . . Y
Command | SYSNETIQPR |  | REACT |  |  | NetIQ Purge Deleted Prfs | 0:00 | . . . . . . .
Command | SYSODBCPRG |  | REACT |  |  | ODBC Log Purge > 2 Years | 0:00 | . . . . . . .
Command | SYSODBCRST |  | REACT |  |  | ODBC 90 Day Reset | 0:00 | . . . . . . .
Command | SYSOPSMAIL | HOLD | REACT |  |  | EMAIL GOC after WKend Prc | 0:00 | . . . . . . Y
Command | SYSPRFDIS |  | REACT |  |  | Profile Disable Utility. | 0:00 | . . . . . . . | IT
Command | SYSPT_APY | HOLD |  |  |  | PTownsend Apply PTFs | 0:00 | . . . . . . .
Command | SYSSTRSBS |  | REACT |  |  | Start System Sunday | 0:00 | . . . . . . Y
Command | SYSSTRSBS2 |  | REACT |  |  | Start System Mon-Fri | 0:00 | . . . . . . .
Command | SYSSWPLOAD | HOLD |  |  |  | Load Post Role Swap Tasks | 0:00 | . . . . . . .
Command | TSG200YP | HOLD |  |  |  | H*Switch Fiscal Calendar | 0:00 | . . . . . . . | SCHEDULING
Command | VRM_WKND |  | REACT |  |  | VRM Weekend run | 0:00 | . . . . . . Y
Command | HBT_CUS#WP |  |  |  |  | *Purge/Create TXECCT WKN | 0:01 | . . . . . Y Y
Command | HBT_DWND_M |  |  |  |  | *FTP HBT-DLY if FTP:Mon | 0:01 | Y . . . . . . | HBT_DWND
Command | ZAACL85 |  |  |  |  | Subsys gen info | 0:01 | Y . . . . . . | PSAUDIT
Command | CKHBTDWN_M |  |  |  |  | Check Resource RBHBT_DWND | 0:02 | Y . . . . . . | RBC
Command | CKDLYSAL |  |  |  |  | Check Resource DLY_SALRPT | 0:05 | Y Y Y Y Y Y . | RBC
Command | DAYCLOSE |  |  |  |  | Day Close | 0:05 | Y Y Y Y Y Y . | DAILY
Command | LCT_UPL1 |  |  |  |  | Upload Labor Cost Xfer | 0:05 | Y . . . . . . | BD APPLN
Command | PERFNAVDR | HOLD |  |  |  | Data Reduction | 0:05 | Y Y Y Y Y Y Y | TECSUPPORT
Command | ZAACL28JD |  |  |  |  | Chgs to USER of a JOBD | 0:05 | Y . . . . . . | PSAUDIT
Command | ZAACL7701 |  |  |  |  | System Values | 0:05 | . . . . . . Y | PSAUDIT
Command | ZAACL7702 |  |  |  |  | Pgms that Adopt QSECOFR | 0:05 | . . . . L . . | PSAUDIT
Command | CH_MSGMON1 |  |  | EVERY |  | Check Job has MSGW-MON-#1 | 0:00 | Y . . . . . . | BD_APP
Command | CKDAYCLO |  |  |  |  | Check Resource RBDAYCLOSE | 0:06 | Y Y Y Y Y Y . | DAYCLOSE
Command | RSOSLOGI |  |  |  |  | Remove Mbr for SOSLOGI | 0:10 | . . . . . Y . | BDAPPLICAT
Command | RSOSLOGO |  |  |  |  | Remove Mbr for SOSLOGO | 0:10 | . . . . . Y . | BDAPPLICAT
Command | ZAACL28SM |  |  |  |  | System Management Changes | 0:10 | Y . . . . . . | PSAUDIT
Command | ZAACL7703 |  |  |  |  | Network Attributes | 0:10 | . . . . . . Y | PSAUDIT
Command | ZAACL98 |  |  |  |  | Pgms adopt QSEC like auth | 0:10 | . . . . L . . | PSAUDIT
Command | HBT_DWND_D |  |  |  |  | *FTP HBT-DLY if FTP:Tu-Sa | 0:15 | . Y Y Y Y Y . | HBT_DWND
Command | ZAACL28VV |  |  |  |  | Service Status Changes | 0:15 | Y . . . . . . | PSAUDIT
Command | ZAACL7715 |  |  |  |  | Local Hardware | 0:15 | . . . . . . Y | PSAUDIT
Command | CKHBTDWN |  |  |  |  | Check Resource RBHBT_DWND | 0:16 | . Y Y Y Y Y . | RBC
Command | ZAACL7709 |  |  |  |  | Output Queue Descriptions | 0:20 | . . . . . . Y | PSAUDIT
Command | ZAACL93 |  |  |  |  | Network job entries | 0:25 | . . . . . . Y | PSAUDIT
Command | CKUPDINV |  |  | EVERY |  | Check Resource UPD_INVLBL | 0:00 | Y Y Y Y Y Y . | RBC
Group | @BU_MON | HOLD |  |  |  | Backup (Mon) | 0:30 | Y . . . . . . | BACKUP | @BU_MON
Command | HBT_CLNW |  |  |  |  | Cleanup issued tax cust. | 0:30 | Y . . . . . . | HBT
Command | PERFNAVDR | HOLD |  |  |  | Perf Nav Data Reduction | 0:30 | Y Y Y Y Y Y Y | MPG
Command | ZAACL88 |  |  |  |  | Dist direct entries | 0:30 | . . . . . . Y | PSAUDIT
Command | ZAACL28PS |  |  |  |  | Profile Swap | 0:40 | . . . . L . . | PSAUDIT
Command | ZAACL28VL |  |  |  |  | Account Limits Exceeded | 0:45 | . . . . L . . | PSAUDIT
Command | SYSBKUP |  |  |  |  | Reg Weekly Shutdown IPL | 0:50 | . . . . . Y .
Command | SYSBKUPPE |  |  |  |  | Period End Shutdown IPL | 0:50 | . . . . . Y .
Command | SYSBKUPQE |  |  |  |  | Quarter End Shutdown IPL | 0:50 | . . . . . Y .
Command | SYSBKUPYE | HOLD |  |  |  | H*Year End Shutdown IPL | 0:50 | . . . . . Y .
Command | ZAACL28OR |  |  |  |  | Object Restore | 0:50 | Y . . . . . . | PSAUDIT
Command | CH_MSGSAT1 |  |  | EVERY |  | Check Job has MSGW-SAT-#1 | 0:00 | . . . . . Y . | BD_APP
Command | ZAACL74 |  |  |  |  | Grp Prfs w/any Spec Auth | 0:55 | . . . . L . . | PSAUDIT
Command | BUSDEP | HOLD |  |  |  | H*DasdPlus Survey | 1:00 | Y . . . . . . | LEARN
Command | HBT_CUS#DP |  |  |  |  | *Purge/Create TXECCT WDAY | 1:00 | Y Y Y Y Y . .
Command | PERFNAVPM | HOLD |  |  |  | Perf Nav Monitor | 1:00 | Y Y Y Y Y Y Y | MPG
Command | SYSILMTSSC |  |  |  |  | ILMT Software Scan | 1:00 | Y Y Y Y Y Y Y
Command | SYSTHRWKLY | HOLD |  |  |  | Weekly threaded save | 1:00 | . . . . . Y .
Command | ZAACL7718 |  |  |  |  | User Profile = Password | 1:00 | . . . . L . . | PSAUDIT
Command | ZAACL80UA |  |  |  |  | Group Profiles | 1:05 | . . . . L . . | PSAUDIT
Command | ZAACL80UB |  |  |  |  | Prf Parm Analysis | 1:10 | . . . . L . . | PSAUDIT
Command | ZAACL80UC |  |  |  |  | Prf Password Exp not 0 | 1:15 | . . . . L . . | PSAUDIT
Command | ZAACL80U3 |  |  |  |  | Prfs without Limited Cap | 1:20 | . . . . L . . | PSAUDIT
Command | ZAACL80U4 |  |  |  |  | Prfs SECADM SECOFR ALLOBJ | 1:25 | . . . . L . . | PSAUDIT
Command | CH_MSGSUN1 |  |  | EVERY |  | Check Job has MSGW-SUN-#1 | 0:00 | . . . . . . Y | BD_APP
Command | ZAACL82 |  |  |  |  | Attn key pgms adopt auth | 1:30 | . . . . L . . | PSAUDIT
Command | ZAACL84 |  |  |  |  | Prfs attn key pgms | 1:35 | . . . . L . . | PSAUDIT
Command | ZAA3010C |  |  |  |  | Profile Integrity | 1:40 | . . . . L . . | PSAUDIT
Command | HLD_DCJOBQ |  |  |  |  | Hold DCDIRECT JOBQ | 1:55 | Y Y Y Y Y . . | BDAPPLN
Command | SYSCHGTIME | HOLD |  |  |  | DST TIME CHANGE -1 HR | 1:55 | . . . . . . Y
Command | REORGFILE |  |  |  |  | REORGANIZE FILES | 2:00 | . Y . . . . . | LEARN
Command | SYSUSRPRF2 |  |  |  |  | DSPUSRPRF to ITTOOLS | 2:00 | Y Y Y Y Y Y Y
Command | ZAACL28CP2 |  |  |  |  | Action To User Prfs | 2:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL28DS |  |  |  |  | DST Password Reset | 2:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL28PA |  |  |  |  | Pgms Chgd Adopt Owner Aut | 2:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL28SV |  |  |  |  | Changes To System Values | 2:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL33AL |  |  |  |  | Cmds For Limited Users | 2:00 | . . . . L . . | PSAUDIT
Command | PERFNAVPG | HOLD |  | DAYNO |  | Reduced Data Purge | 2:30 | 1 | TECSUPPORT
Command | PERFNAVPG | HOLD |  |  |  | PN Reduced Data Purge | 2:30 | . . . . . 1 . | MPG
Command | RSOSLOGIWE |  |  |  |  | Remove Mbr for SOSLOGI-WE | 2:40 | . . Y . . . . | BDAPPLICAT
Command | RSOSLOGOWE |  |  |  |  | Remove Mbr for SOSLOGO-WE | 2:40 | . . Y . . . . | BDAPPLICAT
Command | DCA1_SLSD2 |  |  | EVERY |  | CA Sales Fri<2:41*10 min | 0:00 | . . . . Y . .
Command | ENDQPGMR |  |  |  |  | ENDQPGMR | 2:50 | . Y Y Y Y . . | LEARN
Command | BPS_OK_NO1 |  |  | EVERY |  | OTH-Refresh BPS Alloc Qty | 0:00 | . Y Y Y Y . .
Command | CH_MSGT2F1 |  |  | EVERY |  | Check Job has MSGW-T2F-#1 | 0:00 | . Y Y Y Y . . | BD_APP
Group | @BU_WDAY | HOLD |  |  |  | Backup (Tue/Wed/Thu/Fri) | 3:00 | . Y Y Y Y . . | BACKUP | @BU_WDAY
Command | DCA_PURGE |  |  |  |  | Wkly Purge DCAINVTRN Mbr | 3:00 | Y . . . . . .
Command | PRODDP |  |  |  |  | Daily Tue-Fri Backup | 3:00 | . Y Y Y Y . . | BRMS
Command | SYSSTPBASE | HOLD |  |  |  | Dasd plus Baseline Survey | 3:00 | . . . . . 1 .
Command | PERFNAVDS | HOLD |  |  |  | Lib and Obj Sizes | 3:30 | . . . . . . Y | TECSUPPORT
Command | PERFNAVDS | HOLD |  |  |  | PN Lib and obj sizes | 3:30 | . . . . . . Y | MPG
Command | RLS_DCJOBQ |  |  |  |  | Release DCDIRECT JOBQ | 3:30 | Y Y Y Y Y . . | BDAPPLN
Command | EXTSL_R1 | HOLD |  |  |  | H*Eml Ext SLS Rpt-R1 | 3:45 | Y . . . . . . | BDAPP
Command | RBL_LNDCT1 |  |  |  |  | Rebuild Store Landed Cost | 3:59 | Y Y Y Y Y Y .
Command | BPS831CL |  |  |  |  | *Operational Excellence | 4:00 | Y Y Y Y Y Y Y | REPORTING
Command | WK_DST_MON |  |  |  |  | WKLY DISTRICT RESULTS-MON | 4:00 | Y . . . . . . | LEARN
Command | WK_RDBFEED | HOLD |  |  |  | H*DashBoard Weekly | 4:00 | Y . . . . . . | BUSDEP
Command | CATMANGETD |  |  |  |  | Dly-Get CATMAN Files | 4:05 | Y Y Y Y Y . Y
Command | CATMANLSTD |  |  |  |  | Dly-Get CATMAN File LST | 4:05 | Y Y Y Y Y . Y
Command | E3_BD_ZAP |  |  |  |  | E3 Weekly Report | 4:05 | Y . . . . . . | LEARN
Command | MOOSEAGGR1 |  |  |  |  | MOOSE AGGREGATE UPDATE | 4:10 | Y Y Y Y Y . . | LEARN
Command | MOOSEAGGR2 |  |  |  |  | *MOOSE AGGREGATE UPD WKN | 4:10 | . . . . . Y Y | LEARN
Command | EXTSL_R2 |  |  |  |  | Eml Ext. SLS Rpt-Reg02 | 4:15 | Y . . . . . . | BDAPP
Command | EXTSL_R5 |  |  |  |  | Eml Ext. SLS Rpt-Reg05 | 4:15 | Y . . . . . . | BDAPP
Command | E3_FREEZE |  |  |  |  | *E3 DAY-END PROCESS | 4:15 | Y Y Y Y Y Y Y | LEARN
Command | ACK_EDI |  |  |  |  | EDI Acknowledgment Update | 4:30 | Y Y Y Y Y Y .
Command | E3_DAYEND |  |  |  |  | *E3 DAY-END PROCESS | 4:30 | Y Y Y Y Y Y Y | LEARN
Command | MONINVBL3A | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 4:30 | . Y Y Y Y . . | BD APPLN
Command | POS_PURGE |  |  |  |  | O*Purge Old Sales Data | 4:30 | Y Y Y Y Y Y Y | BD-APP
Command | PURG_RPL |  |  |  |  | Purge Mult Mbr-Sys:RPL | 4:30 | Y . . . . . . | BDAPP
Command | PURGE_WSID |  |  |  |  | Purge Virtual WS ID QPAD* | 4:30 | Y Y Y Y Y . . | BD APP SUP
Command | RBA90501 |  |  |  |  | Transmission Log Delete | 4:30 | Y . . . . . . | ALERT
Command | RBA90601 |  |  |  |  | Message History Delete | 4:30 | Y . . . . . . | ALERT
Command | RBC000WP |  |  |  |  | Robot Console Hist Purge | 4:30 | . . . . . Y .
Command | INVBAX_API | HOLD |  | EVERY |  | H*API Call to upd invbax | 0:00 | Y Y Y Y Y Y Y
Command | F_BUSPLN |  |  |  |  | Business Plan Data Feed | 5:00 | . . . Y . . . | BD-APPS
Command | GM_WK_RPT |  |  |  |  | Auto GM Weekly Report-Mon | 5:00 | Y . . . . . . | BDAPPLN
Command | NONSALE_UP |  |  |  |  | Update the Status of | 5:00 | Y Y Y Y Y Y Y | BUSDEP
Command | PERFNAVIFS | HOLD |  |  |  | IFS Size Collection | 5:00 | . . . . . . Y | TECSUPPORT
Command | PERFNAVIFS | HOLD |  |  |  | Perf Nav IFS size coll | 5:00 | . . . . . . Y | MPG
Command | PLNMST | HOLD |  |  |  | H*FTP Pln Master Tables | 5:00 | Y Y . Y Y . . | BDAPPS
Command | PLNMST_SLS | HOLD |  |  |  | H*FTP WKly Mstr/SLS to DB | 5:00 | . . Y . . . . | BDAPPS
Command | SAARMNT |  |  | DAYNO |  | Bank Reconciliation | 5:00 | 1 | BDA
Command | SABNKMNT |  |  | DAYNO |  | Bank Reconciliation | 5:00 | 1 | BDA
Command | SAI_INRT |  |  |  |  | Weekly RT Feed From Alpha | 5:00 | . . . . . Y . | BDAPPLICAT
Command | UPDVEND# |  |  |  |  | Refresh Vendr-UPC/BCD/RTN | 5:00 | Y Y Y Y Y . . | BDAPP
Command | ZAACL28NA |  |  |  |  | Chgs To Net Attributes | 5:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL28SE |  |  |  |  | Subsystem Routing Changes | 5:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL28ST |  |  |  |  | Use of Service Tools | 5:00 | Y Y Y Y Y Y . | PSAUDIT
Command | CATMANGETF |  |  |  |  | Fri-Get CATMAN Files | 5:05 | . . . . Y . .
Command | CATMANLSTF |  |  |  |  | Fri-Get CATMAN File LST | 5:05 | . . . . Y . .
Command | E3TWAIT |  |  |  |  | *E3 DAY-END PROCESS | 5:15 | Y Y Y Y Y Y Y | LEARN
Command | EVER_SKUFL |  |  |  |  | Set Ever Sku Flag | 5:20 | Y Y Y Y Y Y . | BDAPPS
Command | AGILENCEDP |  |  |  |  | Send Agilence LP File DLY | 5:30 | Y Y Y Y Y . . | BUSDEP
Command | CPS_DAILY |  |  |  |  | Extract Sales for C&P SO | 5:30 | Y Y Y Y Y Y Y | BD APPLN
Command | DCA3_DAILY |  |  |  |  | *CA Morning Setup *Once | 5:30 | Y Y Y Y Y Y Y
Command | MOO_SUM | HOLD |  |  |  | H*Build MOOSE Summary | 5:30 | Y . . . . . . | BDAPPS
Command | PLNVMST_UP |  |  |  |  | FTP Get POG/Sku,Str,Desc | 5:30 | . . . . Y . . | BDAPPS
Command | SUNIRF_DP |  |  |  |  | SUNRISE Inv Fresh Mon-Fri | 5:30 | Y Y Y Y Y . . | BDAPPLN
Command | SYSGENRBT | HOLD |  |  |  | re-gen robot message file | 5:30 | . . Y . . . Y
Command | SYSTELSSL | HOLD |  |  |  | Create DTAAREA for TELSSL | 5:30 | . . . Y . . .
Command | EM_PRC2OD | HOLD |  |  |  | H*Eml Prc Chg-FU-On Deman | 5:35 | . . . . . Y . | BUSDEP APP
Command | MPOS_330DP | HOLD |  |  |  | H*Send Full PLU-MPOS-330 | 5:40 | Y Y Y Y Y . . | BDAPPLN
Command | BPS_INVENT |  |  |  |  | Eml BPS Ord Activity Rpt | 5:45 | Y Y Y Y Y Y Y | BUSDEP
Command | CLR_IFSDP |  |  |  |  | Clear IFS tmp folder-DLY | 5:45 | Y Y Y Y Y . . | BD-APPLICA
Command | F_PDBRCLDP |  |  |  |  | *FTP RCL Fee-> Google WD | 5:45 | Y Y Y Y Y . . | BD_APP
Command | F_PDBVNDDP |  |  |  |  | *FTP Vend Master-> PDB WD | 5:45 | Y Y Y Y Y . . | BD_APP
Command | PCA_PURAS4 |  |  |  |  | *Clear AS400 Count Files | 5:45 | . . . Y . . . | BD-APPS
Command | POSLOG |  |  |  |  | Monitoring POS Polling | 5:45 | Y Y Y Y Y Y Y | POS
Command | PPR_OH_DP |  |  |  |  | PPR On Hand - rolling | 5:45 | Y Y Y Y Y Y . | BD-APP
Command | RLS_RVFAX |  |  |  |  | Release RVFax JOB Queue | 5:45 | . . . . . Y . | BDAPPLN
Command | SYSCHKSUN | HOLD |  |  |  | check sunrise | 5:45 | . . . . . . Y
Command | F_GXDLY2TB |  |  |  |  | *FTP Google Master TBL#2 | 5:50 | Y Y Y Y Y Y Y | BD_APP
Command | BLD_PRXFDP |  |  |  |  | Bld Program Ref-Daily | 5:55 | Y Y Y Y Y . . | BD APPLN
Command | FCHN_SKUDP | HOLD |  |  |  | H*CHN Sku Lst-Fil Rpt-Dly | 5:55 | Y Y Y Y Y . . | BD APPLN
Command | F_GXDLY1TB |  |  |  |  | *FTP Google Master TBL#1 | 5:58 | Y Y Y Y Y Y Y | BD_APP
Command | EMPMSTDP |  |  |  |  | Upl Empl Mstr SLSEMPWK-DP | 5:59 | Y Y Y Y Y . . | BD APPLN
Command | ADDINVRTN |  |  |  |  | Add Missing INVTRN Record | 6:00 | Y Y Y Y Y Y . | BDAPPLN
Command | BDDLOC_CPY |  |  |  |  | Backup BDDLOC => BDDLOCBK | 6:00 | Y Y Y Y Y Y . | BD_APPLN
Command | CBT_DAILY |  |  |  |  | *File feed transmission | 6:00 | Y Y Y Y Y Y Y | BD APPLN
Command | CLR_E3PROD |  |  |  |  | Clear E3PROD Outq | 6:00 | . Y . . . . . | LEARN
Command | CLR_IFSALL |  |  |  |  | O*Clear IFS see IFSLIST | 6:00 | Y Y Y Y Y Y Y | BDAPP
Command | DST_DAILY |  |  |  |  | DAILY DISTRICT STORE RES | 6:00 | Y Y Y Y Y . . | LEARN
Command | ETS_DAILY |  |  |  |  | ETS-WebErr & ESPtablesFTP | 6:00 | Y Y Y Y Y Y Y | BDAPPS
Command | F_SUPORD |  |  |  |  | FTP Supply Order->Ruscom | 6:00 | Y Y Y Y Y Y . | BDAPPS
Command | KRONOSDP |  |  |  |  | DYLY:Store Data->Kronos | 6:00 | Y Y Y Y Y . . | BDAPPLN
Command | MKB_REPORT | HOLD |  |  |  | H*Market Basket Report | 6:00 | Y Y Y Y Y Y Y | BUSDEP
Command | MONINVBL2A | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 6:00 | Y . . . . . . | BD APPLN
Command | MPOS_330WP | HOLD |  |  |  | H*Send Full PLU-MPOS-330 | 6:00 | . . . . . Y Y | BDAPPLN
Command | PLNPOS |  |  |  |  | Upload Sign Type/# Copies | 6:00 | . . . . Y . . | BD APP
Command | SAI_MAC |  |  |  |  | *SA Daily MAC Interface | 6:00 | Y Y Y Y Y Y Y | BD APP
Command | SE_DAILY |  |  |  |  | *Send Daily Feeds for SE | 6:00 | Y Y Y Y Y . Y | BUSDEP
Command | SE_WEEK |  |  |  |  | Send Weekly Feeds for SE | 6:00 | . . . . . Y . | BUSDEP
Command | SKUEXT2 |  |  |  |  | *Sku Master ext part 2 | 6:00 | Y Y Y Y Y Y Y | BD APPLN
Command | SOSIFSCLR | HOLD |  |  |  | H*Spec Order Payment Conf | 6:00 | Y Y Y Y Y . . | BUSDEP
Command | SYSAUDROBL |  |  | DAYNO |  | Robot Audit Reports | 6:00 | 1
Command | SYSBRMSLOG |  |  | DAYNO |  | Monthly Audit BRMS Log | 6:00 | 1
Command | SYSLOGFTP | HOLD |  |  |  | FTP Network Transactions | 6:00 | Y Y Y Y Y Y Y
Command | SYSRRMTRAN | HOLD |  |  |  | Capture all Network Trans | 6:00 | Y Y Y Y Y Y Y
Command | SYSSTORAUD | HOLD |  |  |  | Audit store 3 & 256 | 6:00 | . Y Y Y Y Y .
Command | UP_GCCOM |  |  |  |  | Refresh Gift Card Com% | 6:00 | Y Y Y Y Y Y Y | BDAPP
Command | CKCLEAR |  |  |  |  | Check Resource RBCLEAR_IF | 6:01 | Y Y Y Y Y . . | RBC
Command | CATMANGETS |  |  |  |  | Sat-Get CATMAN Files | 6:05 | . . . . . Y .
Command | CATMANLSTS |  |  |  |  | Sat-Get CATMAN File LST | 6:05 | . . . . . Y .
Command | AGILENCEWP |  |  |  |  | *Send Agilence LP File WN | 6:15 | . . . . . Y Y | BUSDEP
Command | AUTO_FTP |  |  |  |  | *Resend Missed POS Price | 6:25 | Y Y Y Y Y Y Y | SDI
Command | ECP1_DAILY | HOLD |  |  |  | H*Easy Care Plan Create | 6:25 | Y Y Y Y Y Y .
Command | EM_PRC1OD | HOLD |  |  |  | H*Eml Prc Chg-IR-On Demnd | 6:25 | . . . . . Y . | BUSDEP APP
Command | CLD_TXNPCK | HOLD |  |  |  | H*StoragePipe Ord Trigger | 6:30 | Y Y Y Y Y Y Y | BDAPPLN
Command | CLR_IFSWP |  |  |  |  | O*Clear IFS TMP Fldr-WN | 6:30 | . . . . . Y Y | BD-APPLICA
Command | CXDAILY |  |  |  |  | Daily SLS CMIS-Weekday | 6:30 | Y Y Y Y Y . . | CMIS
Command | CXTBLBDG |  |  |  |  | *Giftcard Reversal TBLMDG | 6:30 | Y Y Y Y Y Y Y | CMIS
Command | ECP_WEEKLY | HOLD |  |  |  | H*ESP Mnth Cont-Hld/Activ | 6:30 | Y . . . . . .
Command | EM_DSAD1 |  |  |  |  | *EMail Daily SLS All Str | 6:30 | Y Y Y Y Y . . | BD_APP
Command | ESPCLOSEWP | HOLD |  |  |  | Not Used-Force closed ESP | 6:30 | . Y . . . . . | BD-APPS
Command | F_DLYSLS |  |  |  |  | FTP Delivery Sls Summary | 6:30 | . Y . . . . . | BDAPPS
Command | INV824JQ |  |  |  |  | Shrink File Update | 6:30 | Y . . . . . . | INV
Command | MOOSE3_DP |  |  |  |  | Rebuild MOOSE3-Weekdays | 6:30 | Y Y Y Y Y . . | BD_APP
Command | PLNFACEX | HOLD |  |  |  | H*Pln Facing Exception | 6:30 | Y . . . . . . | BD-APPS
Command | PPA_DATE |  |  |  |  | Roll Prepaid Activation D | 6:30 | Y Y Y Y Y Y Y | SORDER
Command | PURG_DBFA | HOLD |  |  |  | H*Purge Data Base File | 6:30 | . L . . . . .
Command | QA_REFRESH |  |  |  |  | QA Lab Daily PLU Updates | 6:30 | Y Y Y Y Y Y Y | SDI899CL
Command | RBT650001 |  |  |  |  | Completion Message Listin | 6:30 | Y Y Y Y Y Y Y | ROBOT
Command | RBT651DP |  |  |  |  | Good Morning Report | 6:30 | Y Y Y Y Y Y Y | PROD. DEL.
Command | RBT651WP |  |  |  |  | Good Morning Report | 6:30 | Y . . . . . . | PROD. DEL.
Command | SACFSDLY |  |  |  |  | CFS Parsing | 6:30 | . Y Y Y Y Y . | BDA
Command | SKUCHKD |  |  |  |  | Recalculate Sku Check Dig | 6:30 | Y Y Y Y Y . . | BUSDEP
Command | SPI_WKLY | HOLD |  |  |  | H*SPI Weekly Update | 6:30 | Y . . . . . . | SPI
Command | SYSEXPPRF |  |  |  |  | Check for expired 365 prf | 6:30 | Y . . . . . .
Command | SYSJRNACT | HOLD |  |  |  | Log Journal Rcvr Activity | 6:30 | Y Y Y Y Y Y Y
Command | SYSODBCPRT |  |  |  |  | Monthly ODBC Access Repor | 6:30 | 1 . . . . . .
Command | SYSSSHCHK |  |  |  |  | AML SSH Config Check | 6:30 | Y Y Y Y Y Y Y
Command | TDSFEE | HOLD |  |  |  | H*TDS FEE Email Report | 6:30 | Y . . . . . . | BD APP SUP
Command | SSWINBND2 |  |  |  |  | *FTP/In Str Signage WHSE | 6:35 | Y Y Y Y Y Y . | BDAPPLN
Command | PURG_E3RPT |  |  |  |  | Purge E3 Report in IFS | 6:40 | . Y . . . . . | BD APP SUP
Command | PURGE_CD |  |  |  |  | Purge E3 Cross Dock Order | 6:40 | . Y . . . . . | BD APP SUP
Command | CKMONSWA |  |  |  |  | Check MONSWABRM for SLA | 6:45 | Y Y Y Y Y Y .
Command | EM_UIDCHDP |  |  |  |  | Eml User ID Chg Err -DLY | 6:45 | Y Y Y Y Y . . | BDAPPS
Command | F_PDBRCLWP |  |  |  |  | *FTP RCL Fee-> Google WN | 6:45 | . . . . . Y Y | BD_APP
Command | F_PDBVNDWP |  |  |  |  | *FTP Vend Master-> PDB WN | 6:45 | . . . . . Y Y | BD_APP
Command | MONINVBL3B | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 6:45 | . Y Y Y Y . . | BD APPLN
Command | PLNSLS_OLD | HOLD |  |  |  | H*Wkly/Mnthly Sls-OLD | 6:45 | . Y . . . . . | BDAPPS
Command | SSWOUTBND |  |  |  |  | FTP/Out Str Signage WHSE | 6:45 | Y Y Y Y Y Y . | BDAPPLN
Command | AS2RESETDP |  |  |  |  | *Reset AS2 Comm. Line | 6:55 | Y Y Y Y Y Y Y | 400 ANLYST
Command | CVM_CSAT | HOLD |  |  |  | H*Send/Receive CVM Data | 6:55 | Y Y Y Y Y Y Y | BD-APP
Command | ESPCUA | HOLD |  |  |  | H*Upld AS400 WebESP Cust | 6:55 | Y Y Y Y Y Y Y | BD APPS
Command | AIRM_DAILY | HOLD |  |  |  | H*Send Daily Feed AIRMILE | 7:00 | Y Y Y Y Y Y Y
Command | CHKBAL_BLD |  |  |  |  | CHECK INVBAL REBUILD | 7:00 | . . . . . . Y
Command | CXSALES |  |  |  |  | Wkly SLS Totals to CMIS | 7:00 | Y . . . . . .
Command | DRPSHPVNDP | HOLD |  |  |  | H*Vendor File | 7:00 | Y Y Y Y Y . . | BD-APPS
Command | EBY_TRF_DP |  |  |  |  | Sends daily eBay transfer | 7:00 | Y Y Y Y Y . . | BD APP
Command | EM_DSTD1 |  |  |  |  | *EMail Daily SLS Transfrm | 7:00 | Y Y Y Y Y . . | BD_APP
Command | EMPMSTWP |  |  |  |  | *Upl Empl Mst SLSEMPWK-WP | 7:00 | . . . . . Y Y | BD APPLN
Command | F_XEROXDP |  |  |  |  | Send PO Rec RTV Info XRX | 7:00 | Y Y Y Y Y Y . | BDAPPS
Command | FCHN_SKUWP | HOLD |  |  |  | H*CHN Sku Lst-Fill Rpt-WN | 7:00 | . . . . . Y Y | BD APPLN
Command | PPR_OH_WP |  |  |  |  | PPR On Hand - rolling-SUN | 7:00 | . . . . . . Y | BD-APP
Command | SPIDRIVE | HOLD |  |  |  | H*SPI Prod Collection | 7:00 | . Y Y Y Y . . | SPI
Command | TSS_ORDPOP |  |  |  |  | Zuora Order Number Popula | 7:00 | Y Y Y Y Y Y Y
Command | UP_MEMCONT |  |  |  |  | *Upd Sku Memory Content | 7:00 | Y Y Y Y Y Y Y | BD_APP
Command | HAMILTON |  |  |  |  | *CREATE CITICORP FILES | 7:15 | Y Y Y Y Y Y Y | LEARN
Command | PRTLABELOD | HOLD |  |  |  | H*Print Labels-On Demand | 7:25 | . . . . . Y . | SDI
Command | BLDINVTR |  |  |  |  | Build Inventory Turn file | 7:30 | . . . . . . .
Command | DESJARDINS |  |  |  |  | *Outbound Line Item Dtl | 7:30 | Y Y Y Y Y Y Y | BD APP
Command | DLYQWKN3AM | HOLD |  |  |  | H*Block 15 QWKNBCH3 Jobs | 7:30 | Y Y Y Y Y . . | BD_APP
Command | EM_PDNVFO |  |  |  |  | Eml Pending Sell Thr Rpt | 7:30 | Y Y Y Y Y Y Y | BD_APP
Command | EM_UIDCHWP |  |  |  |  | Eml User ID Chg Err -WKN | 7:30 | . . . . . Y Y | BDAPPS
Command | E3FCTVAR |  |  |  |  | E3 variance reports | 7:30 | Y . . . . . . | BD-APPS
Command | F_ORDSTSYD |  |  |  |  | Copy FC Order Sts Journal | 7:30 | Y Y Y Y Y Y Y | BD APPLN
Command | F_OS_POTRD |  |  |  |  | FTP Unrec PO Trf-BTS Wk D | 7:30 | Y Y Y Y Y . . | BDAPPS
Command | PURG_DBF |  |  |  |  | Purge Data Base File | 7:30 | . Y . . . . .
Command | REV_SKU |  |  |  |  | Flag Reversal Sku-INVSKU | 7:30 | Y Y Y Y Y . . | BDAPPS
Command | SAALPDLY |  |  |  |  | Alpha Parsing | 7:30 | . Y Y Y Y Y . | BDA
Command | SBMZAPJOBS |  |  |  |  | Submit purge jobs | 7:30 | . . Y . . . . | SYS
Command | SOINGRAM |  |  |  |  | Ingram Special Orders | 7:30 | Y Y Y Y Y . . | SORDER
Command | SYM_SLS |  |  |  |  | symantec sales file | 7:30 | . Y . . . . . | BD APPS
Command | SYSPSJRN |  |  | INDAY |  | Delete PSJRN Receivers | 7:30 | . . . . . . .
Command | VRM_INVOIC |  |  |  |  | VRM Inv DO NOT take DO | 7:30 | Y . . . . . .
Command | CK_E3EOD2A |  |  |  |  | Check E3 EOD (M-F) ASR | 7:40 | Y Y Y Y Y . . | BDAPPLN
Command | EBY_SLPOST |  |  |  |  | eBay Sales Posting | 7:40 | Y Y Y Y Y . . | BDAPPS
Command | MONINVBL2B | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 7:45 | Y . . . . . . | BD APPLN
Command | VRM_28RPTD |  |  |  |  | VRM C28 Report for Distr. | 7:45 | Y . . . . . .
Command | CK_E3EOD2W |  |  |  |  | Check E3 EOD (M-F) AWR | 7:55 | Y Y Y Y Y . . | BDAPPLN
Command | EDI_DAILY |  |  |  |  | EMAIL TO MERCH FOR PO'S | 7:55 | . Y . . Y . . | LEARN
Command | AOOS_WKLY |  |  |  |  | Weekly AOOS Email Reports | 8:00 | Y . . . . . . | IS4TC
Command | BPS_LABOUR |  |  |  |  | BOPIS CA Orders Report | 8:00 | Y . . . . . . | BUSDEP
Command | CRT_R40CTL | HOLD |  |  |  | H*Not Use-Run in CPCDaily | 8:00 | Y Y Y Y Y Y Y | BDAPPLN
Command | CSG_CHDTWP |  |  |  |  | Consignment Check Detail | 8:00 | . . . . . Y . | B DEPOT
Command | CVM_MNTHLY |  |  | DAYNO |  | Monthly CVM Interface | 8:00 | 1 | CVM
Command | CXDLYSAT |  |  |  |  | Daily SLS CMIS-Satuday | 8:00 | . . . . . Y . | CMIS
Command | CXDLYSUN |  |  |  |  | Daily SLS CMIS-Sunday | 8:00 | . . . . . . Y | CMIS
Command | DST_SAT |  |  |  |  | SAT DISTRICT STORE RES | 8:00 | . . . . . Y . | LEARN
Command | EM_PMDAY | HOLD |  |  |  | H*P&M Flash Sales-CPC Eml | 8:00 | Y Y Y Y Y . . | BD_APP
Command | EM_PRC2DP |  |  |  |  | *Email Price Chg-Follw Up | 8:00 | Y Y Y Y Y Y Y | BUSDEP APP
Command | E3_RPLEN |  |  |  |  | *E3 Repln*Before E3_Frz | 8:00 | Y Y Y Y Y Y Y | APPLN
Command | F_ESPTBL | HOLD |  |  |  | H*FTP ESP TABLE TO ETS | 8:00 | Y Y Y Y Y Y Y | BDAPPS
Command | KRONOSWP |  |  |  |  | *WKLY:Store Data->Kronos | 8:00 | . . . . . Y Y | BDAPPLN
Command | OS_BATCH |  |  |  |  | OUT OF STOCK SUMMARY RPT | 8:00 | . . . Y . . . | LEARN
Command | PCA_STRCNT |  |  |  |  | Thur->Sun Inventory Count | 8:00 | . . . Y Y Y Y | BP-APPS
Command | PLNCHGFIL |  |  |  |  | Get PLNCHGFIL->PLNCHG Fil | 8:00 | Y . . . . . . | BD APPLIC
Command | PRGE_PRCZN |  |  |  |  | Purge Expired PRCZNO rcds | 8:00 | Y Y Y Y Y Y Y | ZONE PRICE
Command | SKC_UPDPRC |  |  |  |  | SKU CENTRAL GALAXY UPDATE | 8:00 | Y Y Y Y Y Y . | LEARN
Command | SYSPRFDSP |  |  |  |  | DSPUSRPRF to BUSDEPUSRS | 8:00 | Y Y Y Y Y Y Y
Command | SYSSSLCHK |  |  |  |  | Check for SSL v2 | 8:00 | Y Y Y Y Y Y Y
Command | SYSUSRPRF | HOLD |  |  |  | DSPUSRPRF to ITTOOLS | 8:00 | Y Y Y Y Y Y Y
Command | TRF_AUTRCV |  |  |  |  | Auto Rec. Old Trfs | 8:00 | Y Y Y Y Y Y Y | BUSDEP
Command | AS2_CHKCOM | HOLD |  |  |  | H*Check AS2 Comm. Line | 8:15 | Y Y Y Y Y Y Y | BD_APPLN
Command | CKMONSWAW |  |  |  |  | Check MONSWABRM for SLA | 8:15 | . . . . . . Y
Command | CPYAHS_P |  |  |  |  | *Upload Auto Hub&Spk Data | 8:15 | Y Y Y Y Y Y Y | BDAPPS
Command | CSH900 |  |  |  |  | PRICE OVERRIDE REPORT | 8:15 | Y Y Y Y Y Y Y | LEARN
Command | EMSLSVARDP |  |  |  |  | Email Sales Var Sum-DP | 8:15 | Y Y Y Y Y . . | BD-APPLICA
Command | EMSLSVARWP |  |  |  |  | Email Sales Var Sum-WP | 8:15 | . . . . . Y Y | BD-APPLICA
Command | PLNE3MINQT |  |  |  |  | Update E3 Min Pres Qty | 8:15 | Y . . . . . . | BD-APPS
Command | CH_E3POCDP |  |  |  |  | Check New E3 PO Count | 8:30 | Y Y Y Y Y . . | BDAPPLN
Command | EM_HUGEQTY |  |  |  |  | Email Huge Inv Adj Qty | 8:30 | Y Y Y Y Y Y Y | BDAPPLN
Command | FD15YSLSDP | HOLD |  |  |  | H*D15 YDay SL-Fill Rpt-DL | 8:30 | Y Y Y Y Y . . | BD APPLN
Command | FD20_SLSDP | HOLD |  |  |  | H*D20 YDay SL-Fill Rpt-DL | 8:30 | Y Y Y Y Y . . | BD APPLN
Command | HEAD_COUNT | HOLD |  |  |  | H*Head Count Sales file | 8:30 | Y Y Y Y Y Y Y | BD APPLN
Command | MANL120C | HOLD |  |  |  | H*MAWM ShipConf/No OB-Sls | 8:30 | Y Y Y Y Y . . | BD
Command | MOOSE3_WP |  |  |  |  | Rebuild MOOSE3-Weekend | 8:30 | . . . . . Y Y | BD_APP
Command | OF_IN_GR |  |  |  |  | Oracle Exch Rates to JDA | 8:30 | Y Y Y Y Y Y Y | BUSDEP
Command | OF_IN_GT |  |  |  |  | Oracle GL TransactionsJDA | 8:30 | Y Y Y Y Y Y Y | BUSDEP
Command | CSH_XTN_WK |  |  |  |  | Cash Bolt-on file-WKN | 8:45 | . . . . . Y Y | BD APPLN
Command | EM_EP_USE |  |  |  |  | Email Wkly Emg Prf Usage | 8:50 | Y . . . . . . | BDAPPS
Command | ALG_BAL_WP |  |  |  |  | *DailyAlgolia Invbal File | 9:00 | . . . . . Y Y | CMIS
Command | APLCARE |  |  |  |  | AppleCare Payment | 9:00 | . . . . . Y .
Command | CSG_3PL |  |  |  |  | 3PL Consignment | 9:00 | . . . Y . . . | BD-APPLICA
Command | CX_MST_WP |  |  |  |  | *Daily CMIS Master Files | 9:00 | . . . . . Y Y | CMIS
Command | DST_SUN |  |  |  |  | SUNDAY DISTRICT STORE RES | 9:00 | . . . . . . Y | LEARN
Command | ECP2_DAILY | HOLD |  |  |  | H*Easy Care Plan Send | 9:00 | Y Y Y Y Y Y .
Command | EM_SAPOREC |  |  |  |  | Email SA PTD PO Rec Rpt | 9:00 | Y . . . . . . | BDAPPLN
Command | EM_SKUADCH |  |  |  |  | Email Sku Add/Change Data | 9:00 | Y Y Y Y Y Y Y | BDAPPLN
Command | EM_SLS_PCS | HOLD |  |  |  | H*Eml SLS Piece Count Rpt | 9:00 | Y Y Y Y Y Y Y | BDAPPLN
Command | EML_CHKCCC | HOLD |  |  |  | H*Check Clr CR Card# Sls | 9:00 | Y Y Y Y Y . . | BDAPPLN
Command | EMMISSD1 |  |  |  |  | Email Missing Rtl Sales | 9:00 | Y Y Y Y Y . . | BDAPPS
Command | EMMISSW1 |  |  |  |  | Email Missing Rtl Sales | 9:00 | . . . . . Y Y | BDAPPS
Command | MANL100C | HOLD |  |  |  | H*MAWM Json Error Alert | 9:00 | Y Y Y Y Y . . | BD
Command | OOSLBD15 | HOLD |  |  |  | H*Prt Out of Stk Lbl D15 | 9:00 | Y Y Y Y Y Y Y | BDAPPLN
Command | PCU100MP | HOLD |  | DAYNO |  | Profile Cleanup Utility. | 9:00 | 1 | IT
Command | POSPRGCOAL |  |  |  |  | Purge Coalition POS Data | 9:00 | . . 2 . . . .
Command | SAI_INPI |  |  |  |  | SA Physical Inventory2010 | 9:00 | . . . . . Y . | INVENTORY
Command | SKU_TRNRPT |  |  |  |  | SKU Translation Report | 9:00 | Y Y Y Y Y . . | BD APP
Command | SUNIRF_WP |  |  |  |  | SUNRISE Inv Fresh Sat-Sun | 9:00 | . . . . . Y Y | BDAPPLN
Command | SYSEMGAUDR |  |  |  |  | Print Emg Prf Audit Rpt | 9:00 | Y . . . . . . | BDAPPS
Command | SYSPRFDLT |  |  | DAYNO |  | Profile Deletion Utility. | 9:00 | 1 | IT
Command | SYSPTFLOAD | HOLD |  |  |  | Load/Set to apply PTF | 9:00 | . . . Y . . . | PTF
Command | SYSSTPROLL | HOLD |  |  |  | Dasd plus Rolling Survey | 9:00 | . . . . . . Y
Command | WRC_INVOIC | HOLD |  |  |  | VRM Inv DO NOT take DO | 9:00 | Y . . . . . .
Command | EM_IPHONE | HOLD |  |  |  | H*Email iPhone Sales Rpt | 9:30 | . Y . . . . . | BDAPPLN
Command | EMSAPRTHUB | HOLD |  |  |  | H* Eml SA Prt Hub Wkly SL | 9:30 | Y . . . . . . | BD_APP
Command | ESPRNWLWP | HOLD |  |  |  | H*Generate list of cust | 9:30 | Y Y Y Y Y Y . | BD-APPS
Command | E3_PO_02 |  |  |  |  | ELECTRONIC PO TRANSFER | 9:30 | . . . . . Y . | LEARN
Command | OF_IN_RC |  |  |  |  | Orcl Reconcil Ttls JDA | 9:30 | Y Y Y Y Y Y Y | BUSDEP
Command | PCA_PURDMZ |  |  |  |  | Purge DMZ Phy Inv Files | 9:30 | . . Y . . . . | BD_APPS
Program | SVC026CL |  |  |  |  | D*Prt SVS Settlement Rpt | 9:30 | Y Y Y Y Y Y Y | SVC REPORT
Command | DPS_DLYSLS | HOLD |  | EVERY |  | H*PCI - OMS DPS Integratn | 0:00 | Y Y Y Y Y Y . | BD-APPLICA
Command | EM_NIPHONE | HOLD |  |  |  | H*Email NoniPhone Sls Rpt | 9:45 | . Y . . . . . | BDAPPLN
Command | MONINVBL1A | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 9:45 | . . . . . . Y | BD APPLN
Command | MONINVBL7A | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 9:45 | . . . . . Y . | BD APPLN
Command | BLD_PRXFWK |  |  |  |  | Bld Program Ref-Wkend | 10:00 | . . . . . Y Y | BD APPLN
Command | CK_E3EOD1A |  |  |  |  | O*Check E3 EOD(Sun)ASR | 10:00 | . . . . . . Y | BDAPPLN
Command | CXMBRRMV |  |  |  |  | Remove CMIS Feed Member | 10:00 | Y . . . . . .
Command | EM_EP_UNAP |  |  |  |  | Email Daily Emg Prf UnApr | 10:00 | Y Y Y Y Y Y Y | BDAPPS
Command | EM_PMWK | HOLD |  |  |  | H*P&M Flash Sales-CPC Eml | 10:00 | . . . . . Y Y | BD_APP
Command | EXTSLSB2WK |  |  |  |  | Build Ext. Sls-2 Week Ago | 10:00 | . . . . . Y . | BDAPPS
Command | F_OS_POTRW |  |  |  |  | FTP Unrec PO Trf-BTS Wk N | 10:00 | . . . . . Y Y | BDAPPS
Command | F_XEROXWP |  |  |  |  | *Send PO Rec RTV Info XRX | 10:00 | . . . . . . Y | BDAPPS
Command | MAPET |  |  |  |  | Marketing and Sales Event | 10:00 | Y . . . . . . | MAPET
Command | PCA940CL |  |  |  |  | Build Prices for Frz file | 10:00 | . . Y . . . . | BD_APPS
Command | PLNCHGOR | HOLD |  |  |  | H*Add/Del Original Report | 10:00 | Y . . . . . . | BD APPLIC
Command | POS_REJECT | HOLD |  |  |  | H*Eml Reject POS Trans Rp | 10:00 | Y Y Y Y Y Y Y | BD-APPS
Command | POSREFRESH |  |  |  |  | Refresh price @ store | 10:00 | Y Y Y Y Y . . | SDI
Command | PURG_TSGNS |  |  |  |  | Purge Temp SGN Suppress | 10:00 | . . . . Y . . | BD APP SUP
Command | RBT655 |  |  |  |  | Purge Robot History | 10:00 | . . . . Y . .
Command | S_SLS_EX |  |  |  |  | Staples Sales Extract | 10:00 | Y . . . . . . | STAPLES
Command | SYSBCKPRG |  |  |  |  | Purge backup audit log | 10:00 | Y Y Y Y Y Y Y
Command | SYSCHKCER1 |  |  |  |  | Check SSL Cert Expiry*SYS | 10:00 | Y . . . . . . | BD_APP
Command | SYSCHKLKEY |  |  |  |  | Check license keys expire | 10:00 | Y Y Y Y Y Y Y
Command | SYSSWPAUD |  |  |  |  | Audit swap profiles | 10:00 | Y Y Y Y Y Y Y
Command | SYSDDMAUDP |  |  |  |  | Add Users to IP DDM SV | 10:01 | Y Y Y Y Y Y Y | HD-AS400
Command | SYSRSFCHK | HOLD |  | EVERY |  | Check RSF communications | 0:00 | Y Y Y Y Y Y Y
Command | EM_PRC3DP |  |  |  |  | Email Price Chg.-Init run | 10:05 | . Y . . . Y Y | BUSDEP APP
Command | EXTSLSB1DW |  |  |  |  | Build Ext. Sls-1 Week Ago | 10:05 | . . . . . . Y | BDAPPS
Command | EXTSLSB2DW |  |  |  |  | Build Ext. Sls-2 Week Ago | 10:05 | . . . . . Y . | BDAPPS
Command | SYSCHKCER2 |  |  |  |  | Check SSL Cert Expiry | 10:05 | Y . . . . . . | BD_APP
Command | CK_E3EOD1W |  |  |  |  | O*Check E3 EOD(Sun)AWR | 10:30 | . . . . . . Y | BDAPPLN
Command | FD15YSLSWP | HOLD |  |  |  | H*D15 YDay SL-Fill Rpt-WN | 10:30 | . . . . . Y Y | BD APPLN
Command | FD20_SLSWP | HOLD |  |  |  | H*D20 YDay SL-Fill Rpt-WK | 10:30 | . . . . . Y Y | BD APPLN
Command | BPS_ALLOC | HOLD |  | EVERY |  | H*Bopis Allocation Bucket | 0:00 | Y Y Y Y Y Y Y | BUSDEP
Command | PRTLABELW |  |  |  |  | *Print Labels | 10:40 | . Y . . . Y Y | SDI
Command | SYSDCMJBSC |  |  |  |  | crt dcm jobscde files | 10:41 | Y Y Y Y Y Y Y
Command | BLUEYNDLCP |  |  |  |  | Blue Yonder LCP | 11:00 | Y Y Y Y Y Y . | BD
Command | CVM_CSAT1 | HOLD |  |  |  | H*Send/Receive CVM Data | 11:00 | Y Y Y Y Y Y Y | BD-APP
Command | D1SLSEML |  |  |  |  | EMail Dly Sls Decision1 | 11:00 | . . Y . . . . | BDAPPS
Command | EM_DSAW1 |  |  |  |  | *EMail Daily SLS All Str | 11:00 | . . . . . Y Y | BD_APP
Command | F_PRECIMA |  |  |  |  | *FTP Precima Prc Data | 11:00 | Y Y Y Y Y Y Y | BDAPPS
Command | MAWM_SYNCH |  |  |  |  | MAWM Inventory Synch ** | 11:00 | . . . . . . Y | BD
Command | MMEJOB | HOLD |  |  |  | H*Run Weekly MME Project | 11:00 | Y Y Y Y Y Y Y | MMEAPL
Command | PASS_CPY |  |  |  |  | *PASS Trans Dtl Feed | 11:00 | Y Y Y Y Y Y Y | BD APPS
Command | SYSCACHBAT |  |  |  |  | cache battery listing | 11:00 | . . Y . . . .
Command | EM_DSTW1 |  |  |  |  | *EMail Daily SLS Transfrm | 11:30 | . . . . . Y Y | BD_APP
Command | EMLCHBER#1 | HOLD |  |  |  | H*Alert-CHub SLS Post ER | 11:30 | Y Y Y Y Y Y Y | BDAPPLN
Command | EMLCHBER#2 |  |  |  |  | EMail CHub Error Report | 11:30 | Y Y Y Y Y Y Y | BD_APPLN
Command | F_ETS_ORD |  |  | EVERY |  | Send Tec Ord to ETS Servr | 11:32 | Y Y Y Y Y Y Y | BDSYSPRF
Command | OVR_PRINTQ |  |  | EVERY |  | Override Store Printq | 11:32 | Y Y Y Y Y Y Y | BDSYSPRF
Command | SAI_DAILY |  |  | EVERY |  | SA Dly/SP E3@10pm Mon-Fri | 11:33 | Y Y Y Y Y Y . | BD APP
Command | BPS_OK_NO2 |  |  | EVERY |  | OTH-Refresh BPS Alloc Qty | 11:35 | . Y Y Y Y . .
Command | BPS_PCKEML |  |  | EVERY |  | Prt/Eml BOPIS Ord Pick Up | 11:35 | Y Y Y Y Y Y Y | BUSDEP
Command | CH_MSGT2F2 |  |  | EVERY |  | Check Job has MSGW-T2F-#2 | 11:35 | . Y Y Y Y . . | BD_APP
Command | CPP_KIOSK |  |  | EVERY |  | ***Copy & Print Kiosk Ord | 11:35 | Y Y Y Y Y Y Y | BDSYSPRF
Command | CPS_ORDRTV |  |  | EVERY |  | Extract C&P Orders for PR | 11:35 | Y Y Y Y Y Y Y | BD APPLN
Command | CXINVAUD |  |  | EVERY |  | Web Service Inventory UPD | 11:35 | Y Y Y Y Y Y Y | BD APPLN
Command | SBL_ORDER |  |  | EVERY |  | SBL Orders Generation | 11:35 | Y Y Y Y Y Y Y | BD APPLN
Command | SOSCFM |  |  | EVERY |  | *Spec Order Payment Confr | 11:35 | Y Y Y Y Y Y Y | BUSDEP
Command | SYSCFSGET |  |  | EVERY |  | Trigger CFS get | 11:35 | Y Y Y Y Y Y Y
Command | SYSSAGET |  |  | EVERY |  | Trigger SAGET | 11:35 | Y Y Y Y Y Y Y
Command | SYSDLTSPLF |  |  | EVERY |  | delete spool files | 11:36 | Y Y Y Y Y Y Y
Command | @XMLSLS |  |  | EVERY |  | XML POS Process XPS=>USI* | 11:40 | Y Y Y Y Y Y Y | BD-APPLICA
Command | CPC_TXNPCK |  |  | EVERY |  | CPC Txn pickup Trigger PT | 11:40 | Y Y Y Y Y Y Y | BD
Command | DCA1_SLSD1 |  |  | EVERY |  | CA Sales Mon-Thur*10 min | 11:40 | Y Y Y Y . . .
Command | STRPRT |  |  | EVERY |  | Start all printers | 11:40 | Y Y Y Y Y Y Y | OPS
Command | AR_UPDATE |  |  |  |  | Update A/R Sub-ledger | 11:45 | Y Y Y Y Y Y Y | AR
Command | CPCDAILY |  |  | EVERY |  | CPC Txn & Tender process | 11:45 | Y Y Y Y Y Y Y | BD
Command | CPP_PO |  |  | EVERY |  | CPC PO creation #1 | 11:45 | Y Y Y Y Y Y Y | BDSYSPRF
Command | CPP_SHIP |  |  | EVERY |  | CPC Ship Ack & Recv #2 | 11:45 | Y Y Y Y Y Y Y | BDSYSPRF
Command | MAWM_OUT |  |  | EVERY |  | MAWM Outbound Feeds | 11:45 | Y Y Y Y Y Y . | BD
Command | OF_IN_CNF |  |  | EVERY |  | Confirmation File Retrvl | 11:45 | Y Y Y Y Y Y Y | BUSDEP
Group | SYSCHKSYS |  |  | EVERY |  | System Resource Checks | 11:45 | Y Y Y Y Y Y Y |  | SYSCHKSYS
Command | SYSCHK992 |  |  | EVERY |  | Check port 992 Close Wait | 11:46 | Y Y Y Y Y Y Y
Command | EM_DSAD2 |  |  |  |  | *EMail Daily SLS All Str | 11:59 | Y Y Y Y Y . . | BD_APP
Command | AV_HOURLY |  |  | EVERY |  | Outbound Hourly Feed to A | 12:00 | Y Y Y Y Y . . | BDAPPLICAT
Command | CH_FC_DATE |  |  |  |  | Check FC Cur Billing Date | 12:00 | Y Y Y Y Y . . | BD_APP
Command | CH_SSH |  |  | EVERY |  | Check SSH Connection | 12:00 | Y Y Y Y Y Y Y | BD_APP
Command | CK_E3EOD3A |  |  |  |  | Check E3 EOD (Sat) ASR | 12:00 | . . . . . Y . | BDAPPLN
Command | CPCWEBTST | HOLD |  |  |  | H*CPC WEBSERVICE RACHAEL* | 12:00 | Y . . . . . . | BD
Command | DLTTRNLOG |  |  |  |  | Transmission Log Delete | 12:00 | . . . . L . . | ALERT
Command | E3_DUP_PO |  |  | EVERY |  | Eml Dup E3 Rls Ord-DLY | 12:00 | Y Y Y Y Y . .
Command | F_ESPOCS | HOLD |  |  |  | H*FTP Open ESP Case->ECP | 12:00 | Y Y Y Y Y Y Y | BDAPPS
Command | MANL115C | HOLD |  |  |  | H*MAWM PORcvd not Verify | 12:00 | Y Y Y Y Y . . | BD
Command | MANL117C | HOLD |  |  |  | H*MAWM PORcpt/Verfy Var | 12:00 | Y Y Y Y Y . . | BD
Command | MANL118C | HOLD |  |  |  | H*MAWM PORcpt/Cost Var | 12:00 | Y Y Y Y Y . . | BD
Command | MANL200C | HOLD |  |  |  | H*MAWM Inbound Json Er Rp | 12:00 | Y Y Y Y Y . . | BD
Command | MAWM_IN |  |  | EVERY |  | MAWM In bound Feeds | 12:00 | Y Y Y Y Y Y . | BD
Command | OF_OUT_AI |  |  | EVERY |  | *Invoice Interface Oracle | 12:00 | Y Y Y Y Y Y Y | BUSDEP
Command | PCA_CNTMST |  |  |  |  | FTP Count Fil,Eml->Inv/Mr | 12:00 | . . Y . . . . | BD_APPS
Command | RMA_RESP |  |  |  |  | RMA Response Monthly | 12:00 | . Y . . . . . | BD_APPLIC
Command | RMAFTP |  |  | EVERY |  | RTV Get Inbound Email ATT | 12:00 | Y Y Y Y Y Y Y | BD APP SUP
Command | SEND_EDI0 |  |  |  |  | EDI PO TRANSFERS | 12:00 | Y Y Y Y Y Y . | LEARN
Command | SYSJOBTBL |  |  |  |  | Check job table size | 12:00 | Y Y Y Y Y Y Y
Command | SYSPQMON |  |  | EVERY |  | fax queue monitor | 12:00 | Y Y Y Y Y Y Y
Command | VFOEMLWP | HOLD |  |  |  | H*Eml Sell Through Offer | 12:00 | . . . . . Y Y | BUSDEP APP
Command | EM_NOSGNWP |  |  |  |  | *Eml No Prc Chg Sign-WKN | 12:01 | . . . . . Y Y | APPLN
Command | SYSCHKCMT |  |  | EVERY |  | Check Open Commits | 12:01 | Y Y Y Y Y Y Y
Command | SYSDSTQCHK |  |  | EVERY |  | DSTQ monitor | 12:01 | Y Y Y Y Y Y Y
Command | DCA2_OTHER |  |  | EVERY |  | *CA DownStreamAps *60 min | 12:05 | Y Y Y Y Y Y Y
Command | EML_AS2ERR |  |  |  |  | Email/Text AS2 Err Rpt | 12:15 | Y Y Y Y Y . . | BDAPPS
Command | MONINVBL1B | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 12:15 | . . . . . . Y | BD APPLN
Command | SP_VND_MET |  |  |  |  | *SPartners Vendor Metric | 12:15 | . . . . . . Y
Command | EM_DSTD2 |  |  |  |  | *EMail Daily SLS Transfrm | 12:30 | Y Y Y Y Y . . | BD_APP
Command | E3_PO_00 |  |  |  |  | ELECTRONIC PO TRANSFER | 12:30 | Y Y Y Y Y . . | LEARN
Command | OF_IN_AT |  |  |  |  | Oracle Terms to JDA | 12:30 | Y Y Y Y Y . . | BUSDEP
Command | OF_IN_AV |  |  |  |  | Oracle Trade Vendors JDA | 12:30 | Y Y Y Y Y . . | BUSDEP
Command | OF_IN_GA |  |  |  |  | Oracle Chart Accts JDA | 12:30 | Y Y Y Y Y Y Y | BUSDEP
Command | OF_IN_GL |  |  |  |  | Oracle Locations to JDA | 12:30 | Y Y Y Y Y Y Y | BUSDEP
Command | OF_OUT_GI |  |  | EVERY |  | Journal Interface Oracle | 12:30 | Y Y Y Y Y Y Y | BUSDEP
Command | CH_CSHXTN |  |  |  |  | Chk Unprocess BOLT On Rec | 13:00 | Y Y Y Y Y Y Y | BD_APP
Command | CLICKSDP |  |  |  |  | *CLICKS TRACKING | 13:00 | Y Y Y Y Y Y Y | BUSDEP
Command | CRMIDLY |  |  |  |  | *Proc M/C Info from Comps | 13:00 | Y Y Y Y Y Y Y | BD APP
Command | CRT_R50CTL | HOLD |  |  |  | H*Not Use-Run in CPCDaily | 13:00 | Y Y Y Y Y Y Y | BDAPPLN
Command | DIVCLN |  |  |  |  | PURGE CANxxx DIVIDEND | 13:00 | . . . . . . Y | LEARN
Command | DRPSHPVNWP | HOLD |  |  |  | H*Vendor File | 13:00 | . . . . . Y Y | BD-APPS
Command | EM_NOSGNTU |  |  |  |  | *Eml No Prc Chg Sign-TUE | 13:00 | . Y . . . . . | APPLN
Command | E3EXCP_B |  |  |  |  | Exception Report BOW | 13:00 | Y . . . . . . | BD APP
Command | OF_EML_CNF |  |  |  |  | Email Outstndng Confirms | 13:00 | Y Y Y Y Y Y Y | BUSDEP
Command | RFRSH_CLN |  |  |  |  | SUNRISE WORKFILE CLEAN-UP | 13:00 | Y Y Y Y Y . . | LEARN
Command | SLS_DWNLOD |  |  |  |  | POPULATE SALES DWNLD FILE | 13:00 | . Y . . . . . | LEARN
Command | SYSCHKJQE3 |  |  | EVERY |  | Check E3 resource jobqs | 13:00 | Y Y Y Y Y Y Y | BUSDEP
Command | SSWINBND1 |  |  |  |  | FTP/In Store Signage WHSE | 13:10 | Y Y Y Y Y Y . | BDAPPLN
Command | CH_LBL_DE |  |  |  |  | Check O/S PRC CHG Signage | 13:30 | Y Y Y Y Y Y Y | BDAPPS
Command | CRMRDLY |  |  |  |  | Process last 2weeks data | 13:30 | Y Y Y Y Y Y Y | BD APP
Command | LWP_DAILY |  |  |  |  | *Lowest Price Daily | 13:30 | Y Y Y Y Y Y Y | BD_APP
Command | SYSSBMJOBT | HOLD |  |  |  | Submit test rmv | 13:35 | Y . . . . . .
Command | CH_E3POCWP |  |  |  |  | Check New E3 PO Count | 13:45 | . . . . . Y Y | BDAPPLN
Command | CK_E3EOD3W |  |  |  |  | Check E3 EOD (Sat) AWR | 13:45 | . . . . . Y . | BDAPPLN
Command | MONINVBL7B | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 13:45 | . . . . . Y . | BD APPLN
Command | ACNEILSENM |  |  |  |  | Snd Sls To AC Neilsen:Mon | 14:00 | Y . . . . . . | ACNEILSEN
Command | AIRM_RVRSE | HOLD |  |  |  | H*Air Mile Sales Reversal | 14:00 | Y Y Y Y Y Y Y
Command | ALG_BAL_DP |  |  |  |  | Daily Algolia Invbal File | 14:00 | Y Y Y Y Y . . | CMIS
Command | CLK_ERR |  |  |  |  | CLICKS ERROR REPORTS | 14:00 | . Y Y Y Y Y Y | BUSDEP
Command | CLK_MON |  |  |  |  | CLICKS REPORTS FROM RBO | 14:00 | Y . . . . . . | BUSDEP
Command | CLR_IFSRMA |  |  |  |  | Clear RMA Obj in IFS | 14:00 | . . . . . Y . | BD-APPLICA
Command | CLR_OUTQSW |  |  |  |  | Weekly Clear Out Queues | 14:00 | . . . . . . Y | LEARN
Command | CX_MST_DP |  |  |  |  | Daily CMIS Master Files | 14:00 | Y Y Y Y Y . . | CMIS
Command | EBY_TRF_WK |  |  |  |  | *Send eBay transfer Wkend | 14:00 | . . . . . Y Y | BD APP
Command | EMLNOSL1 | HOLD |  |  |  | H*Eml No SLS List Batch 1 | 14:00 | Y Y Y Y Y Y .
Command | EMLNOSL5 | HOLD |  |  |  | H*Eml No SLS List Batch 5 | 14:00 | Y Y Y Y Y Y .
Command | EMMISSD2 |  |  |  |  | Email Missing Rtl Sales | 14:00 | Y Y Y Y Y . . | BDAPPS
Command | PURGELBL |  |  |  |  | purge signage spool file | 14:00 | Y Y Y Y Y Y Y | BD APP
Command | SKU_TRNSLN |  |  |  |  | SKU French Translation | 14:00 | Y Y Y Y Y Y Y | BD_APPL
Command | SLS_GM_RPT |  |  |  |  | SALES GROSS MARGIN REPORT | 14:00 | . . . . . . Y | LEARN
Command | SYSBRMSMNT |  |  |  |  | Run BRMS Maintenance | 14:00 | Y Y Y Y Y Y Y | BRMS
Command | CRMXDLY |  |  |  |  | *Send m/c data to compass | 14:30 | Y Y Y Y Y Y Y | BD APPLICA
Command | EM_PRC1DP |  |  |  |  | Eml Prc Chg.-Init. Run | 14:30 | Y . Y Y Y . . | BUSDEP APP
Command | LBR_ERNMON | HOLD |  |  |  | H*Upload Store Spt Hr-Mon | 14:55 | Y . . . . . . | BD APPLN
Command | LBR_ERNTUE | HOLD |  |  |  | H*Upl Store Spent Hr-Tue | 14:55 | . Y . . . . . | BD APPLN
Command | CH_LBL_OD |  |  |  |  | Check O/S On Demand Signs | 15:00 | Y Y Y Y Y Y Y | BDAPPS
Command | CKQESLIN |  |  |  |  | Check Resource QESLINE | 15:00 | Y Y Y Y Y Y Y | SYSTEM
Command | CKQESPPL |  |  |  |  | Check Resource QESPPLIN | 15:00 | Y Y Y Y Y Y Y | SYSTEM
Command | EM_DSAW2 |  |  |  |  | *EMail Daily SLS All Str | 15:00 | . . . . . Y Y | BD_APP
Command | EMLNOSL2 | HOLD |  |  |  | H*Eml No SLS List Batch 2 | 15:00 | Y Y Y Y Y Y .
Command | MAWM_PURGE |  |  |  |  | MAWM file Purge | 15:00 | . . . . . . Y | BD
Command | RBCSTRTMON |  |  |  |  | Re-start RBCQSYSOPR | 15:00 | Y Y Y Y Y Y Y
Command | RBT34504 |  |  |  |  | ROBOT Schedule of Jobs to | 15:00 | Y Y Y Y Y Y Y | ROBOT
Command | SAI_DPRNT | HOLD |  |  |  | H* Dly SBA Digital Print | 15:00 | Y Y Y Y Y Y Y | BDAPPLICAT
Command | SKUMOO |  |  |  |  | SKUMOO Spread Sheet | 15:00 | Y . . . . . . | MER
Command | SYSBKUPRPT |  |  |  |  | MOVE BRMS BACKUP REPORTS | 15:00 | Y Y Y Y Y Y Y | BRMS
Command | BPS_AVLQTY | HOLD |  | EVERY |  | H*Refresh BOPIS Avail Qty | 0:00 | Y Y Y Y Y Y Y
Command | EM_DSTW2 |  |  |  |  | *EMail Daily SLS Transfrm | 15:30 | . . . . . Y Y | BD_APP
Command | E3_PO_01 |  |  |  |  | ELECTRONIC PO TRANSFER | 15:30 | Y Y Y Y Y . . | LEARN
Command | E3_PO_03 |  |  |  |  | *ELECTRONIC PO TRANSFER | 15:30 | . . . . . . Y | LEARN
Command | LCT_UPL2 |  |  |  |  | Upload Labor Cost Xfer | 15:30 | . Y . . . . . | BD APPLN
Command | PRTLABEL |  |  |  |  | *Print Signage Label | 15:30 | Y . Y Y Y . . | SDI
Command | CH_PRCCHGC |  |  |  |  | Alert Sku Price Change CT | 15:32 | Y Y Y Y Y Y Y | BD APPLN
Command | DLYQWKN3PM | HOLD |  |  |  | H*Block 15 QWKNBCH3 Jobs | 16:00 | Y Y Y Y Y . . | BD_APP
Command | EMLNOSL3 | HOLD |  |  |  | H*Eml No SLS List Batch 3 | 16:00 | Y Y Y Y Y Y .
Command | EMLNOSL6 |  |  |  |  | Email No SLS List Batch 5 | 16:00 | . . . . . . Y
Command | PCA_EMLLST |  |  |  |  | Email Wkly Str Inv Lst | 16:00 | . . Y . . . . | BDAPPLN
Command | PO_OD_RPT |  |  | INDAY |  | Overdue PO report | 16:00 | . . . . . . .
Command | RTVPENDING |  |  |  |  | Create RTV Pending record | 16:00 | . . . . . . Y | RTV
Command | SEND_EDI1 |  |  |  |  | EDI PO TRANSFERS | 16:00 | Y Y Y Y Y Y . | LEARN
Command | SPIINTUP | HOLD |  |  |  | H*SPI Prod Integration | 16:00 | . Y Y Y Y . . | SPI
Command | SPIPURGE | HOLD |  |  |  | H*Purge SPI Collection Dt | 16:00 | Y . . . . . . | BD APPS
Command | SYSCHKBCK |  |  |  |  | Check Backup Job Logs | 16:00 | Y Y Y Y Y Y Y
Command | POS_TENDER | HOLD |  | EVERY |  | H*Populate AN# to CSHTND | 0:00 | Y Y Y Y Y Y Y | BD-APPLICA
Command | VFOEMLDP |  |  |  |  | Email Sell Through Offer | 16:30 | Y Y Y Y Y . . | BUSDEP APP
Command | EM_NOSGNDP |  |  |  |  | *Eml No Prc Chg Sign-DLYP | 16:50 | Y . Y Y Y . . | APPLN
Command | AGEOUTQ | HOLD |  |  |  | H*Age Outq Qprint | 17:00 | Y Y Y Y Y . .
Command | BHN_DLYSTM |  |  |  |  | BHN statement posting | 17:00 | Y Y Y Y Y Y Y | BD-APPLICA
Command | CCF2SUNR |  |  |  |  | *Send Coupon to Sunrise | 17:00 | Y Y Y Y Y Y Y | CCF2SUNR
Command | EMLNOSL4 | HOLD |  |  |  | H*Eml No SLS List Batch 4 | 17:00 | Y Y Y Y Y Y .
Command | JRNRCVDLWP | HOLD |  |  |  | H*Delete Journal Receiver | 17:00 | Y . . . . . . | HD-AS400
Command | LVTINVOICE |  |  |  |  | Livingston Invoice | 17:00 | . . . . . Y .
Command | PERFNAVPM | HOLD |  |  |  | Monitor | 17:00 | Y Y Y Y Y Y Y | TECSUPPORT
Command | SEND_EDI2 |  |  |  |  | EDI PO TRANSFERS | 17:00 | Y Y Y Y Y . Y | LEARN
Command | SP_SALES |  |  |  |  | StaplesPartners Sales Hst | 17:00 | Y . . . . . .
Command | CLR_QEZJOB |  |  |  |  | Clear outq qezjoblog | 17:15 | . . . . Y . . | CLR_QEZJOB
Command | INVBAX_API | HOLD |  | EVERY |  | H*API INVBAX | 0:00 | Y Y Y Y Y Y Y
Command | DLTHSTLOG | HOLD |  |  |  | H*Delete History | 18:00 | Y Y Y Y Y Y Y
Command | EMLTRFVAR |  |  |  |  | Email Transfer Var Rpt | 18:00 | . . . . . . Y | BDAPPS
Command | JACKRTLRPT |  |  |  |  | *Print Retail Jackie Rpt | 18:00 | . . . . . . Y | BDAPPS
Command | LBR_PHYI |  |  |  |  | Labour Hours Phy Inv Flag | 18:00 | . . . . . Y . | LABOUR_HRS
Command | MICROSOFT |  |  |  |  | *EDI RUN FOR MICROSOFT | 18:00 | . . . . . . Y | LEARN
Command | NPD_SLS |  |  |  |  | Weekly Sales Summary | 18:00 | . . . . . . Y | BD APPS
Command | RBN35001 |  |  |  |  | Product Events Delete | 18:00 | . . . . Y . . | NETWORK
Command | RBN35002 |  |  |  |  | Packet History Delete | 18:00 | . . . . Y . . | NETWORK
Command | SEND_EDI3 |  |  |  |  | EDI PO TRANSFERS | 18:00 | Y Y Y Y Y . . | LEARN
Command | SYSJRNCHK | HOLD |  |  |  | Journal Monitor Program | 18:00 | Y Y Y Y Y Y Y
Command | SYSODBCPNT |  |  |  |  | Check for ODBC Exit Prog | 18:00 | Y Y Y Y Y Y Y
Command | SYSSAVARC |  |  |  |  | Archive check pts to hst | 18:00 | Y Y Y Y Y Y Y
Command | WHS_TRFR |  |  |  |  | DAILY TRFWKN FILE DATA | 18:00 | Y Y Y Y Y Y . | LEARN
Command | CHK_DUPPO |  |  |  |  | Check Duplicate PO/Sku | 18:30 | . . . . Y . . | BDAPPLN
Command | EMMISSW2 |  |  |  |  | Email Missing Rtl Sales | 18:30 | . . . . . Y Y | BDAPPS
Command | AR_MSTUPD |  |  |  |  | Vendor Ar update | 19:00 | Y Y Y Y Y . . | BD-APPS
Command | AUT_OOSOPN |  |  |  |  | Auto Scan Batch Open | 19:00 | Y Y Y Y Y Y Y
Command | EXTSLSB1WK |  |  |  |  | *BLD Ext. Sls-1 Week Ago | 19:00 | . . . . . . Y | BDAPPS
Command | IS4_AUTOPN | HOLD |  |  |  | H*Auto Scan Batch Open | 19:00 | Y Y Y Y Y Y Y
Command | SAE_POCNL |  |  |  |  | SA Daily PO Auto Cancel | 19:00 | Y Y Y Y Y . . | BD APP
Command | SKU_BPSFLG |  |  |  |  | SKU Bopisflag feed to PDB | 19:00 | Y Y Y Y Y Y Y | BUSDEP
Command | SPOOLS |  |  |  |  | Weekly Spool backup | 19:00 | . . . . . Y . | BRMS
Command | SYS_ORACLE |  |  |  |  | Clean up ORACLE Outq | 19:00 | . . . . . . Y
Command | SYSRSJOB1 | HOLD |  | DATE |  | Post Swap + 1 Day Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB2 | HOLD |  | DATE |  | Post Swap + 2 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB3 | HOLD |  | DATE |  | Post Swap + 3 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB4 | HOLD |  | DATE |  | Post Swap + 4 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB5 | HOLD |  | DATE |  | Post Swap + 5 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB6 | HOLD |  | DATE |  | Post Swap + 6 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB7 | HOLD |  | DATE |  | Post Swap + 7 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB8 | HOLD |  | DATE |  | Post Swap + 14 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB9 | HOLD |  | DATE |  | Post Swap + 30 Days Tasks | 19:00 | . . . . . . .
Command | SYSSIAMUID | HOLD |  |  |  | SIAM UID Update | 19:00 | Y Y Y Y Y Y Y
Command | VC_DAILY |  |  |  |  | Inbound invoice JDA AR | 19:00 | Y Y Y Y Y Y . | BUSDEP
Command | VRM_BLD_R |  |  |  |  | H*VRM Weekly HSTR & HSTCR | 19:00 | . . . . . Y .
Command | VRM_BLD_RY | HOLD |  |  |  | H*VRM Weekly HSTR & HSTCR | 19:00 | . . . . . Y .
Command | WK_DST_SUN |  |  |  |  | WKLY DISTRICT RESULTS-SUN | 19:00 | . . . . . . Y | LEARN
Command | EDISATRF |  |  |  |  | EDI S302 Transfer to SA | 19:25 | Y Y Y Y Y . . | BDAPPLICAT
Command | EML_DUPLNK |  |  |  |  | Check Dupl Recycle Fee | 19:30 | Y Y Y Y Y Y Y | BDAPPLN
Command | SP_CHECK |  |  |  |  | StaplesPartners Check Dtl | 19:30 | . . . . Y . .
Command | ARP010CL |  |  |  |  | AUTO-REPLENISHMENT UPDATE | 19:35 | . . . . . Y . | UPDATE,
Command | FD15TSLSWP | HOLD |  |  |  | H*D15 TDay SL-Fill Rpt-WK | 19:45 | . . . . . Y Y | BD APPLN
Command | CLD_PRICE | HOLD |  |  |  | H*Feeds to Storage Pipe | 20:00 | Y Y Y Y Y Y Y
Command | CLR_OUTQSD |  |  |  |  | Daily Clear Out Queues | 20:00 | Y Y Y Y Y Y Y | CLR_QPRINT
Command | CPC_PRICE |  |  |  |  | *Copy Centre Payments | 20:00 | Y Y Y Y Y Y Y | BD-APPLICA
Command | CPC_RSPO |  |  |  |  | *Auto Resend CPC PO | 20:00 | Y Y Y Y Y Y Y | BD_APP
Command | E3_DUP_PO1 |  |  |  |  | Eml Dup E3 Rls Ord-WKN | 20:00 | . . . . . Y Y
Command | MAWM_DITEM |  |  |  |  | MAWM Daily Item Delta | 20:00 | Y Y Y Y Y Y Y | BD
Command | ST_TYPE27 |  |  |  |  | *Sell Thru Type 27 entry | 20:00 | Y Y Y Y Y Y Y | BD-APPS
Command | SVC_ACT |  |  |  |  | *SVC Card Batch Activate | 20:00 | Y Y Y Y Y Y Y | BD APP SUP
Command | SYSRMTSYNC | HOLD |  |  |  | Sync Robot ALert Files | 20:00 | Y Y Y Y Y Y Y
Command | SYSCHKCQ | HOLD |  | EVERY |  | Check RBNCQ record count | 0:00 | Y Y Y Y Y Y Y
Command | HBT_DCUP |  |  |  |  | DC.COM Upload | 20:30 | Y Y Y Y Y . . | HBT_DCUP
Command | SLCWEEKLY |  |  |  |  | Weekly Sales Contest | 20:30 | . Y . . . . . | SALEQRY
Command | ENDQINTWKE |  |  |  |  | ENDQINTWKE | 20:40 | . . . . . Y Y | LEARN
Command | UP_RELOC2N |  |  |  |  | Reloc Store POS Active=N | 20:45 | Y Y Y Y Y Y Y | BD_APP
Command | HLDJOBQS |  |  |  |  | Hold Job Queues | 20:50 | Y Y Y Y Y Y Y | HLDJOBQS
Command | ENDQINT |  |  |  |  | ENDQINT | 20:55 | Y Y Y Y Y . . | LEARN
Command | EMLPRCPR |  |  |  |  | Email Price Protection | 20:58 | Y Y Y Y Y Y Y | BDAPPLN
Command | DAYSTART |  | REACT |  |  | Day Start | 21:00 | Y Y Y Y Y . . | DAILY
Command | DAYSTARTW |  | REACT |  |  | Day Start | 21:00 | . . . . . Y Y | BD-APP
Command | E3EXCP_E |  |  |  |  | Exception Report EOW | 21:00 | . . . . . Y . | BD APP
Command | MAWM_ZITEM | HOLD |  |  |  | H*MAWM FULL Item Feed | 21:00 | Y . . . . . . | BD
Command | MAWM_ZSTOR | HOLD |  |  |  | H*MAWM FULL Store Feed | 21:00 | Y . . . . . . | BD
Command | MAWM_ZVEND |  |  |  |  | MAWM FULL Vendor Feed | 21:00 | . . . . . . Y | BD
Command | OF_PURGE | HOLD |  |  |  | H*Interface Data Purging | 21:00 | Y . . . . . . | BUSDEP
Command | PKSLIP_101 | HOLD |  | EVERY |  | H*Print Pick Slip-MinDDC | 0:00 | Y Y Y Y Y . . | BDAPPLN
Command | SYSAMLOUTQ | HOLD |  |  |  | AML OUTQ Load | 21:00 | Y Y Y Y Y Y Y
Command | CKDAYSTR |  |  |  |  | Check Resource RBDAYSTART | 21:01 | Y Y Y Y Y Y Y | RBC
Command | CHK_DAYSTR |  |  |  |  | Check DAYSTART/W Status | 21:15 | Y Y Y Y Y Y Y | BDAPPLN
Command | CH_E3_VND |  |  |  |  | Check E3 Vendor in E3SITM | 21:30 | Y Y Y Y Y Y Y | BD_APP
Command | CSH_XTN |  |  |  |  | Cash Bolt-on file-Daily | 21:30 | Y Y Y Y Y . . | BD APPLN
Command | PLNCHGFU | HOLD |  |  |  | H*Add/Del Follow Up Rpt | 21:30 | . . . . . Y . | BD APPLIC
Command | SYSAUDBKUP |  |  |  |  | Audit libraries backup | 21:30 | . . . . . . Y | BRMS
Command | AV_DAILY |  |  |  |  | Outbound Daily Feed to A | 22:00 | Y Y Y Y Y . . | BDAPPLICAT
Command | EM_REFPO |  |  |  |  | Reference PO Report | 22:00 | . . . . . Y .
Command | ESPCUI | HOLD |  |  |  | H*Upld Web ESP Cust Info | 22:00 | Y Y Y Y Y Y Y | BD APPS
Command | F_PDBPRD |  |  |  |  | *FTP Prod Master to PDB | 22:00 | Y Y Y Y Y Y Y | BD_APP
Command | HBT_GNRD |  |  |  |  | TXECCT records generation | 22:00 | Y Y Y Y Y Y Y | HBT_GNRD
Command | SAI_INRF |  |  |  |  | Weekly RF Feed From WIS | 22:00 | . . . . . . Y | BDAPPLICAT
Command | SP_STORE |  |  |  |  | StaplesPartners Store inf | 22:00 | Y Y Y Y Y Y Y
Command | SYSCLNQEZJ |  |  |  |  | Clean QEZJOBLOG | 22:00 | Y Y Y Y . . .
Command | SYSENDMMX |  |  |  |  | Special End of Mimix | 22:00 | . . . . Y . .
Command | SYSILMTHSC |  |  |  |  | ILMT Hardware Scan | 22:00 | Y Y Y Y Y Y Y
Command | UPD_CSTPLN |  |  |  |  | *Set CSTPLN for Tomorrow | 22:00 | Y Y Y Y Y Y Y | BD_APP
Command | CKRBTGNR |  |  |  |  | Check Resource RBRBT_GNRD | 22:01 | Y Y Y Y Y Y Y | RBC
Command | SYSUSRAUD |  |  |  |  | User Auditing Set | 22:15 | Y Y Y Y Y Y Y
Command | EM_IMJCK |  |  |  |  | Email Import Jackie Rpt | 22:25 | . . . . . . Y | BDAPPLN
Command | SYSUSRAUD2 |  |  |  |  | User Auditing Remove | 22:25 | Y Y Y Y Y Y Y
Command | SAI_INFI |  |  |  |  | Weekly FB Feed From Alpha | 22:30 | . . . . . . Y | BDAPPLICAT
Command | SP_OPNPO |  |  |  |  | StaplesPartners opn PO | 22:30 | Y Y Y Y Y Y Y
Command | SYSSIAMAUT |  |  |  |  | SIAM GRTOBJAUT *ALL | 22:30 | Y Y Y Y Y Y Y
Command | FD15TSLSDP | HOLD |  |  |  | H*D15 TDay SL-Fill Rpt-DL | 22:45 | Y Y Y Y Y . . | BD APPLN
Command | DYNSKU_P | HOLD |  |  |  | H*FTP Dynamic Sku List | 22:55 | Y Y Y Y Y Y Y | BDAPPS
Command | CLRJDADEP |  |  |  |  | CLEAR JDA JOB DEPENDENCY | 23:00 | . . . . . . Y
Command | ENDQPGMRSA |  |  |  |  | ENDQPGMRSA | 23:00 | . . . . . Y Y | LEARN
Command | ESPCUO | HOLD |  |  |  | H*Dld AS400 ESP Cust Info | 23:00 | Y Y Y Y Y Y Y | BD APPS
Command | FRN_TRFCNL |  |  |  |  | Cancel outdated furniture | 23:00 | Y Y Y Y Y . . | BD-APPLI
Command | POSCLEANUP |  |  |  |  | POS IFS folder cleanup | 23:00 | Y Y Y Y Y Y Y | BD
Command | PROGRESPTF | HOLD |  | INDAY |  | H*Progress PTF SI14206 | 23:00 | . . . . . . .
Command | SAI_INFW |  |  |  |  | Weekly FW Feed From WIS | 23:00 | . . . . . . Y | BDAPPLICAT
Command | SPOOLSM | HOLD |  |  |  | H*Special spl files save | 23:00 | . . . . Y . . | BRMS
Command | CH_SAE3SKU |  |  |  |  | Check SA E3 Sku Interface | 23:30 | Y Y Y Y Y . . | BD_APP
Command | SAI_INVR |  |  | EVERY |  | SA Weekly Inventory | 0:00 | . . . . . Y . | BD APP
Command | SYSCLNALLS |  |  |  |  | Clean Alliance/SSH | 23:30 | Y Y Y Y Y Y Y
Command | SYSCLNIMAI |  |  |  |  | Clean IMAIL log files | 23:30 | Y Y Y Y Y Y Y
Command | SYSCLNRMA |  |  |  |  | Clean /APPS/RMA/IN | 23:30 | Y Y Y Y Y Y Y
Command | SYSCLNTOWN |  |  |  |  | Clean townsend archive | 23:30 | Y Y Y Y Y Y Y
Command | DCA1_SLSD3 |  |  | EVERY |  | CA Sales Fri-Sat *10 min | 0:00 | . . . . Y Y .
Command | DCA1_SLSWP |  |  | EVERY |  | *CA Sales Sunday *10 min | 0:00 | . . . . . . Y
Command | AUT_OOSCLS |  |  |  |  | Auto Scan Batch Close | 23:45 | Y Y Y Y Y Y Y
Command | CLR_HDMSG |  |  |  |  | Clear Msq Que HD33MSG | 23:45 | . . . . . . Y
Command | EMLPOSERR | HOLD |  |  |  | H*POS File Mering Error | 23:45 | Y Y Y Y Y Y Y | BDAPPLN
Command | N_MAR003JQ |  |  |  |  | End Merch Analzer Rpt | 23:45 | . . . . Y Y . | BD APPLN
Command | AV_HOLIDAY |  |  |  |  | Send Dummy AV CTL-Holiday | 23:50 | Y Y Y Y Y . . | BDAPPLICAT
Command | ENDQPGMRSU |  |  |  |  | ENDQPGMRSU | 23:50 | . . . . Y . . | LEARN
Command | SYSBKUPIPL |  |  |  |  | 3rd Week Shutdown PTF&IPL | 23:50 | . . . . 3 . .
Command | AUT_OOSMIS |  |  |  |  | Track-Create Missing OOS | 23:55 | Y Y Y Y Y Y Y
Command | BPS_OK_NMO |  |  | EVERY |  | MON-Refresh BPS Alloc Qty | 0:00 | Y . . . . . .
Command | BPS_OK_NSA |  |  | EVERY |  | SAT-Refresh BPS Alloc Qty | 0:00 | . . . . . Y .
Command | BPS_OK_NSU |  |  | EVERY |  | SUN-Refresh BPS Alloc Qty | 0:00 | . . . . . . Y
Command | CH_MSGMON2 |  |  | EVERY |  | Check Job has MSGW-MON-#2 | 0:00 | Y . . . . . . | BD_APP
Command | CH_MSGSAT2 |  |  | EVERY |  | Check Job has MSGW-SAT-#2 | 0:00 | . . . . . Y . | BD_APP
Command | CH_MSGSUN2 |  |  | EVERY |  | Check Job has MSGW-SUN-#2 | 0:00 | . . . . . . Y | BD_APP
Command | SUNDAY1 |  |  |  |  | Initiate sunday process | 23:59 | . . . . . Y .
Command | SYSMODCHK |  |  | EVERY |  | check IPL mode | 0:00 | 1 1 1 1 1 1 1
Command | RBNPOLL | HOLD |  | EVERY |  | H*Poll systems in network | 0:00 | Y Y Y Y Y . .
Command | SETOFF_BU |  |  |  | GroupMember | Set BDBACKUP to blank | 99:99 | . . . . . . . | BACKUP
Command | SETON_BU |  |  |  | GroupMember | Set BDBACKUP to active | 99:99 | . . . . . . . | BACKUP
Patrick Town Send Active FTP Records before Switch |  |  |  |  | As of Oct 19 2023
| FTP Definations Active Records |  |  | Scan Dirs Active Records |  | Auto Scan Active Records
FDNAME | FDDESC | FDSTAT | DRNAME | DRDESC | DRSTAT | SCNAME | SCDESC | SCSTAT
AGILENCEPT | Agilence-Transfer/LP/Archive | 1 | AGILEOUT | Send from /Transfer/LP/Out CHG525200 | 1 | BELLKSSCNN | Bell Kiosk Trans files Scan- every minut | 1
BELLACK | Azure Send Copy Ack CHG490772 | 1 | BELLACK | Azure Copy - Send ACK file CHG000490772 | 1 | BELLSHPSCN | Bell Ship Confirm files Scan | 1
BELLKIOGTN | Azure Copy Kiosk-Get every min | 1 | BELLPO | Azure Copy Server PO/PC file | 1 | BOOMERSCAN | Scan corpdmz - CA_report* for boomerang | 1
BELLPO | Azure Copy PO files | 1 | BELLPOR | Azure Copy Server PO Received | 1 | CBTUPSSCAN | CBT UPS Scan file CHG000615788 | 1
BELLPOR | Bell PO Received | 1 | BELLPRI | Azure Copy Server - Send Pricing file | 1 | DATASCNSCN | DATASCAN - SCAN OF REMOTE FOLDER INBOUND | 1
BELLPRI | Azure Copy - Send Price file | 1 | BELLTXN | Azure Copy-Trigger for TXN FileCHG490772 | 1 | DENISSCN | DENIS SUPREME GET REMOTE SCAN | 1
BELLSHPGET | Azure Copy - Ship Confirm get | 1 | BOOMERPUT | Send CA_WHITELIST.CSV to CORPDMZ | 1 | HUBRPTSCN | Hub Report-Scan files CHG000427866 | 1
BELLTXN | Azure SL-Trigger_TXN CHG490772 | 1 | CBTUPSPUT | CBT to UPS Put file CHG000615778 | 1 | LVINGJDASC | Scan files from Livingston CHG000513581 | 1
BOOMERGET | Get CA_report from corpdmz | 1 | CFSGET | CFS - Receive files (GET). | 1 | POSRICOHSC | POS scan Ricoh system CHG000507933 | 1
BOOMERPUT | Send CA_WHITELIST - CORPDMZ | 1 | CFSPUT | CFS - Send files (Put). | 1 | SLSEMPWSCN | SLSEMPWK Scan - labour hour files | 1
CBTUPSGET | CBT UPS Get CHG000615788 | 1 | DATASCNPUT | DATASCAN PUT | 1 | SOLBUILDSC | Solution Builder scan CHG000526328 | 1
CBTUPSPUT | CBT UPS Put CHG000615788 | 1 | DENISPUT | DENIS SUPREME PUT SEND FILES | 1 | STPLEXCHSC | Scan Staples Exchange CHG000477713 | 1
CFSGET | CFS GET | 1 | HBTPUT | Put HBT to lmftpnasv01 | 1 | VENDPERF | Vendor Performance | 1
CFSPUT | CFS PUT | 1 | ILMTFEEDPT | ILMT file feed CHG000509976 | 1
DATASCNGET | DATASCAN GET DEF FOR AUTO SCAN | 1 | POSRICOHAU | Change Authority on /pos/XMLRCH/Tmp file | 1
DATASCNPUT | DATASCAN PUT DEFINITION | 1 | SAPGPIN | SA PGP IN - decrypt and move. | 1
DENISGET | DENIS SUPREME GET DEF OPT 14 | 1 | SAPUT | Staples Advantage (CE -CA) Put files. | 1
DENISPUT | DENIS SUPREME SEND DEF OPT 5 | 1 | SAPUTE3 | Staples Advantage (JDA E3) Put files | 1
HBTPUT | Put HBT to lmftpnasv01 | 1 | SAPUTPGP | Staples Advantage (CE-CA) Put PGP files. | 1
HUBRPTGET | Hub Report-Get files CHG435517 | 1 | SLSEMPW | SLSEMPW - Process Inbound files | 1
ILMTFEEDPT | ILMT file feed CHG000509976 | 1 | SPPUTNEW | Staples Partners push | 1
LVINGJDAGT | Get from Livingston CHG513581 | 1 | STGPSEND | Storage Pipe FTP trans Send file | 1
POSRICOHGT | POS from Ricoh CHG000507933 | 1 | STGPSSHAUT | Chance Authority /pos/XMLCLD/Tmp files | 1
SAGETSCN | Staples Advantage - Get files | 1 | XRXPUT | Push files from xeroxput to Xerox | 1
SAPUT | Staples Advantage Put. | 1
SAPUTE3 | SA JDA E3 FTP TO FTP SERVER | 1
SLSEMPWGET | SLSEMPWGET - labour hour | 1
SOLBUILDGT | SolBuilder get CHG000526328 | 1
SPPUTNEW | sppytnew | 1
STPLEXCHGT | Get from StaplesEx CHG00047771 | 1
VENDPERF | Vendor Peformance | 1
XRXPUT | Send files to Xerox | 1

## P1 BUSDEP SHUTDOWN
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
|  | 5:30AM |  |  | BUSDEP | Use HMC to connect in QCTL susbsystem.
[5 empty] | BUSDEP | Sign on using QSECOFR id
[5 empty] | BUSDEP | Type WRKJOBQ and ensure that no jobs are waiting to be run from all job queues.
[5 empty] | BUSDEP | Type WRKACTJOB to check if no jobs are running in the following batch subsystems: BRMSSBS, DCDIRECT, OPERATIONS, QBATCH, QBATCHE3, QBSDI, QWEEKEND, SYSMGMT
[5 empty] | BUSDEP | ADDLIBLE SECMANISH
[5 empty] | BUSDEP | Submit DRSHUTDOWN as follows to shutdown the system in a normal order.
SBMJOB CMD(CALL PGM(SECMANISH/DRSHUTDOWN)) JOB(DRSHUTDOWN) JOBQ(QCTL) LOGCLPGM(*YES) HOLD(*YES)
if ready to SHUTDOWN, release this job from QCTL jobq
[5 empty] | BUSDEP | Type ENDTCPIFC INTNETADR('10.19.244.76') to end the user connection TCP interface. This is to ensure that no users can sign on to BUSDEP using BUSDEP DNS name and to prevent any FTPs in and out of the box. |  |  | User connection Interface
[5 empty] | BUSDEP | Type RBTAUTOSTR AUTOSTART(*NO) so that RBTSLEEPER sbs will NOT start Robot Scheduler. On DR system, only Alert and Console is needed. |  |  | BUSDEP is going to be new DR system
[5 empty] | BUSDEP | Varry off all APPC cntl first for APPN control point to be able to change
[5 empty] | BUSDEP | Type CHGNETA LCLCPNAME(BUSDEPHA) LCLLOCNAME(BUSDEPHA) Change local control point and local location name to BUSDEPHA |  |  | This is needed for SNA and APPC controllers on BUSDEP
[5 empty] | BUSDEP | Change QSTRUPPGM system value to MIDRANGE/QSTRUPHA. This is to run same start up program as BUSDEPHA after role swap.
[5 empty] | BUSDEP | Type CHGIPLA STRTCP(*YES) - this is needed to start tcp after IPL on DR box since not managed by Robot job SYSBKUP2.
[5 empty] | BUSDEP | Release jobs from WRKJOBSCDE as follows:
[5 empty] | BUSDEP | Type WRKSBS and ensure that only the following subsystems are running.
[5 empty] | BUSDEP | End AUD300DP job from QCTL before switch

## P1 BUSDEPHA SHUTDOWN
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
|  | 5:30AM |  |  | BUSDEPHA | Use HMC to connect in QCTL susbsystem.
[5 empty] | BUSDEPHA | Sign on using QSECOFR id
[5 empty] | BUSDEPHA | Type HLDJOBSCDE JOB(*ALL) to hold all job schedule entries from native job scheduler.
[5 empty] | BUSDEPHA | Type WRKJOBQ and ensure that no jobs are waiting to be run from all job queues.
[5 empty] | BUSDEPHA | Type WRKACTJOB to check if no jobs are running in the following batch subsystems: BRMSSBS, DCDIRECT, OPERATIONS, QBATCH, QBATCHE3, QBSDI, QWEEKEND, SYSMGMT
[5 empty] | BUSDEPHA | ADDLIBLE SECMANISH
[5 empty] | BUSDEPHA | Submit DRSHUTDOWN as follows to shutdown the system in a normal order.
[5 empty] | BUSDEPHA | SBMJOB CMD(CALL PGM(SECMANISH/DRSHUTDOWN)) JOB(DRSHUTDOWN) JOBQ(QCTL) LOGCLPGM(*YES) HOLD(*YES)
if ready to SHUTDOWN, release this job from QCTL jobq
[5 empty] | BUSDEPHA | Type WRKSBS and ensure that only the following subsystems are running. MIMIXSBS, QCTL, QSERVER, QSYSWRK
[5 empty] | BUSDEPHA | Type ENDTCPIFC INTNETADR('10.19.240.76') to end the user connection TCP interface. This is to ensure that no users can sign on to BUSDEPHA using BUSDEPHA DNS name and to prevent any FTPs in and out of the box. |  |  | User ip

## P1- DNS and NETWORK Switch
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
[5 empty] | Network | Contact Staples Network Support team to make DNS changes. DNS BUSDEP, BUSDEP.staplescan.com and BUSDEP.staples.com to point to BUSDEPHA ip 10.19.240.76. |  | Bart / Wayne
[5 empty] | Network | Contact Staples AZURE team to make DNS changes for BUSDEP in AZURE prod environment to point to BUSDEPHA ip 10.19.240.76. |  | Bart / Wayne
[5 empty] | MAR4DEV1/BUSDEP/BUSDEPHA | Flip BUSDEP IP to point to BUSDEPHA IP 10.19.240.76, and BUSDEPHA IP to point to BUSDEP IP 10.19.244.76 in the local host table entries.( CFGTCP option 10 ) | This is needed for all FTP to BUSDEP, SNADS, and IMPLEMENTOR code promotions
[5 empty] | BUSDEPHA | Chagne Domain Name to BUSDEP from BUSDEPHA in CFGTCP option 12 ( if needed )
[5 empty] | BUSDEP | Chagne Domain Name to BUSDEPHA from BUSDEP in CFGTCP option 12 ( if needed )

## P1 BUSDEPHA STARTUP
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
|  |  |  | 1 | BUSDEPHA | Use MARKHAM HMC to connect in QCTL susbsystem.
|  |  |  | 10 | BUSDEPHA | Update system name as BUSDEP in ROBOT as follows: ROBOTLIB/RBTSWAPSYS SOURCESYS(BUSDEP) TARGETSYS(BUSDEPHA) | TGT system name should be same on where you run this command | Midrange
|  |  |  | 1 | BUSDEPHA | Type STRTCPIFC INTNETADR('10.19.240.76') to start the user connection TCP interface.
|  |  |  | 1 | BUSDEPHA | Varry off all APPC cntl first for APPN control point to be able to change
|  |  |  | 1 | BUSDEPHA | Type CHGNETA LCLCPNAME(BUSDEP) LCLLOCNAME(BUSDEP) Change local control point and local location name to BUSDEP |  |  | This is needed for SNA and APPC controllers on BUSDEPHA
|  |  |  | 1 | BUSDEPHA | Type RBTAUTOSTR AUTOSTART(*NO) so that RBTSLEEPER sbs will NOT start Robot Scheduer | This is needed to hold the regular schedule jobs before missed jobs to be run
[5 empty] | BUSDEPHA | Confirm that ROBOT Scheduler is INACTIVE in RBO | Very Important that no jobs start running at this point on BUSDEPHA DR system
· Type RBO
· Take option 1 Robot Schedule
· Take option 3 Control Menu
· Check the status at top right corner should be INACTIVE
|  |  |  | 5 | BUSDEPHA | Hold all Patrick Townsend FTP jobs: | > UPDATE ALLFTM100/ANFTPD set FDSTAT = '2' |  | HOLD PT
[6 empty] | · Sign on as QSECOFR | 134 rows updated in ANFTPD in ALLFTM100. |  | HOLD PT
[6 empty] | · Type STRSQL | > UPDATE ALLFTM100/ANDIRS SET DRSTAT= '2' |  | HOLD PT
[6 empty] | · UPDATE ALLFTM100/ANFTPD set FDSTAT = '2' | 75 rows updated in ANDIRS in ALLFTM100. |  | HOLD PT
[6 empty] | · UPDATE ALLFTM100/ANDIRS SET DRSTAT= '2' | > UPDATE ALLFTM100/ANSCAN set SCSTAT = '2' | Not needed | HOLD PT
[6 empty] | · UPDATE ALLFTM100/ANSCAN set SCSTAT = '2' | 44 rows updated in ANSCAN in ALLFTM100. |  | HOLD PT
[6 empty] | · Verify that all PT FTP definitions, Scan Directories/File Actions and Auto Scan records are in Inactive status. |  |  | HOLD PT
|  |  |  | 10 | BUSDEPHA | On BUSDEPHA, update hardcoded local IP in SUNRISE, SUNBEAM, MAR4DEV1, GALAXY APPC controllers to point to 10.19.240.76. (WRKCFGSTS, Vary off, Change IP, Vary On)
[5 empty] | SUNRISE, SUNBEAM, MAR4DEV1 and GALAXY | On SUNRISE, SUNBEAM, MAR4DEV1 and GALAXY, update hardcoded remote IP in BUSDEP APPC controller to point to 10.19.240.76 (WRKCFGSTS, Vary off, Change IP, Vary On) | Call iseries on call support at 508-253-3314
|  |  |  | 1 | BUSDEPHA | Type WRKJOBQ and check if all the job queues in Release status.
|  |  |  | 1 | BUSDEPHA | Change QSTRUPPGM system value to ITTOOLS/QSTRUP. This is to run same start up program as BUSDEP after role swap.
|  |  |  | 1 | BUSDEPHA | Comment out STRSBS QINTER command in ITTOOLS/STARTINTER file.
|  |  |  | 1 | BUSDEPHA | Comment out STRSBS QPGMR command in ITTOOLS/STARTBATCH file.
|  |  |  | 5 | BUSDEPHA | Change Or Confirm SMTP settings in Patrick Townsend, IMAIL and ROBOT Alert as follows:
PATRICK TOWNSEND FTP (ALLIANCE FTP MANAGER)
· ADDLIBLE ALLFTM100
· GO AMMAIN
· Option 31 Email menu
· Option 1 SNMP email menu
· Option 10 Application settings
· Change local host name to BUSDEPHA
This value is replicated and BUSDEP needs to be changed to BUSDEPHA
Completed
IMAIL
· Addlible iMail
· Go IMAIL
· Option 1
· Change Domain Name to Staplescan.com
· Press F10 to save
Completed. EMAIL test worked as is using BUSDEP name from HA box.
This might need to change to BUSDEPA for BUSDEP in Local Host and Email addresses
This might need to change to BUSDEPA for BUSDEP in Local Host and Email addresses
This might need to change to BUSDEPA for BUSDEP in Local Host and Email addresses
This might need to change to BUSDEPA for BUSDEP in Local Host and Email addresses
ROBOT ALERT
· ADDLIBLE ROBOTLIB
· ADDLIBLE RBTALRLIB
· ADDLIBLE RBTCONLIB
· Type RBO
· Take option 2 Robot Alert
· Take option 3 Directory Menu
· Take Option 1 Vendor Maintenance Menu
· Take Option 2 Maintain Existing Vendors
· Take Option 1 to Select SPLSEMAIL
· Change SMTP Host to SCASMTPINT.STAPLESCAN.COM
Completed
|  |  |  | 10 | BUSDEPHA | Start system as follow:
· Sign on as QSECOFR.
[6 empty] | · STRSBS QCTL (This should be running already). This will start QSYSWRK subsystem and will run STRTCP command | Already running
[6 empty] | · STRSBS QSERVER | Already running
[6 empty] | · STRSBS QUSRWRK | Already running
ADDLIBLE SECMANISH
[6 empty] | Submit DRSTARTSYS as follows to start the system in a normal order. | CALL RBT103 was commented to not start RBT Scheduler in STRRBT cl.
|  |  | 7.15 |  |  | SBMJOB CMD(CALL PGM(SECMANISH/DRSTARTSYS)) JOB(DRSTARTSYS) JOBQ(QCTL) LOGCLPGM(*YES) HOLD(*YES) JOBD(QGPL/QDFTJOBD) USER(MISOPR) | STRSBS RBTSLEEPER sbs will start all robot products accept Robot scheduler
if ready to START SYSTEM, release this job from QCTL jobq
|  |  |  | 1 | BUSDEPHA | Type WRKSBS and verify that the following subsystems are running except QINTER and QPGMR subsystems from the list below.
|  |  |  | 1 | BUSDEPHA | Type WRKACTJOB SBS(QHTTPSVR) and verify that the following HTTP and IWS jobs are running. These are needed for IBM Web services.
|  |  |  | 1 | BUSDEPHA | Type WRKACTJOB SBS(QCMN) and verify that the E3COMSERV job is running. These are needed for E3 AWR and ASR application.
|  |  |  | 1 | BUSDEPHA | Type WRKACTJOB SBS(QUSRWRK) and verify that the M3005 and D3005 jobs are running. These are used by IMPLEMENTER receiver.
|  |  |  | 1 | BUSDEPHA | Type WRKACTJOB SBS(ZMHTTPSRV) and verify that the AS2 jobs are running. These are needed by AS2 application.
|  |  |  | 1 | BUSDEPHA | Type WRKACTJOB and verify that below jobs are running in ZPSE, ZPSSMON and ZALOG subsystems. These are needed by NetIQ Security application.
AS2 Proxi job did not start and had to DO on AS2RESETDP job from Robot
|  |  |  | 1 | BUSDEPHA | Type WRKACTJOB SBS(RBTSLEEPER) and verify that below jobs are running These are needed by ROBOT products.
|  |  |  | 1 | BUSDEPHA | Type WRKACTJOB SBS(ALFTM100) and verify that below jobs are running These are needed by Patrick Townsend FTP product.
|  |  |  | 1 | BUSDEPHA | Type CFGTCP and take option 1 to verify that the following interfaces are active.
|  |  |  | 1 | BUSDEPHA | Release all the Store Printer Output queues ( Pnnnnnnn )
|  |  |  | 1 | BUSDEPHA | Add supplememtal groups PROD and EMGPRO to developers id so they can do validations
|  |  |  | 1 | MIDRANGE | Ensure that enough tapes are loaded in MARKHAM LOCATION TAPE library that can accommodate daily and weekly backups from BUSDEPHA
|  |  |  | 5 | BUSDEPHA | Hold jobs from WRKJOBSCDE as follows as backups and BRMS jobs runs from Robot on BUSDEPHA in DR mode.
|  | Total |  | 66 | MIN
Note on G16: Tamakuwala, Manish: > UPDATE ALLFTM100/ANFTPD set FDSTAT = '2' 129 rows updated in ANFTPD in ALLFTM100. > UPDATE ALLFTM100/ANDIRS SET DRSTAT='2' 72 rows updated in ANDIRS in ALLFTM100. > UPDATE ALLFTM100/ANSCAN set SCSTAT = '2' 42 rows updated in ANSCAN in ALLFTM100. Remove trailing spaces to avoid Invaid Token

## P1 BUSDEPHA Validation
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
1 | Sunday | 8:00AM | 9:00AM |  |  | Start POS FTPs services for a sample test store only ( 49 or 91 or 448 stores) | Before GO Validation | Alain Miron / Joyal | Alain / Joyal to confirm stores
2 | Sunday | 8:00AM | 9:00AM |  | BUSDEPHA | Add PROD and EMGPROG supplimentry groups to Developers profiles for production access to test | Before GO Validation | Manish
Run CL SECMANISH/DRGRTAUTH
3 |  |  |  |  | BUSDEPHA | Vendor Software Verification
4 | [5 empty] | · Verify Client Access / ACS functions |  | Manish
5 | [5 empty] | · Verify DBU functions |  | Masoud
6 | [5 empty] | · Verify IMAIL functions |  | Masoud/Manish
7 | Sunday | 8:00AM | 9:00AM |  |  | · Verify MARKMAGIC to be able to print Forms/labels | Before GO Validation | Masoud
8 | [5 empty] | · Verify TAATOOL functions |  | Manish
9 | [5 empty] | · Verify ROBOT Schedule, Alert and Robot Console functions |  | Manish
10 | [5 empty] | · Verify IMPLEMENTER functions to promote code from MAR4DEV1 |  | Masoud/Manish
11 |  |  | ` |  |  | · Verify NetIQ Pentasafe functions |  | Manish
12 | [5 empty] | · Verify OpenText Liaison functions (Peter to test) |  | Peter / Stephen
13 | [5 empty] | · Verify Gentran functions (Peter to test) |  | Peter / Stephen
14 | [5 empty] | · Verify Patrick TownSend functions (with Dennis and Supreem, Martin is the contact ) |  | Manish
15 |  |  |  |  | BUSDEPHA | Network Verification
16 | Sunday | 8:00AM | 9:00AM |  |  | · Verify store connection (store #49, 91 and 448) from Bell and TELUS Network as well as checkpoint / ISR routers | Before GO Validation | Wayne / Helpdesk / Bart / Haran
17 | [5 empty] | Store 49, Telus MPLS (Montreal) |  | Mustapha Medani GM 438-832-1509
18 | [5 empty] | Store 91, Bell MPLS (Nova Scotia) |  | Leanne Candelora at 902 565-1652 (cell #)
19 | [5 empty] | Store 448, Broadband (Toronto) |  | Joshua Cere Service mgr 905 246 2141 Frank Caruso General Manager Store 448 Frank Caruso General Manager Store 448
20 | [5 empty] | · Verify FC99 and FC351 FC connection on Monday due to FC not available on Weekends |  | Wayne / FC users | Patrick to follow up with FC99 and FC 351 for users, NOT required, FC not working on weekend
21 | [5 empty] | · Verify Mini-DDC (317) connection ( Converted to TCPIP printing from SNADS ) |  | Patrick | find a resource from 317
22 | [5 empty] | · Verify Client Access and Citrix connection using DRTESTxx sessions. Use 3 stores with different networks |  | Manish / Masoud / HelpDesk /Wayne | Haran to provide Helpdesk resource
23 | Sunday | 8:00AM | 9:00AM |  |  | · Verify store scanner functions (store #49,91,448). QPGMR or BUSDEP/SCANNERS SBS needs to be started for test | Before GO Validation | Masoud / Store Associate / Help Desk | Haran to provide Helpdesk resource, need stores that are opened. Need to get east coast stores for testing. Manish to turn on QPGMR SBS then turn off after test | Mukesh
24 | [5 empty] | · Verify home office and VPN connections |  | Wayne / Bart
25 |  |  |  |  | BUSDEPHA | JDA Basic Functions
26 | [5 empty] | · Verify BRMS Backup functions |  | Manish / Midrange
27 | Sunday | 8:00AM | 9:00AM |  |  | · Verify DDM, APPC, ICF file connections with Sunrise and Sunbeam. Need a CR for iSeries Engineering team support | Before GO Validation | Manish / Patrick / iSeries Team US | iSeries team US configure first, then Patrick's team to test
28 | [5 empty] | · Verify Emmergency profile check out tool works |  | Masoud / Manish
29 | [5 empty] | Verify labour hours entered on BUSDEP for store 462 replicated to BUSDEPHA |  | Stanley followup
30 | Sunday | 8:00AM | 9:00AM |  |  | · Verify Printer testing to store xxx | Before GO Validation | Masoud | Need to find a store that will be opened, tie to store scanner test (use the same store #)
31 | [5 empty] | · Verify Printer testing at home office |  | Masoud
32 | [5 empty] | · Verify FTP using port 21 (Various Contacts) |  | Masoud
33 | [5 empty] | · Verify RightFax Connection : Move a test fax spool file called REPORT from SECMANISH outputq to QGPL/PULSE output queue. Call MIKE Gee to confirm if he received the FAX. |  | Manish / Masoud / Michael Gee (US)
34 |  |  |  |  | BUSDEPHA | JDA Critical Functions
35 | [5 empty] | · Verify JDA MMS basic functions |  | Masoud / Zoya
36 | [5 empty] | · Verify User JDA MMS Menu function via Navigating the JDA MMS menu, access different screens without making any updates. |  | Masoud / Zoya | For Business Role Swap, needs Finance and Merch
37 | [5 empty] | Verify STRPATHR function ( this should work on BUSDEP ) |  | Manish
38 | [5 empty] | · Verify AS2 Proxy sever connection |  | Peter / Stephen
39 | [5 empty] | · Verify EDI connection |  | Peter / Stephen
40 | [5 empty] | · send 997 to external, one through AS2, one thrugh VAN
41 | [5 empty] | · Verify JDA E3 ASR/AWR connection |  | Curtis / Nasser / Manish
42 | Sunday | 8:00AM | 9:00AM |  |  | · Verify Price File FTP to CPC via Patrick Townsend. | Before GO Validation | Manish / Jun Ling / Carol | use dummy file to test
43 | [5 empty] | Put the trigger file in IFS using a menu option on MENIOD optin 26 | Before GO Validation
44 | [5 empty] | From PT, Run the BELLPRI ftp defination and Scan Dir to ACTIVE so file will be picked up and FTPed | Before GO Validation
45 | [5 empty] | · Verify Salesforce order processing |  | Masoud / Ken
46 | Sunday |  |  |  |  | · Verify FTP from BUSDEP to Access Via using Store 448 as test store, VIABATC, Uses scanner to request a print signage |  | Sonja / Rachael / Stanley
47 | Sunday | 8:00AM | 9:00AM |  |  | · Verify BOPIS inventory count / MLS Webservices | Before GO Validation | Masoud / Manish / Stuti / Jitendra (US Team) | Manish to call US team if any issues
48 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Kiosk Order ( Solution Builder ) | Before GO Validation | Carol / Ramya
49 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Online SalesPosting, Return and Refund (via EAI) | Before GO Validation | Ramya // Anson | Need to stop actual hellboy posting during roleswap
50 | Sunday | 8:00AM | 9:00AM |  |  | Ding / Anson will post an open transaction to validate the connection | Before GO Validation
51 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Store Return, Refund (via EAI) , | Before GO Validation | Ramya / Anson
#REF! | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - BINQTY (from BUSDEP to POS) , | Before GO Validation | Yajun / Ramya
#REF! | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - INVAUD (from BUSDEP to CMIS) | Before GO Validation | Yajun / Ramya
#REF! | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - ECP Sync (from ETS to Busdep) | Before GO Validation | Yajun / Ramya
#REF! | Sunday | 8:00AM | 9:00AM |  |  | http://busdep:10021/web/services/ECPCaseStoreUpdService/ECPCaseStoreUpd | Before GO Validation
| Sunday | 8:00AM | 9:00AM |  |  | Verify ODBC connection from Sequel 16 to BUSDEP server | Before GO Validation | Kevin
| Sunday | 8:00AM | 9:00AM |  |  | Verify ODBC connection from Sequel 05 to BUSDEP server | Before GO Validation | Kevin
[6 empty] | Verify file generated and FTPed to SVS server ( depends on ECP IWS working ) | Before GO Validation | Kevin / Stanley
#REF! | Sunday | 8:00AM | 9:00AM |  |  | Verify IWS Web Service - HBT ( Host Based Tax ) ( via EAI ) | Before GO Validation | Ramya via Postman | Need resource from Alain
#REF! | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Inventory Lookup (for CPC), | Before GO Validation | Ramya via Postman | similar to step 4.17 for same resource to do
#REF! | Sunday | 8:00AM | 9:00AM |  |  | http://BUSDEP.staples.com:8088/ws/WSIVS10/OnHand/15/934103/0/0 | Before GO Validation
#REF! | Sunday | 8:00AM | 9:00AM |  |  | Verify IWS Web Service - Inventory Lookup (for POS), Can be tested from Postman | Before GO Validation | Alain / Haran / Joyal | Need resource from Alain, Chris to follow up with Tong
#REF! | Sunday | 8:00AM | 9:00AM |  |  | Verify Manhattan to Busdep: Resend: Item, Vendor, Store, Order, PO, ASN | Before GO Validation | Zoya
#REF! | Sunday | 8:00AM | 9:00AM |  |  | Verufy Busdep to Manhattan: Resend: Receipt, Verification, ShipConfirm, Adjustment, InventorySynch | Before GO Validation | Zoya
#REF! | Sunday | 8:00AM | 9:00AM |  |  | · Verify POS connectivity from Store (Price Download), Price file to be deleted after test is over | Before GO Validation | Masoud / Joyal
#REF! | Sunday | 8:00AM | 9:00AM |  |  | · Verify POS connectivity from Store (Sales Upload), store # 49,91,448) to be used | Before GO Validation | Masoud / Joyal
#REF! | [5 empty] | Test DATASCAN FTP |  | Manish
#REF! | [5 empty] | Test DenisSupreme |  | Manish
#REF! |  |  |  |  | BUSDEPHA | Receive Business sign off on validation test |  | Edward / Manish

## P1 -BUSDEPHA GO LIVE
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
[5 empty] | BUSDEPHA | Communicate to Busines when system will be available to all stores and home office users
[5 empty] | BUSDEPHA | Start all POS FTPs services |  | Alain Miron / Joyal | 905-716-3377
[5 empty] | BUSDEPHA | Start all FC Sales Feed |  | Devop team / Jerry
[5 empty] | BUSDEPHA | Start all Salesforce orders feed |  | Ken / Emma
[5 empty] | BUSDEPHA | Start all Copy and Print orders |  | Bonny / Carol
[5 empty] | BUSDEPHA | Start Zuora Transactions/ Allstate / TSS |  | Kevin Liang (Bo) / Jamie
[5 empty] | BUSDEPHA | Start Inventory Sync from Manhanton WMS |  | Karthik / Edward to send email
[5 empty] | BUSDEPHA | Use MARKHAM HMC to connect in QCTL susbsystem.
[5 empty] | BUSDEPHA | Allow all store users and home office users to sign on to BUSDEP
· Type STRSBS QINTER
· Type STRSBS QPGMR
· Type WRKACTJOB SBS(QINTER) and WRKACTJOB SBS(QPGMR) to verify users sessions.
[5 empty] | BUSDEPHA | Change the status of Patrick Town send jobs to ACTIVE to their actual matching status as follows: |  | Manish | P0 PREPERATION SWITCHBACK listing to be used
[6 empty] | Sign on as QSECOFR |  |  | This CL will run a SQL query from SECMANISH/QSQLSRC(DRUPDPTSTS)
[6 empty] | Run a CL using CALL SECMANISH/DRUPDPTSTS |  |  | Ensure that QSQLSRC(DRUPDPTSTS) has latest PT active records from PO Prepration Switch TAB
Take option 7 to start on all AUTO scan active jobs to start
Check in PT that all status are active for FTP Definations, SCAN dir and Auto Scan
[5 empty] | BUSDEPHA | Run VRINCOME job that was cancelled by Stanley on BUSDEP before role swap. This jobs is dependant job for VRM_INVOIC and VRM_WKND job below. |  | Stanley / Nasser
[5 empty] | BUSDEPHA | Run VRM jobs CCL_WKLY, VRM_WKRPT, VRM_INVOIC and VRM_WKND that were held by Nasser on BUSDEP before roleswap. |  | Stanley / Nasser
[5 empty] | BUSDEPHA | Run all jobs that were submitted from Robot that were missed on BUSDEP between 3AM to GO-LIVE. |  | Stanley / Nasser | Stanley has steps to run all job based on dependency
[5 empty] | BUSDEPHA | Make ROBOTScheduler ACTIVE in RBO to start running all jobs as per normal schedule |  |  | All jobs should have same status as BUSDEP due to replication on ROBOT libs
· Type RBO
· Take option 1 Robot Schedule
· Take option 3 Control Menu
· Take option 1 Start Robot
· Check the status at top right corner should be ACTIVE
[5 empty] | BUSDEPHA | Remove comments from STRSBS QINTER command in ITTOOLS/STARTNTER file.
[5 empty] | BUSDEPHA | Remove comment from STRSBS QPGMR command in ITTOOLS/STARTBATCH file.
[5 empty] | BUSDEPHA | Remove comments from SUNDAY1 job for job 312 PRODSUDP submission since it needs to go back to normal schedule
[5 empty] | BUSDEPHA | Release SUNDAY2 job since it needs to go back to normal schedule
[5 empty] | BUSDEPHA | Release SYSSTRSBS job since it needs to go back to normal schedule
[5 empty] | BUSDEPHA | Type RBTAUTOSTR AUTOSTART(*YES) so that RBTSLEEPER sbs start Robot Scheduler in a normal way |  |  | BUSDEPHA is a production system from here.
[5 empty] | BUSDEPHA | Update system name parameter for EMG Profile Inquiry MENIOD option 14 as follows: (1) CALL A, MENU MENMEN Option 1, Enter MENIOD and press Enter twice, then enter menu option to maintain to 14, change the system name to BUSDEPHA in Parameter 1 field. Press Enter to save.
[5 empty] | BUSDEPHA | Type CHGIPLA STRTCP(*NO) - this is NOT needed on production box since managed by Robot job SYSBKUP2. |  |  | Original setting of BUSDEP
[5 empty] | BUSDEP | Start RBT Alert and Console. ( NO Rbt Schedule should be started due to direct replication )
[5 empty] | BUSDEPHA | Remove PROD and EMGPROD groups from developers/testers profiles
Run CL SECMANISH/DRRVKAUTH
At this point,
· All store and home office users are able to sign on and update or send/receive files
· All ROBOT jobs are active to run at their scheduled date and time
· Patrick Town send jobs are active to run at their scheduled time
· All BRMS backup jobs to run as scheduled
END OF DR FAILOVER EXERCISE !!
to be removed later on after next role swap
[5 empty] | BUSDEPHA | Run CPC_TXNPCK trigger job for Carol/Jun Ling FTPs |  |  | This is just a priority job to run before running all jobs via Script
[5 empty] | BUSDEPHA | Upload DOJOBS file from the DOJOBS Upload Tab in this Excel to SECMANISH library on BUSDEP
[5 empty] | BUSDEPHA | Update DOJOBS file to inclue only jobs to run upto the time of the call to DRDOJOBS ( exampl 2AM to 9AM during the outage at that timestamp )
[5 empty] | BUSDEPHA | Run SECMANISH/DRDOJOBS cl run all jobs that were missed on BUSDEPHA during role swap. These jobs were identified in P0 Preperation Tab.
[5 empty] | BUSDEPHA | Run all E3xxxxxxxx jobs as follows: (1) E3_FREEZE to run as normal from DOJOBS list (2) E3_DAYEND to run after 15 mins of E3_FREEZE run (3) E3TWAIT to run after 15 mins of E3_DAYEND run |  | Stanley / Nasser
[5 empty] | BUSDEPHA | Run MOOSE3_WP job after all E3xxxxxxx jobs finished in above step. |  | Stanley / Nasser
[5 empty] | BUSDEPHA | Run reactive job RPL_SUGQTY job that was cancelled on BUSDEP before role swap |  | Stanley / Nasser
[5 empty] | BUSDEPHA | Run Call SECMANISH/DRRBTOVRR cl to release all ROBOT scheduled jobs to their actual status. |  |  | Ensure that SECMANISH/RBTOVRRIDE file exist from P0 Preperation for Switch Tab
[5 empty] | BUSDEPHA | After 12:00 MIDNIGHT on Sunday, Set Auto Run option to Y in Robot Scheduler as follows |  |  | This value to be only changed after DR test is complete and ready to resume with next day operation after midnight
· Type RBO
· Take option 1 Robot Schedule
· Take option 4 System Setup menu
· Take option 1 General System Defaults
· Change Run Auto work at Startup of ROBOT to value Y
· This option will ensure that no jobs will run that were missed after 12 midnight due to outage on BUSDEP during the role swap.

## P3 PREPERATION FOR SWITCHBACK
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
[5 empty] | BUSDEP | Apply or Verify vendor software license keys as follows: ( Turn off MIMIX replication if needed for some products due to file lock on BUSDEPHA )
ROBOT SCHEDULE
· ADDLIBLE ROBOTLIB
· CALL RBT240
· Press F11 to cut/paste the license code in the License Code field and press Enter to save the license keys.
[6 empty] | Q0S889F4F5KU5Y+03MSXE3EYTX13*P863GLM3YEN2MRG03QZ8TM+LJ3QV*Y6ICT6JQK6HBE6T16 | completed
ROBOT ALERT
· ADDLIBLE RBTALRLIB
· CALL RBA250
· Press F11 to cut/paste the license code in the License Code field for appropriate lpar as below and press Enter to save the license keys
[6 empty] | DGR8A73D02RXSR3Q09STM0MUSMU0W0WX0B730ZB74VVB90IA1HVGLA0*5GZX46PX2K+XKSZFTUX | completed
ROBOT CONSOLE
· ADDLIBLE RBTCONLIB
· CALL RBC245
· Press F11 to cut/paste the license code in the License Code field for appropriate lpar as below and press Enter to save the license keys
[6 empty] | 7ZI01 8E4B8 HPEEU 3*R36 X*X8F 6I*X4 FL*WR **AA3JEIQJT24A8 LI*PT71C51GX81P391ZM93831 | completed
IMAIL
· These codes are for IMAIL30 product and same code were applied for IMAIL product as well.
· ADDLIBLE IMAIL ( for BUSDEP and BUSDPHA )
· ADDLIBLE IMAIL30 ( only on MAR4DEV1 )
· Type REGISTER and press Enter
· From the Module Registration Screen, Cut Paste keys for IMAIL and IMAIL30 products on appropriate lpars as follows:
· Press F10 to update
[6 empty] | IMAIL: 33;38XgCXgX73Cgp6GG7CC1P07pXg3XXXVg3CT29CC3c | completed
[6 empty] | IMAIL30: 33;38XgCXgX73Cgp6GG7CC1P07pXg3XXXVg3CT29CC3c | completed
DBU11
· ADDLIBLE DBU11
· Type DBUSEC and copy and paste the bolded key below.
· Press Enter
Serial Software Rls Access Code
7887C00 DBU 11.0 A3B7DB 8F50C0 FC3E01 5103 ________enter partition 3
IMPLEMENTOR
· ADDLIBLE IMPRCV
· Cut Past keys as follows for appropriate lpar
· Cut and past this entire line from command line
[6 empty] | RESET SECSTR(00062900 70900400 04804102 60669999 64894795 19900034) LIB(IMPRCV) | Can not see the existing codes | Cut and past this entire line from command line
MARKMAGIC Ver 10
· Sign on as QSECOFR
· Enter command MRKMAG100/SETMMPRM
· Press F8 to enter key information
*LIST Prod: MM100 Mod: 42A S/N: 7887C00 Proc: P20
EXP LPAR USERs PTRs KEY
*PERM RUN Labels 99/99/99 3 999999 999999 C9490 D18BB 9CD06 AC501
*PERM Opt-PDF 99/99/99 3 999999 999999 5A3D8 3C348 60E24 21301
OPENTEXT
· ADDLIBLE ZMODLIB10
· Type setzmlic copy and paste your license codes
[6 empty] | nuBridges secure EDIIP . . . . . . . . . . Jx/3/8KosrYI | code expires *PERM | 9999 Partners
[6 empty] | nuBridges HTTP Client . . . . . . . . . AADz/xnXD30M | code expires *PERM
GENTRAN
· MAR4DEV1 keys were used on BUSDEPHA box due to it is serial number-based keys
ADDLIBLE G3X5PGM
ADDLIBLE G3X5DTA
Type EXTEND and F4 prompt and input the product extension code:
[6 empty] | Extension Code . . . . . . . . . . 8 49 99C A0 99778920 | Code can not be displayed
Enter ACTFTP and F4 prompt and input the FTP activation code:
[6 empty] | Activation Code. . . . . . . . . . 7 990 9890 A978C9 42 | Code can not be displayed
TAATOOLS
· ADDLIBLE TAATOOL
· Type CHGTAAKEY and press Enter
· The key information should be entered as:
[6 empty] | Key value 1B 0B 31 66 50 17 67 30 45 8A 92 EB 52 79 FA 81 02 88 A7 0C 38 ED C1 D3 EA EC 6F BE 18 1D | Code can not be displayed
Position 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30
PSAudit and PSSecure
· Sign on as QSECOFR.
· Addlible PSCOMMON
· PSMENU
· Take option 80 Enter Access Codes
· Enter below PERM Keys Provided by Tony from Micro Foucs
[6 empty] | DSEVA FSEVS GSEVD 80B7C 37DS5 VVCVA | Code can not be displayed
[6 empty] | PATRICK TOWNSEND | Code says Valid
· ADDLIBLE ALLFTM100
· GO AMMAIN
· Take Option 1 : Installation
· Take Option 2: Enter FTP Manager perm code AND Take Option 4: Enter PGP Option perm code
· Cut Paste keys as follows for appropriate menu option and lpar, Press Enter to save the keys.
[6 empty] | FTP Manager Code: E66B452D868A2C1A41FF7C6A9D4490F6 | Code displayed
[6 empty] | PGP Option Code: 936BE9E909DB3E385EE1DDE6448A0418 | Code displayed
PGP C9 Keys
[6 empty] | Download the PGP C9 Files from email sent by Kris for all 3 lpars on 2020/10/13 for (BUSDEP TSPGP_License - 7887C00.003.txt) |  | Upload this PGP license file to BUSDEP in /PGM IFS folder
FTP the file to the /PGP on the IFS from C: drive location where PGP C9 file is downloaded.
Start-> Run->FTP LPARNAME of IP
[6 empty] | USERID (your user ID) |  | BUSDEP key file should look as below
[6 empty] | Password (your password) |  | Browse : /pgp/TSPGP_License.txt
[6 empty] | BINARY |  | Record : 1 of 2 by 18 Column : 1 132 by 131
[6 empty] | cd /PGP |  | Control :
lcd c:\
[6 empty] | put TSPGP_License.txt |  | ....+....1....+....2....+....3....+....4....+....5....+....6....+....7....+....8....+....9....+....0....+....1....+....2....+....3.
[6 empty] | quit |  | ************Beginning of data**************
[6 empty] | · Go to the main menu: |  | Ryv4RnqbbvO4wwSYBpYyFib5RC3DIYZ9vp8dBFg6yQIQfJ4+UP13eB+fyi0r46LHUNUl0Pqu2x5WA/K+gKYf5anNxfZ3xZpizPCAJQWrZlJdDfQ7mx5vd3f7JVtxpnKHUNUl
[6 empty] | · ADDLIBLE ALLFTM100 |  | 0Pqu2x5WA/K+gKYf5fJwjCJtk8x+birHw/yciPg47G/9mGRZG10dGPiqvc6ux9n+MDGeH2xraw3dfpY5Sigw0oIi4pdD9+Ha1a3qVlQ=
[6 empty] | · GO AMMAIN |  | ************End of Data********************
· Option 1 for installation
· Option 12 to install PGP Command line 9 license
· Make the following changes:
PGP License File: /pgp/TSPGP_License.txt
(If you receive an error message when trying to install the license, try pressing F10 after the license file.)
Customer Name: See Below
Email: See Below
(Please reference the above screenshot to verify the customer name and email. This is case-sensitive and must be entered exactly as in the screenshot.)
Press Enter
[5 empty] | BUSDEP | Check that BUSDEP has the matching HOST Table Entries as BUSDEPHA. MIDRANGE to replicate QUSRSYS/QATOCHOST. |  | MIDRANGE
[5 empty] | BUSDEP | Check that BUSDEP has the matching WRKDIRE entries as BUSDEPHA
[5 empty] | BUSDEPHA | Capture all ROBOT Scheduler jobs list using ROBOT GUI as follows
Click on RBT Scheduler 13 GUI Icon on desktop
From the top menu, click on Job Schedule List (Icon in Red color just above the name column )
Right click on one of job displayed
From the Drop menu, select Select All to highlight all jobs in Yelllow color
Right Click again on highlighted job and select Copy to Clipboard
Select Yes for Include the Header screen pop up
All records will be copied to Clipboard and ready to be pasted in Excel
Paste all records in this excel at the bottom
(See the list at bottom on this Excel)
[5 empty] | BUSDEPHA | Run a query SECMANISH/RBTOVRRIDE to to create an output file called RBTOVRRIDE |  | This lis contains all jobs that do not have any override code and will be used to put the job status from HOLD to RELEASE in tab P1 BUSDEPHA GO LIVE
(See the tab ROBOT job with no override )
[5 empty] | BUSDEPHA | Capture all Patrick Townsend Active Jobs listing running these SQL statements |  | This list contains only ACTIVE PT Records
|  |  |  | 1 | FTP Definitions | SELECT * FROM allftm100/anftpd WHERE fdstat='1' ORDER BY fdname
|  |  |  | 2 | Scan DIR | SELECT DRNAME, DRDESC, DRSTAT FROM allftm100/anDIRS WHERE drstat='1' ORDER BY drname
|  |  |  | 3 | Auto Scan | SELECT * FROM allftm100/anscan WHERE scstat='1' ORDER BY scname
[6 empty] | Update SEMANISH/QSQLSRC(DRUPDPTSTS) member with only active PT records using this list created. |  | This SECMANISH/QSQLSRC(DRUPDPTSTS) meber contains SQL statements that will be run using SECMANISH/QCLSRC(DRUPDPTSTS) in P3 BUSDEP GO LIVE tab
[6 empty] | (See the list at bottom of this Excel) |  | This cl is replicated to BUSDEP so it will run on BUSDEP in P3 BUSDEP GO LIVE to activate records in PT
[5 empty] | BUSDEPHA | Capture all IBM WRKJOBSCDE Entries that on SCD
[5 empty] | BUSDEPHA | On BUSDEPHA, Run a query SECMANISH/SUNJOBS using WRKQRY to create a SECMANISH/SUNJOBS file to list all Sunday jobs
Download SUNJOBS file in SUNJOB_LATEST tab and sort by Sched_Run_time_1
Copy 4am to 10AM jobs from SUNJOB_LATEST tab to tab Vlookup ( in Red )
Copy 4am to 10AM jobs from ALL SUNDAY JOBS NEW to tab vlookup ( in Blue)
Find the new added jobs using vlookup in green, =N/A jobs in Vlookup tab here ( in Green )
Copy these new jobs from SUNJOB_LATEST to ALL_SUNDAY JOBS NEW to proper row loacation ( in Red )
Decide on action to take on new added jobs via DO or Skip, talk to Nasser and Stanley for action
Copy these final list of 4 am to 10am jobs with action column to DOJOBS UPLOAD
Upload DOJOBS UPLOAD to BUSDEP in DOJOBS file
These MISSED jobs to be run ON HA after switch since they were mised on BUSDEP between 4am to 10 AM while switching the role.
CL to run is SECMANISH/DRDOJOBS in tab P3 BUSDEP Go LIVE
BUSDEP Robot Scheduler Jobs List before Switch ( Original State ) |  |  |  |  | As of July 14 2023
Type | Name | Override(SCHOVR) | Reactive | Schedule Code | Attributes | Description | Time | M T W TH F ST SN | Application | Group Name
Group | @BU_RLS | HOLD | REACT |  |  | Error Recovery | 0:00 | Y Y Y Y Y . . | BACKUP | @BU_RLS
Command | @CLR_IFSPT | HOLD |  |  |  | H*Clear IFS Transfer Fldr | 0:00 | . . . . . . . | BD-APPLICA
Command | @SALESTEMP | HOLD |  |  |  | Sales Posting-On Demand | 0:00 | . . . . . . . | APPLN
Group | @SALESWDAY |  | REACT |  |  | Sales Process WeekDay | 0:00 | Y Y Y Y Y . . | SALESAUDIT | @SALESWDA1
Group | @SALESWEND |  | REACT |  |  | Sales Process WeekEnd | 0:00 | . . . . . Y Y | SALESAUDIT | @SALESWEND
Command | AGILENCETL | HOLD |  |  |  | **On Demand Agilence TLOG | 0:00 | . . . . . . . | BUSDEP
Command | AIRM_WEEK | HOLD | REACT |  |  | H*Send Wkly Feed AIRMILES | 0:00 | Y . . . . . .
Command | ARRECYCLE |  |  |  |  | Recycle Active Reasoning | 0:00 | . . . . . . .
Command | CKPURGE |  | REACT |  |  | Check Resource RBPURGE_DH | 0:00 | . . . . . . . | RBC
Command | CPC_PRC_OD | HOLD |  |  |  | On Demand-Clone CPC_PRICE | 0:00 | . . . . . . . | BD-APPLICA
Command | DAILY_BU | HOLD |  |  | GroupMember | H*Daily backup STRBKUBRM | 0:00 | . Y Y Y Y . . | BACKUP
Command | DRSHUTDOWN | HOLD |  |  |  | H*BUSDEP SHUTDOWN FOR DR | 0:00 | . . . . . . .
Command | DRSTARTSYS | HOLD |  |  |  | H*BUSDEP START UP FOR DR | 0:00 | . . . . . . .
Command | EM_EP_AUD |  |  |  |  | Eml Qtrly Emg Prf Requstr | 0:00 | . . . . . . . | BDAPPS
Command | EXTSLSB1OD | HOLD |  |  |  | H*BLD Ext Sls-1 On Demand | 0:00 | . . . . . . . | BDAPPS
Command | E3_EXTRACT | HOLD |  |  |  | On Demand-Ext E3 SLS Data | 0:00 | . . . . . . . | LEARN
Command | F_GXONDEMD |  |  |  |  | H*FTP Google On Demand | 0:00 | . . . . . . . | BD_APP
Command | F100906001 | [5 empty] | 0:00 | . . . . . . .
Command | F100906001 | [5 empty] | 0:00 | . . . . . . .
Command | HBT_DWNDOD | HOLD |  |  |  | H*FTP HBT-On Demand/Hold | 0:00 | . . . . . . . | HBT_DWND
Command | HJQ_OLORD1 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #1 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD2 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #2 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD3 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #3 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD4 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #4 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD5 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #5 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD6 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #6 | 0:00 | . . . . . . . | BD_APP
Command | HJQ_OLORD7 | HOLD |  |  |  | H*Hold OnlineOrd JobQ #7 | 0:00 | . . . . . . . | BD_APP
Command | HLDSDI_JB1 |  |  |  | GroupMember | Hold QBSDI_JB1 job queue | 0:00 | . . . . . . . | SDI
Command | HLDSDI_UPL |  |  |  | GroupMember | Hold QBSDI_UPL job queue | 0:00 | . . . . . . . | SDI
Command | JDA |  | REACT |  |  | Unrestrict JDA | 0:00 | . . . . . . Y
Command | MPOS0330RS | HOLD |  |  |  | H*Rsnd Full PLU-MPOS-330 | 0:00 | . . . . . . . | BDAPPLN
Command | OF_EML_RC |  | REACT |  |  | Outstndng Reconcil Vari | 0:00 | . . . . . . . | BUSDEP
Command | PCU000MP | HOLD | REACT |  |  | Profile Cleanup Utility. | 0:00 | . . . . . . . | IT
Command | PLNSLS_NEW | HOLD |  |  |  | H*FTP WK SL New-On Demand | 0:00 | . . . . . . . | BDAPPS
Command | PRODMODP |  | REACT |  |  | Daily Monday Backup | 0:00 | Y . . . . . . | BRMS
Command | PRODSOX2DP |  | REACT |  |  | PRODSOX to RPT2WEB | 0:00 | Y Y Y Y Y Y Y | 400 ANALST
Command | PRODSUDP |  |  |  |  | Daily Sunday Backup | 0:00 | . . . . . . Y | BRMS
Command | PURGE_DHD | HOLD | REACT |  |  | H*Purge DHD Delivery Ord | 0:00 | . . . . . . . | TRANSFER
Command | RBL_LNDCT2 |  | REACT |  |  | Rebuild Store Landed Cost | 0:00 | . . . . . . Y
Command | RBTBLDFCT |  |  |  |  | Forecast build | 0:00 | . . . . . . .
Command | RBT34501 |  |  |  |  | Work Schedule by Time Sch | 0:00 | . . . . . . . | ROBOT
Command | RBT34502 |  |  |  |  | Weekly Work Schedule by C | 0:00 | . . . . . . . | ROBOT
Command | RBT34701 |  |  |  |  | Report Distribution by Da | 0:00 | . . . . . . . | ROBOT
Command | RBT34702 |  |  |  |  | Report Distribution by Re | 0:00 | . . . . . . . | ROBOT
Command | REP00006 | [5 empty] | 0:00 | . . . . . . . | REP
Command | REP29701No |  |  |  |  | Report Archive Status rep | 0:00 | . . . . . . . | REP
Command | RJQ_OLORD1 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #1 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD2 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #2 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD3 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #3 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD4 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #4 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD5 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #5 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD6 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #6 | 0:00 | . . . . . . . | BD_APP
Command | RJQ_OLORD7 | HOLD |  |  |  | H*Rls OnlineOrd JobQ #7 | 0:00 | . . . . . . . | BD_APP
Command | RLSSDI_JB1 |  |  |  | GroupMember | Release QBSDI_JB1 jobq | 0:00 | . . . . . . . | SDI
Command | RLSSDI_UPL |  |  |  | GroupMember | Release QBSDI_UPL jobq | 0:00 | . . . . . . . | SDI
Command | RPL_SUGQTY | HOLD | REACT |  |  | CALCULATION OF ORDER QTY. | 0:00 | . . . . . . Y | LEARN
Command | R000000022 |  |  |  |  | Check Resource RBHBT_DWND | 0:00 | . . . . . . . | RBC
Command | R000000029 |  |  |  |  | Check Resource BRMSSBS | 0:00 | . . . . . . . | BUSDEP
Command | R000000042 |  |  |  |  | Check Resource QINTER | 0:00 | . . . . . . . | BUSDEP
Command | R000000158 |  |  |  |  | Check Resource BRMSJOBQ | 0:00 | . . . . . . . | BUSDEP
Command | R000000233 |  |  |  |  | Check Resource SCAN_DIRS | 0:00 | . . . . . . . | TOWNSEND
Program | SDI860CL |  |  |  | GroupMember | Set PNDSALFIL *dtaara | 0:00 | . . . . . . . | SALESAUDIT
Program | SDI865CL |  |  |  | GroupMember | Submit SALESsssss jobs | 0:00 | . . . . . . . | SALESAUDIT
Command | SUNDAY2 | HOLD | REACT |  |  | Post Sync-Point Jobs +HBT | 0:00 | . . . . . . Y
Command | SYSAUDALOB | HOLD |  |  |  | ALLOBJ user audit report | 0:00 | . . . . . . .
Command | SYSBKUREST | HOLD |  |  |  | Restrict system no bkup | 0:00 | . . . . . . .
Command | SYSBKU2 |  |  |  |  | Bring system up | 0:00 | . . . . . . .
Command | SYSBKU2YE | HOLD |  |  |  | H*Bring system up | 0:00 | . . . . . . .
Command | SYSCCCAUTH | HOLD |  | EVERY |  | Run Agent resetauth.sh | 0:00 | Y Y Y Y Y Y Y
Command | SYSCHKCTL |  |  |  | GroupMember | Check Controllers | 0:00 | . . . . . . . | BUSDEP
Command | SYSCHKJOB |  |  |  | GroupMember | Check Critial Jobs | 0:00 | . . . . . . . | BUSDEP
Command | SYSCHKJOBQ |  |  |  | GroupMember | Check Resource JOBQ | 0:00 | . . . . . . . | BUSDEP
Command | SYSCHKLIN |  |  |  | GroupMember | Check Com Lines | 0:00 | . . . . . . . | BUSDEP
Command | SYSCHKSBS |  |  |  | GroupMember | Check Subsystems | 0:00 | . . . . . . . | BUSDEP
Command | SYSE3LIBS | HOLD |  |  |  | E3 libraries save | 0:00 | . . . . . . . | BRMS
Command | SYSFLTREC | HOLD |  |  |  | Collect BRMS flight recs | 0:00 | . . . . . . .
Command | SYSJOBTST |  |  |  |  | test | 0:00 | . . . . . . .
Command | SYSMAFSBMM |  | REACT |  |  | Submit Final monthly jobs | 0:00 | . . . . . . Y
Command | SYSMAFSBMW |  | REACT |  |  | Submit Final weekly jobs | 0:00 | . . . . . . Y
Command | SYSNETIQPR |  | REACT |  |  | NetIQ Purge Deleted Prfs | 0:00 | . . . . . . .
Command | SYSODBCPRG |  | REACT |  |  | ODBC Log Purge > 2 Years | 0:00 | . . . . . . .
Command | SYSODBCRST |  | REACT |  |  | ODBC 90 Day Reset | 0:00 | . . . . . . .
Command | SYSOPSMAIL | HOLD | REACT |  |  | EMAIL GOC after WKend Prc | 0:00 | . . . . . . Y
Command | SYSPRFDIS |  | REACT |  |  | Profile Disable Utility. | 0:00 | . . . . . . . | IT
Command | SYSPT_APY | HOLD |  |  |  | PTownsend Apply PTFs | 0:00 | . . . . . . .
Command | SYSSTRSBS | OMIT | REACT |  |  | Start System Sunday | 0:00 | . . . . . . Y
Command | SYSSTRSBS2 |  | REACT |  |  | Start System Mon-Fri | 0:00 | . . . . . . .
Command | SYSSWPLOAD | HOLD |  |  |  | Load Post Role Swap Tasks | 0:00 | . . . . . . .
Command | TSG200YP | HOLD |  |  |  | H*Switch Fiscal Calendar | 0:00 | . . . . . . . | SCHEDULING
Command | VRM_WKND | HOLD | REACT |  |  | VRM Weekend run | 0:00 | . . . . . . Y
Command | HBT_CUS#WP |  |  |  |  | *Purge/Create TXECCT WKN | 0:01 | . . . . . Y Y
Command | HBT_DWND_M |  |  |  |  | *FTP HBT-DLY if FTP:Mon | 0:01 | Y . . . . . . | HBT_DWND
Command | ZAACL85 |  |  |  |  | Subsys gen info | 0:01 | Y . . . . . . | PSAUDIT
Command | CKHBTDWN_M |  |  |  |  | Check Resource RBHBT_DWND | 0:02 | Y . . . . . . | RBC
Command | CKDLYSAL |  |  |  |  | Check Resource DLY_SALRPT | 0:05 | Y Y Y Y Y Y . | RBC
Command | DAYCLOSE |  |  |  |  | Day Close | 0:05 | Y Y Y Y Y Y . | DAILY
Command | LCT_UPL1 |  |  |  |  | Upload Labor Cost Xfer | 0:05 | Y . . . . . . | BD APPLN
Command | PERFNAVDR | HOLD |  |  |  | Data Reduction | 0:05 | Y Y Y Y Y Y Y | TECSUPPORT
Command | SYSJOBTBL |  |  |  |  | Check job table size | 0:05 | Y Y Y Y Y Y Y
Command | ZAACL28JD |  |  |  |  | Chgs to USER of a JOBD | 0:05 | Y . . . . . . | PSAUDIT
Command | ZAACL7701 |  |  |  |  | System Values | 0:05 | . . . . . . Y | PSAUDIT
Command | ZAACL7702 |  |  |  |  | Pgms that Adopt QSECOFR | 0:05 | . . . . L . . | PSAUDIT
Command | CH_MSGMON1 |  |  | EVERY |  | Check Job has MSGW-MON-#1 | 0:00 | Y . . . . . . | BD_APP
Command | CKDAYCLO |  |  |  |  | Check Resource RBDAYCLOSE | 0:06 | Y Y Y Y Y Y . | DAYCLOSE
Command | RSOSLOGI |  |  |  |  | Remove Mbr for SOSLOGI | 0:10 | . . . . . Y . | BDAPPLICAT
Command | RSOSLOGO |  |  |  |  | Remove Mbr for SOSLOGO | 0:10 | . . . . . Y . | BDAPPLICAT
Command | ZAACL28SM |  |  |  |  | System Management Changes | 0:10 | Y . . . . . . | PSAUDIT
Command | ZAACL7703 |  |  |  |  | Network Attributes | 0:10 | . . . . . . Y | PSAUDIT
Command | ZAACL98 |  |  |  |  | Pgms adopt QSEC like auth | 0:10 | . . . . L . . | PSAUDIT
Command | HBT_DWND_D |  |  |  |  | *FTP HBT-DLY if FTP:Tu-Sa | 0:15 | . Y Y Y Y Y . | HBT_DWND
Command | ZAACL28VV |  |  |  |  | Service Status Changes | 0:15 | Y . . . . . . | PSAUDIT
Command | ZAACL7715 |  |  |  |  | Local Hardware | 0:15 | . . . . . . Y | PSAUDIT
Command | CKHBTDWN |  |  |  |  | Check Resource RBHBT_DWND | 0:16 | . Y Y Y Y Y . | RBC
Command | ZAACL7709 |  |  |  |  | Output Queue Descriptions | 0:20 | . . . . . . Y | PSAUDIT
Command | ZAACL93 |  |  |  |  | Network job entries | 0:25 | . . . . . . Y | PSAUDIT
Command | CKUPDINV |  |  | EVERY |  | Check Resource UPD_INVLBL | 0:00 | Y Y Y Y Y Y . | RBC
Group | @BU_MON | HOLD |  |  |  | Backup (Mon) | 0:30 | Y . . . . . . | BACKUP | @BU_MON
Command | HBT_CLNW |  |  |  |  | Cleanup issued tax cust. | 0:30 | Y . . . . . . | HBT
Command | PERFNAVDR | HOLD |  |  |  | Perf Nav Data Reduction | 0:30 | Y Y Y Y Y Y Y | MPG
Command | ZAACL88 |  |  |  |  | Dist direct entries | 0:30 | . . . . . . Y | PSAUDIT
Command | ZAACL28PS |  |  |  |  | Profile Swap | 0:40 | . . . . L . . | PSAUDIT
Command | ZAACL28VL |  |  |  |  | Account Limits Exceeded | 0:45 | . . . . L . . | PSAUDIT
Command | SYSBKUP |  |  |  |  | Reg Weekly Shutdown IPL | 0:50 | . . . . . Y .
Command | SYSBKUPPE |  |  |  |  | Period End Shutdown IPL | 0:50 | . . . . . Y .
Command | SYSBKUPQE |  |  |  |  | Quarter End Shutdown IPL | 0:50 | . . . . . Y .
Command | SYSBKUPYE | HOLD |  |  |  | H*Year End Shutdown IPL | 0:50 | . . . . . Y .
Command | ZAACL28OR |  |  |  |  | Object Restore | 0:50 | Y . . . . . . | PSAUDIT
Command | CH_MSGSAT1 |  |  | EVERY |  | Check Job has MSGW-SAT-#1 | 0:00 | . . . . . Y . | BD_APP
Command | ZAACL74 |  |  |  |  | Grp Prfs w/any Spec Auth | 0:55 | . . . . L . . | PSAUDIT
Command | BUSDEP | HOLD |  |  |  | H*DasdPlus Survey | 1:00 | Y . . . . . . | LEARN
Command | HBT_CUS#DP |  |  |  |  | *Purge/Create TXECCT WDAY | 1:00 | Y Y Y Y Y . .
Command | PERFNAVPM | HOLD |  |  |  | Perf Nav Monitor | 1:00 | Y Y Y Y Y Y Y | MPG
Command | SYSILMTSSC |  |  |  |  | ILMT Software Scan | 1:00 | Y Y Y Y Y Y Y
Command | SYSTHRWKLY | HOLD |  |  |  | Weekly threaded save | 1:00 | . . . . . Y .
Command | ZAACL7718 |  |  |  |  | User Profile = Password | 1:00 | . . . . L . . | PSAUDIT
Command | ZAACL80UA |  |  |  |  | Group Profiles | 1:05 | . . . . L . . | PSAUDIT
Command | ZAACL80UB |  |  |  |  | Prf Parm Analysis | 1:10 | . . . . L . . | PSAUDIT
Command | ZAACL80UC |  |  |  |  | Prf Password Exp not 0 | 1:15 | . . . . L . . | PSAUDIT
Command | ZAACL80U3 |  |  |  |  | Prfs without Limited Cap | 1:20 | . . . . L . . | PSAUDIT
Command | ZAACL80U4 |  |  |  |  | Prfs SECADM SECOFR ALLOBJ | 1:25 | . . . . L . . | PSAUDIT
Command | CH_MSGSUN1 |  |  | EVERY |  | Check Job has MSGW-SUN-#1 | 0:00 | . . . . . . Y | BD_APP
Command | ZAACL82 |  |  |  |  | Attn key pgms adopt auth | 1:30 | . . . . L . . | PSAUDIT
Command | ZAACL84 |  |  |  |  | Prfs attn key pgms | 1:35 | . . . . L . . | PSAUDIT
Command | ZAA3010C |  |  |  |  | Profile Integrity | 1:40 | . . . . L . . | PSAUDIT
Command | HLD_DCJOBQ |  |  |  |  | Hold DCDIRECT JOBQ | 1:55 | Y Y Y Y Y . . | BDAPPLN
Command | SYSCHGTIME | HOLD |  |  |  | DST TIME CHANGE -1 HR | 1:55 | . . . . . . Y
Command | REORGFILE |  |  |  |  | REORGANIZE FILES | 2:00 | . Y . . . . . | LEARN
Command | SYSUSRPRF2 |  |  |  |  | DSPUSRPRF to ITTOOLS | 2:00 | Y Y Y Y Y Y Y
Command | ZAACL28CP2 |  |  |  |  | Action To User Prfs | 2:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL28DS |  |  |  |  | DST Password Reset | 2:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL28PA |  |  |  |  | Pgms Chgd Adopt Owner Aut | 2:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL28SV |  |  |  |  | Changes To System Values | 2:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL33AL |  |  |  |  | Cmds For Limited Users | 2:00 | . . . . L . . | PSAUDIT
Command | PERFNAVPG | HOLD |  | DAYNO |  | Reduced Data Purge | 2:30 | 1 | TECSUPPORT
Command | PERFNAVPG | HOLD |  |  |  | PN Reduced Data Purge | 2:30 | . . . . . 1 . | MPG
Command | RSOSLOGIWE |  |  |  |  | Remove Mbr for SOSLOGI-WE | 2:40 | . . Y . . . . | BDAPPLICAT
Command | RSOSLOGOWE |  |  |  |  | Remove Mbr for SOSLOGO-WE | 2:40 | . . Y . . . . | BDAPPLICAT
Command | DCA1_SLSD2 |  |  | EVERY |  | CA Sales Fri<2:41*10 min | 0:00 | . . . . Y . .
Command | ENDQPGMR |  |  |  |  | ENDQPGMR | 2:50 | . Y Y Y Y . . | LEARN
Command | BPS_OK_NO1 |  |  | EVERY |  | OTH-Refresh BPS Alloc Qty | 0:00 | . Y Y Y Y . .
Command | CH_MSGT2F1 |  |  | EVERY |  | Check Job has MSGW-T2F-#1 | 0:00 | . Y Y Y Y . . | BD_APP
Group | @BU_WDAY | HOLD |  |  |  | Backup (Tue/Wed/Thu/Fri) | 3:00 | . Y Y Y Y . . | BACKUP | @BU_WDAY
Command | DCA_PURGE |  |  |  |  | Wkly Purge DCAINVTRN Mbr | 3:00 | Y . . . . . .
Command | PRODDP |  |  |  |  | Daily Tue-Fri Backup | 3:00 | . Y Y Y Y . . | BRMS
Command | SYSSTPBASE | HOLD |  |  |  | Dasd plus Baseline Survey | 3:00 | . . . . . 1 .
Command | PERFNAVDS | HOLD |  |  |  | Lib and Obj Sizes | 3:30 | . . . . . . Y | TECSUPPORT
Command | PERFNAVDS | HOLD |  |  |  | PN Lib and obj sizes | 3:30 | . . . . . . Y | MPG
Command | RLS_DCJOBQ |  |  |  |  | Release DCDIRECT JOBQ | 3:30 | Y Y Y Y Y . . | BDAPPLN
Command | EXTSL_R1 | HOLD |  |  |  | H*Eml Ext SLS Rpt-R1 | 3:45 | Y . . . . . . | BDAPP
Command | RBL_LNDCT1 |  |  |  |  | Rebuild Store Landed Cost | 3:59 | Y Y Y Y Y Y .
Command | BPS831CL |  |  |  |  | *Operational Excellence | 4:00 | Y Y Y Y Y Y Y | REPORTING
Command | WK_DST_MON |  |  |  |  | WKLY DISTRICT RESULTS-MON | 4:00 | Y . . . . . . | LEARN
Command | WK_RDBFEED | HOLD |  |  |  | H*DashBoard Weekly | 4:00 | Y . . . . . . | BUSDEP
Command | CATMANGETD |  |  |  |  | Dly-Get CATMAN Files | 4:05 | Y Y Y Y Y . Y
Command | CATMANLSTD |  |  |  |  | Dly-Get CATMAN File LST | 4:05 | Y Y Y Y Y . Y
Command | E3_BD_ZAP |  |  |  |  | E3 Weekly Report | 4:05 | Y . . . . . . | LEARN
Command | MOOSEAGGR1 |  |  |  |  | MOOSE AGGREGATE UPDATE | 4:10 | Y Y Y Y Y . . | LEARN
Command | MOOSEAGGR2 |  |  |  |  | *MOOSE AGGREGATE UPD WKN | 4:10 | . . . . . Y Y | LEARN
Command | E3_RPLEN |  |  |  |  | *E3 Repln*Before E3_Frz | 4:13 | Y Y Y Y Y Y Y | APPLN
Command | EXTSL_R2 |  |  |  |  | Eml Ext. SLS Rpt-Reg02 | 4:15 | Y . . . . . . | BDAPP
Command | EXTSL_R5 |  |  |  |  | Eml Ext. SLS Rpt-Reg05 | 4:15 | Y . . . . . . | BDAPP
Command | E3_FREEZE |  |  |  |  | *E3 DAY-END PROCESS | 4:15 | Y Y Y Y Y Y Y | LEARN
Command | ACK_EDI |  |  |  |  | EDI Acknowledgment Update | 4:30 | Y Y Y Y Y Y .
Command | E3_DAYEND |  |  |  |  | *E3 DAY-END PROCESS | 4:30 | Y Y Y Y Y Y Y | LEARN
Command | MONINVBL3A | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 4:30 | . Y Y Y Y . . | BD APPLN
Command | POS_PURGE |  |  |  |  | O*Purge Old Sales Data | 4:30 | Y Y Y Y Y Y Y | BD-APP
Command | PURG_RPL |  |  |  |  | Purge Mult Mbr-Sys:RPL | 4:30 | Y . . . . . . | BDAPP
Command | PURGE_WSID |  |  |  |  | Purge Virtual WS ID QPAD* | 4:30 | Y Y Y Y Y . . | BD APP SUP
Command | RBA90501 |  |  |  |  | Transmission Log Delete | 4:30 | Y . . . . . . | ALERT
Command | RBA90601 |  |  |  |  | Message History Delete | 4:30 | Y . . . . . . | ALERT
Command | RBC000WP |  |  |  |  | Robot Console Hist Purge | 4:30 | . . . . . Y .
Command | INVBAX_API | HOLD |  | EVERY |  | H*API Call to upd invbax | 0:00 | Y Y Y Y Y Y Y
Command | F_BUSPLN |  |  |  |  | Business Plan Data Feed | 5:00 | . . . Y . . . | BD-APPS
Command | GM_WK_RPT |  |  |  |  | Auto GM Weekly Report-Mon | 5:00 | Y . . . . . . | BDAPPLN
Command | NONSALE_UP |  |  |  |  | Update the Status of | 5:00 | Y Y Y Y Y Y Y | BUSDEP
Command | PERFNAVIFS | HOLD |  |  |  | IFS Size Collection | 5:00 | . . . . . . Y | TECSUPPORT
Command | PERFNAVIFS | HOLD |  |  |  | Perf Nav IFS size coll | 5:00 | . . . . . . Y | MPG
Command | PLNMST | HOLD |  |  |  | H*FTP Pln Master Tables | 5:00 | Y Y . Y Y . . | BDAPPS
Command | PLNMST_SLS | HOLD |  |  |  | H*FTP WKly Mstr/SLS to DB | 5:00 | . . Y . . . . | BDAPPS
Command | SAARMNT |  |  | DAYNO |  | Bank Reconciliation | 5:00 | 1 | BDA
Command | SABNKMNT |  |  | DAYNO |  | Bank Reconciliation | 5:00 | 1 | BDA
Command | SAI_INRT |  |  |  |  | Weekly RT Feed From Alpha | 5:00 | . . . . . Y . | BDAPPLICAT
Command | UPDVEND# |  |  |  |  | Refresh Vendr-UPC/BCD/RTN | 5:00 | Y Y Y Y Y . . | BDAPP
Command | ZAACL28NA |  |  |  |  | Chgs To Net Attributes | 5:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL28SE |  |  |  |  | Subsystem Routing Changes | 5:00 | Y Y Y Y Y Y . | PSAUDIT
Command | ZAACL28ST |  |  |  |  | Use of Service Tools | 5:00 | Y Y Y Y Y Y . | PSAUDIT
Command | CATMANGETF |  |  |  |  | Fri-Get CATMAN Files | 5:05 | . . . . Y . .
Command | CATMANLSTF |  |  |  |  | Fri-Get CATMAN File LST | 5:05 | . . . . Y . .
Command | E3TWAIT |  |  |  |  | *E3 DAY-END PROCESS | 5:15 | Y Y Y Y Y Y Y | LEARN
Command | EVER_SKUFL |  |  |  |  | Set Ever Sku Flag | 5:20 | Y Y Y Y Y Y . | BDAPPS
Command | AGILENCEDP |  |  |  |  | Send Agilence LP File DLY | 5:30 | Y Y Y Y Y . . | BUSDEP
Command | CPS_DAILY |  |  |  |  | Extract Sales for C&P SO | 5:30 | Y Y Y Y Y Y Y | BD APPLN
Command | DCA3_DAILY |  |  |  |  | *CA Morning Setup *Once | 5:30 | Y Y Y Y Y Y Y
Command | MOO_SUM | HOLD |  |  |  | H*Build MOOSE Summary | 5:30 | Y . . . . . . | BDAPPS
Command | PLNVMST_UP |  |  |  |  | FTP Get POG/Sku,Str,Desc | 5:30 | . . . . Y . . | BDAPPS
Command | SUNIRF_DP |  |  |  |  | SUNRISE Inv Fresh Mon-Fri | 5:30 | Y Y Y Y Y . . | BDAPPLN
Command | SYSGENRBT | HOLD |  |  |  | re-gen robot message file | 5:30 | . . Y . . . Y
Command | SYSTELSSL | HOLD |  |  |  | Create DTAAREA for TELSSL | 5:30 | . . . Y . . .
Command | EM_PRC2OD | HOLD |  |  |  | H*Eml Prc Chg-FU-On Deman | 5:35 | . . . . . Y . | BUSDEP APP
Command | MPOS_330DP | HOLD |  |  |  | H*Send Full PLU-MPOS-330 | 5:40 | Y Y Y Y Y . . | BDAPPLN
Command | BPS_INVENT |  |  |  |  | Eml BPS Ord Activity Rpt | 5:45 | Y Y Y Y Y Y Y | BUSDEP
Command | CLR_IFSDP |  |  |  |  | Clear IFS tmp folder-DLY | 5:45 | Y Y Y Y Y . . | BD-APPLICA
Command | F_PDBRCLDP |  |  |  |  | *FTP RCL Fee-> Google WD | 5:45 | Y Y Y Y Y . . | BD_APP
Command | F_PDBVNDDP |  |  |  |  | *FTP Vend Master-> PDB WD | 5:45 | Y Y Y Y Y . . | BD_APP
Command | PCA_PURAS4 |  |  |  |  | *Clear AS400 Count Files | 5:45 | . . . Y . . . | BD-APPS
Command | POSLOG |  |  |  |  | Monitoring POS Polling | 5:45 | Y Y Y Y Y Y Y | POS
Command | PPR_OH_DP |  |  |  |  | PPR On Hand - rolling | 5:45 | Y Y Y Y Y Y . | BD-APP
Command | RLS_RVFAX |  |  |  |  | Release RVFax JOB Queue | 5:45 | . . . . . Y . | BDAPPLN
Command | SYSCHKSUN | HOLD |  |  |  | check sunrise | 5:45 | . . . . . . Y
Command | F_GXDLY2TB |  |  |  |  | *FTP Google Master TBL#2 | 5:50 | Y Y Y Y Y Y Y | BD_APP
Command | BLD_PRXFDP |  |  |  |  | Bld Program Ref-Daily | 5:55 | Y Y Y Y Y . . | BD APPLN
Command | FCHN_SKUDP | HOLD |  |  |  | H*CHN Sku Lst-Fil Rpt-Dly | 5:55 | Y Y Y Y Y . . | BD APPLN
Command | F_GXDLY1TB |  |  |  |  | *FTP Google Master TBL#1 | 5:58 | Y Y Y Y Y Y Y | BD_APP
Command | EMPMSTDP |  |  |  |  | Upl Empl Mstr SLSEMPWK-DP | 5:59 | Y Y Y Y Y . . | BD APPLN
Command | ADDINVRTN |  |  |  |  | Add Missing INVTRN Record | 6:00 | Y Y Y Y Y Y . | BDAPPLN
Command | BDDLOC_CPY |  |  |  |  | Backup BDDLOC => BDDLOCBK | 6:00 | Y Y Y Y Y Y . | BD_APPLN
Command | CBT_DAILY |  |  |  |  | *File feed transmission | 6:00 | Y Y Y Y Y Y Y | BD APPLN
Command | CLR_E3PROD |  |  |  |  | Clear E3PROD Outq | 6:00 | . Y . . . . . | LEARN
Command | CLR_IFSALL |  |  |  |  | O*Clear IFS see IFSLIST | 6:00 | Y Y Y Y Y Y Y | BDAPP
Command | DST_DAILY |  |  |  |  | DAILY DISTRICT STORE RES | 6:00 | Y Y Y Y Y . . | LEARN
Command | ETS_DAILY |  |  |  |  | ETS-WebErr & ESPtablesFTP | 6:00 | Y Y Y Y Y Y Y | BDAPPS
Command | F_SUPORD |  |  |  |  | FTP Supply Order->Ruscom | 6:00 | Y Y Y Y Y Y . | BDAPPS
Command | KRONOSDP |  |  |  |  | DYLY:Store Data->Kronos | 6:00 | Y Y Y Y Y . . | BDAPPLN
Command | MKB_REPORT | HOLD |  |  |  | H*Market Basket Report | 6:00 | Y Y Y Y Y Y Y | BUSDEP
Command | MONINVBL2A | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 6:00 | Y . . . . . . | BD APPLN
Command | MPOS_330WP | HOLD |  |  |  | H*Send Full PLU-MPOS-330 | 6:00 | . . . . . Y Y | BDAPPLN
Command | PLNPOS |  |  |  |  | Upload Sign Type/# Copies | 6:00 | . . . . Y . . | BD APP
Command | SAI_MAC |  |  |  |  | *SA Daily MAC Interface | 6:00 | Y Y Y Y Y Y Y | BD APP
Command | SE_DAILY |  |  |  |  | *Send Daily Feeds for SE | 6:00 | Y Y Y Y Y . Y | BUSDEP
Command | SE_WEEK |  |  |  |  | Send Weekly Feeds for SE | 6:00 | . . . . . Y . | BUSDEP
Command | SKUEXT2 |  |  |  |  | *Sku Master ext part 2 | 6:00 | Y Y Y Y Y Y Y | BD APPLN
Command | SOSIFSCLR | HOLD |  |  |  | H*Spec Order Payment Conf | 6:00 | Y Y Y Y Y . . | BUSDEP
Command | SYSAUDROBL |  |  | DAYNO |  | Robot Audit Reports | 6:00 | 1
Command | SYSBRMSLOG |  |  | DAYNO |  | Monthly Audit BRMS Log | 6:00 | 1
Command | SYSLOGFTP | HOLD |  |  |  | FTP Network Transactions | 6:00 | Y Y Y Y Y Y Y
Command | SYSODBCPNT |  |  |  |  | Check for ODBC Exit Prog | 6:00 | Y Y Y Y Y Y Y
Command | SYSRRMTRAN | HOLD |  |  |  | Capture all Network Trans | 6:00 | Y Y Y Y Y Y Y
Command | SYSSTORAUD | HOLD |  |  |  | Audit store 3 & 256 | 6:00 | . Y Y Y Y Y .
Command | UP_GCCOM |  |  |  |  | Refresh Gift Card Com% | 6:00 | Y Y Y Y Y Y Y | BDAPP
Command | CKCLEAR |  |  |  |  | Check Resource RBCLEAR_IF | 6:01 | Y Y Y Y Y . . | RBC
Command | CATMANGETS |  |  |  |  | Sat-Get CATMAN Files | 6:05 | . . . . . Y .
Command | CATMANLSTS |  |  |  |  | Sat-Get CATMAN File LST | 6:05 | . . . . . Y .
Command | AGILENCEWP |  |  |  |  | *Send Agilence LP File WN | 6:15 | . . . . . Y Y | BUSDEP
Command | AUTO_FTP |  |  |  |  | *Resend Missed POS Price | 6:25 | Y Y Y Y Y Y Y | SDI
Command | ECP1_DAILY | HOLD |  |  |  | H*Easy Care Plan Create | 6:25 | Y Y Y Y Y Y .
Command | EM_PRC1OD | HOLD |  |  |  | H*Eml Prc Chg-IR-On Demnd | 6:25 | . . . . . Y . | BUSDEP APP
Command | CLD_TXNPCK | HOLD |  |  |  | H*StoragePipe Ord Trigger | 6:30 | Y Y Y Y Y Y Y | BDAPPLN
Command | CLR_IFSWP |  |  |  |  | O*Clear IFS TMP Fldr-WN | 6:30 | . . . . . Y Y | BD-APPLICA
Command | CXDAILY |  |  |  |  | Daily SLS CMIS-Weekday | 6:30 | Y Y Y Y Y . . | CMIS
Command | CXTBLBDG |  |  |  |  | *Giftcard Reversal TBLMDG | 6:30 | Y Y Y Y Y Y Y | CMIS
Command | ECP_WEEKLY | HOLD |  |  |  | H*ESP Mnth Cont-Hld/Activ | 6:30 | Y . . . . . .
Command | EM_DSAD1 |  |  |  |  | *EMail Daily SLS All Str | 6:30 | Y Y Y Y Y . . | BD_APP
Command | ESPCLOSEWP | HOLD |  |  |  | Not Used-Force closed ESP | 6:30 | . Y . . . . . | BD-APPS
Command | F_DLYSLS |  |  |  |  | FTP Delivery Sls Summary | 6:30 | . Y . . . . . | BDAPPS
Command | INV824JQ |  |  |  |  | Shrink File Update | 6:30 | Y . . . . . . | INV
Command | MOOSE3_DP |  |  |  |  | Rebuild MOOSE3-Weekdays | 6:30 | Y Y Y Y Y . . | BD_APP
Command | PLNFACEX | HOLD |  |  |  | H*Pln Facing Exception | 6:30 | Y . . . . . . | BD-APPS
Command | PPA_DATE |  |  |  |  | Roll Prepaid Activation D | 6:30 | Y Y Y Y Y Y Y | SORDER
Command | PURG_DBFA | HOLD |  |  |  | H*Purge Data Base File | 6:30 | . L . . . . .
Command | QA_REFRESH |  |  |  |  | QA Lab Daily PLU Updates | 6:30 | Y Y Y Y Y Y Y | SDI899CL
Command | RBT650001 |  |  |  |  | Completion Message Listin | 6:30 | Y Y Y Y Y Y Y | ROBOT
Command | RBT651DP |  |  |  |  | Good Morning Report | 6:30 | Y Y Y Y Y Y Y | PROD. DEL.
Command | RBT651WP |  |  |  |  | Good Morning Report | 6:30 | Y . . . . . . | PROD. DEL.
Command | SACFSDLY |  |  |  |  | CFS Parsing | 6:30 | . Y Y Y Y Y . | BDA
Command | SKUCHKD |  |  |  |  | Recalculate Sku Check Dig | 6:30 | Y Y Y Y Y . . | BUSDEP
Command | SPI_WKLY | HOLD |  |  |  | H*SPI Weekly Update | 6:30 | Y . . . . . . | SPI
Command | SYSEXPPRF |  |  |  |  | Check for expired 365 prf | 6:30 | Y . . . . . .
Command | SYSJRNACT | HOLD |  |  |  | Log Journal Rcvr Activity | 6:30 | Y Y Y Y Y Y Y
Command | SYSODBCPRT |  |  |  |  | Monthly ODBC Access Repor | 6:30 | 1 . . . . . .
Command | SYSSSHCHK |  |  |  |  | AML SSH Config Check | 6:30 | Y Y Y Y Y Y Y
Command | TDSFEE | HOLD |  |  |  | H*TDS FEE Email Report | 6:30 | Y . . . . . . | BD APP SUP
Command | SSWINBND2 |  |  |  |  | *FTP/In Str Signage WHSE | 6:35 | Y Y Y Y Y Y . | BDAPPLN
Command | PURG_E3RPT |  |  |  |  | Purge E3 Report in IFS | 6:40 | . Y . . . . . | BD APP SUP
Command | PURGE_CD |  |  |  |  | Purge E3 Cross Dock Order | 6:40 | . Y . . . . . | BD APP SUP
Command | CKMONSWA |  |  |  |  | Check MONSWABRM for SLA | 6:45 | Y Y Y Y Y Y .
Command | CX_MST_DP |  |  |  |  | Daily CMIS Master Files | 6:45 | Y Y Y Y Y . . | CMIS
Command | EM_UIDCHDP |  |  |  |  | Eml User ID Chg Err -DLY | 6:45 | Y Y Y Y Y . . | BDAPPS
Command | F_PDBRCLWP |  |  |  |  | *FTP RCL Fee-> Google WN | 6:45 | . . . . . Y Y | BD_APP
Command | F_PDBVNDWP |  |  |  |  | *FTP Vend Master-> PDB WN | 6:45 | . . . . . Y Y | BD_APP
Command | MONINVBL3B | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 6:45 | . Y Y Y Y . . | BD APPLN
Command | PLNSLS_OLD | HOLD |  |  |  | H*Wkly/Mnthly Sls-OLD | 6:45 | . Y . . . . . | BDAPPS
Command | SSWOUTBND |  |  |  |  | FTP/Out Str Signage WHSE | 6:45 | Y Y Y Y Y Y . | BDAPPLN
Command | AS2RESETDP |  |  |  |  | *Reset AS2 Comm. Line | 6:55 | Y Y Y Y Y Y Y | 400 ANLYST
Command | CVM_CSAT | HOLD |  |  |  | H*Send/Receive CVM Data | 6:55 | Y Y Y Y Y Y Y | BD-APP
Command | ESPCUA | HOLD |  |  |  | H*Upld AS400 WebESP Cust | 6:55 | Y Y Y Y Y Y Y | BD APPS
Command | AIRM_DAILY | HOLD |  |  |  | H*Send Daily Feed AIRMILE | 7:00 | Y Y Y Y Y Y Y
Command | ALG_BAL_DP |  |  |  |  | Daily Algolia Invbal File | 7:00 | Y Y Y Y Y . . | CMIS
Command | CHKBAL_BLD |  |  |  |  | CHECK INVBAL REBUILD | 7:00 | . . . . . . Y
Command | CXSALES |  |  |  |  | Wkly SLS Totals to CMIS | 7:00 | Y . . . . . .
Command | DRPSHPVNDP | HOLD |  |  |  | H*Vendor File | 7:00 | Y Y Y Y Y . . | BD-APPS
Command | EBY_TRF_DP |  |  |  |  | Sends daily eBay transfer | 7:00 | Y Y Y Y Y . . | BD APP
Command | EM_DSTD1 |  |  |  |  | *EMail Daily SLS Transfrm | 7:00 | Y Y Y Y Y . . | BD_APP
Command | EMPMSTWP |  |  |  |  | *Upl Empl Mst SLSEMPWK-WP | 7:00 | . . . . . Y Y | BD APPLN
Command | F_XEROXDP |  |  |  |  | Send PO Rec RTV Info XRX | 7:00 | Y Y Y Y Y Y . | BDAPPS
Command | FCHN_SKUWP | HOLD |  |  |  | H*CHN Sku Lst-Fill Rpt-WN | 7:00 | . . . . . Y Y | BD APPLN
Command | PPR_OH_WP |  |  |  |  | PPR On Hand - rolling-SUN | 7:00 | . . . . . . Y | BD-APP
Command | SPIDRIVE | HOLD |  |  |  | H*SPI Prod Collection | 7:00 | . Y Y Y Y . . | SPI
Command | TSS_ORDPOP |  |  |  |  | Zuora Order Number Popula | 7:00 | Y Y Y Y Y Y Y
Command | UP_MEMCONT |  |  |  |  | *Upd Sku Memory Content | 7:00 | Y Y Y Y Y Y Y | BD_APP
Command | VFOEMLDP |  |  |  |  | Email Sell Through Offer | 7:00 | Y Y Y Y Y . . | BUSDEP APP
Command | HAMILTON |  |  |  |  | *CREATE CITICORP FILES | 7:15 | Y Y Y Y Y Y Y | LEARN
Command | PRTLABELOD | HOLD |  |  |  | H*Print Labels-On Demand | 7:25 | . . . . . Y . | SDI
Command | BLDINVTR |  |  |  |  | Build Inventory Turn file | 7:30 | . . . . . . .
Command | DESJARDINS |  |  |  |  | *Outbound Line Item Dtl | 7:30 | Y Y Y Y Y Y Y | BD APP
Command | DLYQWKN3AM | HOLD |  |  |  | H*Block 15 QWKNBCH3 Jobs | 7:30 | Y Y Y Y Y . . | BD_APP
Command | EM_PDNVFO |  |  |  |  | Eml Pending Sell Thr Rpt | 7:30 | Y Y Y Y Y Y Y | BD_APP
Command | EM_UIDCHWP |  |  |  |  | Eml User ID Chg Err -WKN | 7:30 | . . . . . Y Y | BDAPPS
Command | E3FCTVAR |  |  |  |  | E3 variance reports | 7:30 | Y . . . . . . | BD-APPS
Command | F_ORDSTSYD |  |  |  |  | Copy FC Order Sts Journal | 7:30 | Y Y Y Y Y Y Y | BD APPLN
Command | F_OS_POTRD |  |  |  |  | FTP Unrec PO Trf-BTS Wk D | 7:30 | Y Y Y Y Y . . | BDAPPS
Command | PURG_DBF |  |  |  |  | Purge Data Base File | 7:30 | . Y . . . . .
Command | REV_SKU |  |  |  |  | Flag Reversal Sku-INVSKU | 7:30 | Y Y Y Y Y . . | BDAPPS
Command | SAALPDLY |  |  |  |  | Alpha Parsing | 7:30 | . Y Y Y Y Y . | BDA
Command | SBMZAPJOBS |  |  |  |  | Submit purge jobs | 7:30 | . . Y . . . . | SYS
Command | SOINGRAM |  |  |  |  | Ingram Special Orders | 7:30 | Y Y Y Y Y . . | SORDER
Command | SYM_SLS |  |  |  |  | symantec sales file | 7:30 | . Y . . . . . | BD APPS
Command | SYSPSJRN |  |  | INDAY |  | Delete PSJRN Receivers | 7:30 | . . . . . . .
Command | VRM_INVOIC | HOLD |  |  |  | VRM Inv DO NOT take DO | 7:30 | Y . . . . . .
Command | CK_E3EOD2A |  |  |  |  | Check E3 EOD (M-F) ASR | 7:40 | Y Y Y Y Y . . | BDAPPLN
Command | EBY_SLPOST |  |  |  |  | eBay Sales Posting | 7:40 | Y Y Y Y Y . . | BDAPPS
Command | E3_PO_00 |  |  |  |  | ELECTRONIC PO TRANSFER | 7:45 | Y Y Y Y Y . . | LEARN
Command | MONINVBL2B | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 7:45 | Y . . . . . . | BD APPLN
Command | VRM_28RPTD |  |  |  |  | VRM C28 Report for Distr. | 7:45 | Y . . . . . .
Command | CK_E3EOD2W |  |  |  |  | Check E3 EOD (M-F) AWR | 7:55 | Y Y Y Y Y . . | BDAPPLN
Command | EDI_DAILY |  |  |  |  | EMAIL TO MERCH FOR PO'S | 7:55 | . Y . . Y . . | LEARN
Command | AOOS_WKLY |  |  |  |  | Weekly AOOS Email Reports | 8:00 | Y . . . . . . | IS4TC
Command | BPS_LABOUR |  |  |  |  | BOPIS CA Orders Report | 8:00 | Y . . . . . . | BUSDEP
Command | CRT_R40CTL | HOLD |  |  |  | H*Not Use-Run in CPCDaily | 8:00 | Y Y Y Y Y Y Y | BDAPPLN
Command | CSG_CHDTWP |  |  |  |  | Consignment Check Detail | 8:00 | . . . . . Y . | B DEPOT
Command | CVM_MNTHLY |  |  | DAYNO |  | Monthly CVM Interface | 8:00 | 1 | CVM
Command | CXDLYSAT |  |  |  |  | Daily SLS CMIS-Satuday | 8:00 | . . . . . Y . | CMIS
Command | CXDLYSUN |  |  |  |  | Daily SLS CMIS-Sunday | 8:00 | . . . . . . Y | CMIS
Command | DST_SAT |  |  |  |  | SAT DISTRICT STORE RES | 8:00 | . . . . . Y . | LEARN
Command | EM_PMDAY | HOLD |  |  |  | H*P&M Flash Sales-CPC Eml | 8:00 | Y Y Y Y Y . . | BD_APP
Command | EM_PRC2DP |  |  |  |  | *Email Price Chg-Follw Up | 8:00 | Y Y Y Y Y Y Y | BUSDEP APP
Command | F_ESPTBL | HOLD |  |  |  | H*FTP ESP TABLE TO ETS | 8:00 | Y Y Y Y Y Y Y | BDAPPS
Command | KRONOSWP |  |  |  |  | *WKLY:Store Data->Kronos | 8:00 | . . . . . Y Y | BDAPPLN
Command | OS_BATCH |  |  |  |  | OUT OF STOCK SUMMARY RPT | 8:00 | . . . Y . . . | LEARN
Command | PCA_STRCNT |  |  |  |  | Thur->Sun Inventory Count | 8:00 | . . . Y Y Y Y | BP-APPS
Command | PLNCHGFIL |  |  |  |  | Get PLNCHGFIL->PLNCHG Fil | 8:00 | Y . . . . . . | BD APPLIC
Command | PRGE_PRCZN |  |  |  |  | Purge Expired PRCZNO rcds | 8:00 | Y Y Y Y Y Y Y | ZONE PRICE
Command | SEND_EDI0 |  |  |  |  | EDI PO TRANSFERS | 8:00 | Y Y Y Y Y Y . | LEARN
Command | SKC_UPDPRC |  |  |  |  | SKU CENTRAL GALAXY UPDATE | 8:00 | Y Y Y Y Y Y . | LEARN
Command | SKU_TRNSLN |  |  |  |  | SKU French Translation | 8:00 | Y Y Y Y Y Y Y | BD_APPL
Command | SYSPRFDSP |  |  |  |  | DSPUSRPRF to BUSDEPUSRS | 8:00 | Y Y Y Y Y Y Y
Command | SYSSSLCHK |  |  |  |  | Check for SSL v2 | 8:00 | Y Y Y Y Y Y Y
Command | SYSUSRPRF | HOLD |  |  |  | DSPUSRPRF to ITTOOLS | 8:00 | Y Y Y Y Y Y Y
Command | TRF_AUTRCV |  |  |  |  | Auto Rec. Old Trfs | 8:00 | Y Y Y Y Y Y Y | BUSDEP
Command | AS2_CHKCOM | HOLD |  |  |  | H*Check AS2 Comm. Line | 8:15 | Y Y Y Y Y Y Y | BD_APPLN
Command | CKMONSWAW |  |  |  |  | Check MONSWABRM for SLA | 8:15 | . . . . . . Y
Command | CPYAHS_P |  |  |  |  | *Upload Auto Hub&Spk Data | 8:15 | Y Y Y Y Y Y Y | BDAPPS
Command | CSH900 |  |  |  |  | PRICE OVERRIDE REPORT | 8:15 | Y Y Y Y Y Y Y | LEARN
Command | EMSLSVARDP |  |  |  |  | Email Sales Var Sum-DP | 8:15 | Y Y Y Y Y . . | BD-APPLICA
Command | EMSLSVARWP |  |  |  |  | Email Sales Var Sum-WP | 8:15 | . . . . . Y Y | BD-APPLICA
Command | PLNE3MINQT |  |  |  |  | Update E3 Min Pres Qty | 8:15 | Y . . . . . . | BD-APPS
Command | CH_E3POCDP |  |  |  |  | Check New E3 PO Count | 8:30 | Y Y Y Y Y . . | BDAPPLN
Command | EM_HUGEQTY |  |  |  |  | Email Huge Inv Adj Qty | 8:30 | Y Y Y Y Y Y Y | BDAPPLN
Command | FD15YSLSDP | HOLD |  |  |  | H*D15 YDay SL-Fill Rpt-DL | 8:30 | Y Y Y Y Y . . | BD APPLN
Command | FD20_SLSDP | HOLD |  |  |  | H*D20 YDay SL-Fill Rpt-DL | 8:30 | Y Y Y Y Y . . | BD APPLN
Command | HEAD_COUNT | HOLD |  |  |  | H*Head Count Sales file | 8:30 | Y Y Y Y Y Y Y | BD APPLN
Command | MANL120C | HOLD |  |  |  | H*MAWM ShipConf/No OB-Sls | 8:30 | Y Y Y Y Y . . | BD
Command | MOOSE3_WP |  |  |  |  | Rebuild MOOSE3-Weekend | 8:30 | . . . . . Y Y | BD_APP
Command | OF_IN_AT |  |  |  |  | Oracle Terms to JDA | 8:30 | Y Y Y Y Y . . | BUSDEP
Command | OF_IN_AV |  |  |  |  | Oracle Trade Vendors JDA | 8:30 | Y Y Y Y Y . . | BUSDEP
Command | OF_IN_GA |  |  |  |  | Oracle Chart Accts JDA | 8:30 | Y Y Y Y Y Y Y | BUSDEP
Command | OF_IN_GL |  |  |  |  | Oracle Locations to JDA | 8:30 | Y Y Y Y Y Y Y | BUSDEP
Command | OF_IN_GR |  |  |  |  | Oracle Exch Rates to JDA | 8:30 | Y Y Y Y Y Y Y | BUSDEP
Command | OF_IN_GT |  |  |  |  | Oracle GL TransactionsJDA | 8:30 | Y Y Y Y Y Y Y | BUSDEP
Command | CSH_XTN_WK |  |  |  |  | Cash Bolt-on file-WKN | 8:45 | . . . . . Y Y | BD APPLN
Command | EM_EP_USE |  |  |  |  | Email Wkly Emg Prf Usage | 8:50 | Y . . . . . . | BDAPPS
Command | ALG_BAL_WP |  |  |  |  | *DailyAlgolia Invbal File | 9:00 | . . . . . Y Y | CMIS
Command | APLCARE |  |  |  |  | AppleCare Payment | 9:00 | . . . . . Y .
Command | CSG_3PL |  |  |  |  | 3PL Consignment | 9:00 | . . . Y . . . | BD-APPLICA
Command | CX_MST_WP |  |  |  |  | *Daily CMIS Master Files | 9:00 | . . . . . Y Y | CMIS
Command | DST_SUN |  |  |  |  | SUNDAY DISTRICT STORE RES | 9:00 | . . . . . . Y | LEARN
Command | ECP2_DAILY | HOLD |  |  |  | H*Easy Care Plan Send | 9:00 | Y Y Y Y Y Y .
Command | EM_SAPOREC |  |  |  |  | Email SA PTD PO Rec Rpt | 9:00 | Y . . . . . . | BDAPPLN
Command | EM_SKUADCH |  |  |  |  | Email Sku Add/Change Data | 9:00 | Y Y Y Y Y Y Y | BDAPPLN
Command | EM_SLS_PCS | HOLD |  |  |  | H*Eml SLS Piece Count Rpt | 9:00 | Y Y Y Y Y Y Y | BDAPPLN
Command | EML_CHKCCC | HOLD |  |  |  | H*Check Clr CR Card# Sls | 9:00 | Y Y Y Y Y . . | BDAPPLN
Command | EMMISSD1 |  |  |  |  | Email Missing Rtl Sales | 9:00 | Y Y Y Y Y . . | BDAPPS
Command | EMMISSW1 |  |  |  |  | Email Missing Rtl Sales | 9:00 | . . . . . Y Y | BDAPPS
Command | MANL100C | HOLD |  |  |  | H*MAWM Json Error Alert | 9:00 | Y Y Y Y Y . . | BD
Command | OF_EML_CNF |  |  |  |  | Email Outstndng Confirms | 9:00 | Y Y Y Y Y Y Y | BUSDEP
Command | OOSLBD15 | HOLD |  |  |  | H*Prt Out of Stk Lbl D15 | 9:00 | Y Y Y Y Y Y Y | BDAPPLN
Command | PCU100MP | HOLD |  | DAYNO |  | Profile Cleanup Utility. | 9:00 | 1 | IT
Command | POSPRGCOAL |  |  |  |  | Purge Coalition POS Data | 9:00 | . . 2 . . . .
Command | SAI_INPI |  |  |  |  | SA Physical Inventory2010 | 9:00 | . . . . . Y . | INVENTORY
Command | SKU_TRNRPT |  |  |  |  | SKU Translation Report | 9:00 | Y Y Y Y Y . . | BD APP
Command | SUNIRF_WP |  |  |  |  | SUNRISE Inv Fresh Sat-Sun | 9:00 | . . . . . Y Y | BDAPPLN
Command | SYSEMGAUDR |  |  |  |  | Print Emg Prf Audit Rpt | 9:00 | Y . . . . . . | BDAPPS
Command | SYSPRFDLT |  |  | DAYNO |  | Profile Deletion Utility. | 9:00 | 1 | IT
Command | SYSPTFLOAD | HOLD |  |  |  | Load/Set to apply PTF | 9:00 | . . . Y . . . | PTF
Command | SYSSTPROLL | HOLD |  |  |  | Dasd plus Rolling Survey | 9:00 | . . . . . . Y
Command | WRC_INVOIC | HOLD |  |  |  | H*VRM Inv DO NOT take DO | 9:00 | Y . . . . . .
Command | EML_AS2ERR |  |  |  |  | Email/Text AS2 Err Rpt | 9:15 | Y Y Y Y Y . . | BDAPPS
Command | EM_IPHONE | HOLD |  |  |  | H*Email iPhone Sales Rpt | 9:30 | . Y . . . . . | BDAPPLN
Command | EMSAPRTHUB | HOLD |  |  |  | H* Eml SA Prt Hub Wkly SL | 9:30 | Y . . . . . . | BD_APP
Command | ESPRNWLWP | HOLD |  |  |  | H*Generate list of cust | 9:30 | Y Y Y Y Y Y . | BD-APPS
Command | E3_PO_02 |  |  |  |  | ELECTRONIC PO TRANSFER | 9:30 | . . . . . Y . | LEARN
Command | OF_IN_RC |  |  |  |  | Orcl Reconcil Ttls JDA | 9:30 | Y Y Y Y Y Y Y | BUSDEP
Command | PCA_PURDMZ |  |  |  |  | Purge DMZ Phy Inv Files | 9:30 | . . Y . . . . | BD_APPS
Program | SVC026CL |  |  |  |  | D*Prt SVS Settlement Rpt | 9:30 | Y Y Y Y Y Y Y | SVC REPORT
Command | DPS_DLYSLS | HOLD |  | EVERY |  | H*PCI - OMS DPS Integratn | 0:00 | Y Y Y Y Y Y . | BD-APPLICA
Command | EM_NIPHONE | HOLD |  |  |  | H*Email NoniPhone Sls Rpt | 9:45 | . Y . . . . . | BDAPPLN
Command | MONINVBL1A | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 9:45 | . . . . . . Y | BD APPLN
Command | MONINVBL7A | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 9:45 | . . . . . Y . | BD APPLN
Command | BLD_PRXFWK |  |  |  |  | Bld Program Ref-Wkend | 10:00 | . . . . . Y Y | BD APPLN
Command | CK_E3EOD1A | OMIT |  |  |  | O*Check E3 EOD(Sun)ASR | 10:00 | . . . . . . Y | BDAPPLN
Command | CXMBRRMV |  |  |  |  | Remove CMIS Feed Member | 10:00 | Y . . . . . .
Command | EM_EP_UNAP |  |  |  |  | Email Daily Emg Prf UnApr | 10:00 | Y Y Y Y Y Y Y | BDAPPS
Command | EM_PMWK | HOLD |  |  |  | H*P&M Flash Sales-CPC Eml | 10:00 | . . . . . Y Y | BD_APP
Command | EXTSLSB2WK |  |  |  |  | Build Ext. Sls-2 Week Ago | 10:00 | . . . . . Y . | BDAPPS
Command | F_OS_POTRW |  |  |  |  | FTP Unrec PO Trf-BTS Wk N | 10:00 | . . . . . Y Y | BDAPPS
Command | F_XEROXWP |  |  |  |  | *Send PO Rec RTV Info XRX | 10:00 | . . . . . . Y | BDAPPS
Command | MAPET |  |  |  |  | Marketing and Sales Event | 10:00 | Y . . . . . . | MAPET
Command | PCA940CL |  |  |  |  | Build Prices for Frz file | 10:00 | . . Y . . . . | BD_APPS
Command | PLNCHGOR | HOLD |  |  |  | H*Add/Del Original Report | 10:00 | Y . . . . . . | BD APPLIC
Command | POS_REJECT | HOLD |  |  |  | H*Eml Reject POS Trans Rp | 10:00 | Y Y Y Y Y Y Y | BD-APPS
Command | POSREFRESH |  |  |  |  | Refresh price @ store | 10:00 | Y Y Y Y Y . . | SDI
Command | PURG_TSGNS |  |  |  |  | Purge Temp SGN Suppress | 10:00 | . . . . Y . . | BD APP SUP
Command | RBT655 |  |  |  |  | Purge Robot History | 10:00 | . . . . Y . .
Command | S_SLS_EX |  |  |  |  | Staples Sales Extract | 10:00 | Y . . . . . . | STAPLES
Command | SYSBCKPRG |  |  |  |  | Purge backup audit log | 10:00 | Y Y Y Y Y Y Y
Command | SYSCHKCER1 |  |  |  |  | Check SSL Cert Expiry*SYS | 10:00 | Y . . . . . . | BD_APP
Command | SYSCHKLKEY |  |  |  |  | Check license keys expire | 10:00 | Y Y Y Y Y Y Y
Command | SYSIFSDLT |  |  |  |  | IFS CLEANUP UTILITY | 10:00 | . . . . . . Y
Command | SYSSWPAUD |  |  |  |  | Audit swap profiles | 10:00 | Y Y Y Y Y Y Y
Command | SYSDDMAUDP |  |  |  |  | Add Users to IP DDM SV | 10:01 | Y Y Y Y Y Y Y | HD-AS400
Command | SYSRSFCHK | HOLD |  | EVERY |  | Check RSF communications | 0:00 | Y Y Y Y Y Y Y
Command | EM_PRC3DP |  |  |  |  | Email Price Chg.-Init run | 10:05 | . Y . . . Y Y | BUSDEP APP
Command | EXTSLSB1DW |  |  |  |  | Build Ext. Sls-1 Week Ago | 10:05 | . . . . . . Y | BDAPPS
Command | EXTSLSB2DW |  |  |  |  | Build Ext. Sls-2 Week Ago | 10:05 | . . . . . Y . | BDAPPS
Command | SYSCHKCER2 |  |  |  |  | Check SSL Cert Expiry | 10:05 | Y . . . . . . | BD_APP
Command | CH_LBL_OD |  |  |  |  | Check O/S On Demand Signs | 10:30 | Y Y Y Y Y Y Y | BDAPPS
Command | CK_E3EOD1W | OMIT |  |  |  | O*Check E3 EOD(Sun)AWR | 10:30 | . . . . . . Y | BDAPPLN
Command | FD15YSLSWP | HOLD |  |  |  | H*D15 YDay SL-Fill Rpt-WN | 10:30 | . . . . . Y Y | BD APPLN
Command | FD20_SLSWP | HOLD |  |  |  | H*D20 YDay SL-Fill Rpt-WK | 10:30 | . . . . . Y Y | BD APPLN
Command | BPS_ALLOC | HOLD |  | EVERY |  | H*Bopis Allocation Bucket | 0:00 | Y Y Y Y Y Y Y | BUSDEP
Command | PRTLABELW |  |  |  |  | *Print Labels | 10:40 | . Y . . . Y Y | SDI
Command | SYSDCMJBSC |  |  |  |  | crt dcm jobscde files | 10:41 | Y Y Y Y Y Y Y
Command | BLUEYNDLCP |  |  |  |  | Blue Yonder LCP | 11:00 | Y Y Y Y Y Y . | BD
Command | CVM_CSAT1 | HOLD |  |  |  | H*Send/Receive CVM Data | 11:00 | Y Y Y Y Y Y Y | BD-APP
Command | D1SLSEML |  |  |  |  | EMail Dly Sls Decision1 | 11:00 | . . Y . . . . | BDAPPS
Command | EM_DSAW1 |  |  |  |  | *EMail Daily SLS All Str | 11:00 | . . . . . Y Y | BD_APP
Command | F_PRECIMA |  |  |  |  | *FTP Precima Prc Data | 11:00 | Y Y Y Y Y Y Y | BDAPPS
Command | MAWM_SYNCH |  |  |  |  | MAWM Inventory Synch ** | 11:00 | . . . . . . Y | BD
Command | MMEJOB | HOLD |  |  |  | H*Run Weekly MME Project | 11:00 | Y Y Y Y Y Y Y | MMEAPL
Command | PASS_CPY |  |  |  |  | *PASS Trans Dtl Feed | 11:00 | Y Y Y Y Y Y Y | BD APPS
Command | SYSCACHBAT |  |  |  |  | cache battery listing | 11:00 | . . Y . . . .
Command | BELL_INVAD | HOLD |  |  |  | BELL Inventory Adjustment | 11:30 | Y Y Y Y Y Y Y
Command | EM_DSTW1 |  |  |  |  | *EMail Daily SLS Transfrm | 11:30 | . . . . . Y Y | BD_APP
Command | EMLCHBER#1 | HOLD |  |  |  | H*Alert-CHub SLS Post ER | 11:30 | Y Y Y Y Y Y Y | BDAPPLN
Command | EMLCHBER#2 |  |  |  |  | EMail CHub Error Report | 11:30 | Y Y Y Y Y Y Y | BD_APPLN
Command | EM_DSAD2 |  |  |  |  | *EMail Daily SLS All Str | 11:59 | Y Y Y Y Y . . | BD_APP
Command | CH_FC_DATE |  |  |  |  | Check FC Cur Billing Date | 12:00 | Y Y Y Y Y . . | BD_APP
Command | CK_E3EOD3A |  |  |  |  | Check E3 EOD (Sat) ASR | 12:00 | . . . . . Y . | BDAPPLN
Command | CPCWEBTST | HOLD |  |  |  | H*CPC WEBSERVICE RACHAEL* | 12:00 | Y . . . . . . | BD
Command | DLTTRNLOG |  |  |  |  | Transmission Log Delete | 12:00 | . . . . L . . | ALERT
Command | F_ESPOCS | HOLD |  |  |  | H*FTP Open ESP Case->ECP | 12:00 | Y Y Y Y Y Y Y | BDAPPS
Command | MANL115C | HOLD |  |  |  | H*MAWM PORcvd not Verify | 12:00 | Y Y Y Y Y . . | BD
Command | MANL117C | HOLD |  |  |  | H*MAWM PORcpt/Verfy Var | 12:00 | Y Y Y Y Y . . | BD
Command | MANL118C | HOLD |  |  |  | H*MAWM PORcpt/Cost Var | 12:00 | Y Y Y Y Y . . | BD
Command | MANL200C | HOLD |  |  |  | H*MAWM Inbound Json Er Rp | 12:00 | Y Y Y Y Y . . | BD
Command | PCA_CNTMST |  |  |  |  | FTP Count Fil,Eml->Inv/Mr | 12:00 | . . Y . . . . | BD_APPS
Command | RMA_RESP |  |  |  |  | RMA Response Monthly | 12:00 | . Y . . . . . | BD_APPLIC
Command | VFOEMLWP | HOLD |  |  |  | H*Eml Sell Through Offer | 12:00 | . . . . . Y Y | BUSDEP APP
Command | EM_NOSGNWP |  |  |  |  | *Eml No Prc Chg Sign-WKN | 12:01 | . . . . . Y Y | APPLN
Command | MONINVBL1B | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 12:15 | . . . . . . Y | BD APPLN
Command | SP_VND_MET |  |  |  |  | *SPartners Vendor Metric | 12:15 | . . . . . . Y
Command | EM_DSTD2 |  |  |  |  | *EMail Daily SLS Transfrm | 12:30 | Y Y Y Y Y . . | BD_APP
Command | CH_CSHXTN |  |  |  |  | Chk Unprocess BOLT On Rec | 13:00 | Y Y Y Y Y Y Y | BD_APP
Command | CLICKSDP |  |  |  |  | *CLICKS TRACKING | 13:00 | Y Y Y Y Y Y Y | BUSDEP
Command | CRMIDLY |  |  |  |  | *Proc M/C Info from Comps | 13:00 | Y Y Y Y Y Y Y | BD APP
Command | CRT_R50CTL | HOLD |  |  |  | H*Not Use-Run in CPCDaily | 13:00 | Y Y Y Y Y Y Y | BDAPPLN
Command | DIVCLN |  |  |  |  | PURGE CANxxx DIVIDEND | 13:00 | . . . . . . Y | LEARN
Command | DRPSHPVNWP | HOLD |  |  |  | H*Vendor File | 13:00 | . . . . . Y Y | BD-APPS
Command | EM_NOSGNTU |  |  |  |  | *Eml No Prc Chg Sign-TUE | 13:00 | . Y . . . . . | APPLN
Command | E3EXCP_B |  |  |  |  | Exception Report BOW | 13:00 | Y . . . . . . | BD APP
Command | RFRSH_CLN |  |  |  |  | SUNRISE WORKFILE CLEAN-UP | 13:00 | Y Y Y Y Y . . | LEARN
Command | SLS_DWNLOD |  |  |  |  | POPULATE SALES DWNLD FILE | 13:00 | . Y . . . . . | LEARN
Command | CH_LBL_DE |  |  |  |  | Check O/S PRC CHG Signage | 13:30 | Y Y Y Y Y Y Y | BDAPPS
Command | CRMRDLY |  |  |  |  | Process last 2weeks data | 13:30 | Y Y Y Y Y Y Y | BD APP
Command | LWP_DAILY |  |  |  |  | *Lowest Price Daily | 13:30 | Y Y Y Y Y Y Y | BD_APP
Command | SYSSBMJOBT | HOLD |  |  |  | Submit test rmv | 13:35 | Y . . . . . .
Command | CH_E3POCWP |  |  |  |  | Check New E3 PO Count | 13:45 | . . . . . Y Y | BDAPPLN
Command | CK_E3EOD3W |  |  |  |  | Check E3 EOD (Sat) AWR | 13:45 | . . . . . Y . | BDAPPLN
Command | MONINVBL7B | HOLD |  |  |  | H*INVBAL Refresh to Sunrs | 13:45 | . . . . . Y . | BD APPLN
Command | ACNEILSENM |  |  |  |  | Snd Sls To AC Neilsen:Mon | 14:00 | Y . . . . . . | ACNEILSEN
Command | AIRM_RVRSE | HOLD |  |  |  | H*Air Mile Sales Reversal | 14:00 | Y Y Y Y Y Y Y
Command | CLK_ERR |  |  |  |  | CLICKS ERROR REPORTS | 14:00 | . Y Y Y Y Y Y | BUSDEP
Command | CLK_MON |  |  |  |  | CLICKS REPORTS FROM RBO | 14:00 | Y . . . . . . | BUSDEP
Command | CLR_IFSRMA |  |  |  |  | Clear RMA Obj in IFS | 14:00 | . . . . . Y . | BD-APPLICA
Command | CLR_OUTQSW |  |  |  |  | Weekly Clear Out Queues | 14:00 | . . . . . . Y | LEARN
Command | EBY_TRF_WK |  |  |  |  | *Send eBay transfer Wkend | 14:00 | . . . . . Y Y | BD APP
Command | EMLNOSL1 | HOLD |  |  |  | H*Eml No SLS List Batch 1 | 14:00 | Y Y Y Y Y Y .
Command | EMLNOSL5 | HOLD |  |  |  | H*Eml No SLS List Batch 5 | 14:00 | Y Y Y Y Y Y .
Command | EMMISSD2 |  |  |  |  | Email Missing Rtl Sales | 14:00 | Y Y Y Y Y . . | BDAPPS
Command | PURGELBL |  |  |  |  | purge signage spool file | 14:00 | Y Y Y Y Y Y Y | BD APP
Command | SLS_GM_RPT |  |  |  |  | SALES GROSS MARGIN REPORT | 14:00 | . . . . . . Y | LEARN
Command | SYSBRMSMNT |  |  |  |  | Run BRMS Maintenance | 14:00 | Y Y Y Y Y Y Y | BRMS
Command | CRMXDLY |  |  |  |  | *Send m/c data to compass | 14:30 | Y Y Y Y Y Y Y | BD APPLICA
Command | EM_PRC1DP |  |  |  |  | Eml Prc Chg.-Init. Run | 14:30 | Y . Y Y Y . . | BUSDEP APP
Command | LBR_ERNMON | HOLD |  |  |  | H*Upload Store Spt Hr-Mon | 14:55 | Y . . . . . . | BD APPLN
Command | LBR_ERNTUE | HOLD |  |  |  | H*Upl Store Spent Hr-Tue | 14:55 | . Y . . . . . | BD APPLN
Command | EM_DSAW2 |  |  |  |  | *EMail Daily SLS All Str | 15:00 | . . . . . Y Y | BD_APP
Command | EMLNOSL2 | HOLD |  |  |  | H*Eml No SLS List Batch 2 | 15:00 | Y Y Y Y Y Y .
Command | MAWM_PURGE |  |  |  |  | MAWM file Purge | 15:00 | . . . . . . Y | BD
Command | SAI_DPRNT | HOLD |  |  |  | H* Dly SBA Digital Print | 15:00 | Y Y Y Y Y Y Y | BDAPPLICAT
Command | SKUMOO |  |  |  |  | SKUMOO Spread Sheet | 15:00 | Y . . . . . . | MER
Command | SYSBKUPRPT |  |  |  |  | MOVE BRMS BACKUP REPORTS | 15:00 | Y Y Y Y Y Y Y | BRMS
Command | BPS_AVLQTY | HOLD |  | EVERY |  | H*Refresh BOPIS Avail Qty | 0:00 | Y Y Y Y Y Y Y
Command | EM_DSTW2 |  |  |  |  | *EMail Daily SLS Transfrm | 15:30 | . . . . . Y Y | BD_APP
Command | E3_PO_03 |  |  |  |  | *ELECTRONIC PO TRANSFER | 15:30 | . . . . . . Y | LEARN
Command | LCT_UPL2 |  |  |  |  | Upload Labor Cost Xfer | 15:30 | . Y . . . . . | BD APPLN
Command | PRTLABEL |  |  |  |  | *Print Signage Label | 15:30 | Y . Y Y Y . . | SDI
Command | CH_PRCCHGC |  |  |  |  | Alert Sku Price Change CT | 15:32 | Y Y Y Y Y Y Y | BD APPLN
Command | DLYQWKN3PM | HOLD |  |  |  | H*Block 15 QWKNBCH3 Jobs | 16:00 | Y Y Y Y Y . . | BD_APP
Command | EMLNOSL3 | HOLD |  |  |  | H*Eml No SLS List Batch 3 | 16:00 | Y Y Y Y Y Y .
Command | EMLNOSL6 |  |  |  |  | Email No SLS List Batch 5 | 16:00 | . . . . . . Y
Command | PCA_EMLLST |  |  |  |  | Email Wkly Str Inv Lst | 16:00 | . . Y . . . . | BDAPPLN
Command | PO_OD_RPT |  |  | INDAY |  | Overdue PO report | 16:00 | . . . . . . .
Command | RTVPENDING |  |  |  |  | Create RTV Pending record | 16:00 | . . . . . . Y | RTV
Command | SEND_EDI1 |  |  |  |  | EDI PO TRANSFERS | 16:00 | Y Y Y Y Y Y . | LEARN
Command | SPIINTUP | HOLD |  |  |  | H*SPI Prod Integration | 16:00 | . Y Y Y Y . . | SPI
Command | SPIPURGE | HOLD |  |  |  | H*Purge SPI Collection Dt | 16:00 | Y . . . . . . | BD APPS
Command | SYSCHKBCK |  |  |  |  | Check Backup Job Logs | 16:00 | Y Y Y Y Y Y Y
Command | POS_TENDER | HOLD |  | EVERY |  | H*Populate AN# to CSHTND | 0:00 | Y Y Y Y Y Y Y | BD-APPLICA
Command | EM_NOSGNDP |  |  |  |  | *Eml No Prc Chg Sign-DLYP | 16:50 | Y . Y Y Y . . | APPLN
Command | AGEOUTQ | HOLD |  |  |  | H*Age Outq Qprint | 17:00 | Y Y Y Y Y . .
Command | BHN_DLYSTM |  |  |  |  | BHN statement posting | 17:00 | Y Y Y Y Y Y Y | BD-APPLICA
Command | CCF2SUNR |  |  |  |  | *Send Coupon to Sunrise | 17:00 | Y Y Y Y Y Y Y | CCF2SUNR
Command | EMLNOSL4 | HOLD |  |  |  | H*Eml No SLS List Batch 4 | 17:00 | Y Y Y Y Y Y .
Command | JRNRCVDLWP | HOLD |  |  |  | H*Delete Journal Receiver | 17:00 | Y . . . . . . | HD-AS400
Command | LVTINVOICE |  |  |  |  | Livingston Invoice | 17:00 | . . . . . Y .
Command | PERFNAVPM | HOLD |  |  |  | Monitor | 17:00 | Y Y Y Y Y Y Y | TECSUPPORT
Command | SP_SALES |  |  |  |  | StaplesPartners Sales Hst | 17:00 | Y . . . . . .
Command | CLR_QEZJOB |  |  |  |  | Clear outq qezjoblog | 17:15 | . . . . Y . . | CLR_QEZJOB
Command | INVBAX_API | HOLD |  | EVERY |  | H*API INVBAX | 0:00 | Y Y Y Y Y Y Y
Command | AV_HOURLY |  |  | EVERY |  | Outbound Hourly Feed to A | 0:00 | Y Y Y Y Y . . | BDAPPLICAT
Command | DLTHSTLOG | HOLD |  |  |  | H*Delete History | 18:00 | Y Y Y Y Y Y Y
Command | EMLTRFVAR |  |  |  |  | Email Transfer Var Rpt | 18:00 | . . . . . . Y | BDAPPS
Command | JACKRTLRPT |  |  |  |  | *Print Retail Jackie Rpt | 18:00 | . . . . . . Y | BDAPPS
Command | LBR_PHYI |  |  |  |  | Labour Hours Phy Inv Flag | 18:00 | . . . . . Y . | LABOUR_HRS
Command | MICROSOFT |  |  |  |  | *EDI RUN FOR MICROSOFT | 18:00 | . . . . . . Y | LEARN
Command | NPD_SLS |  |  |  |  | Weekly Sales Summary | 18:00 | . . . . . . Y | BD APPS
Command | RBN35001 |  |  |  |  | Product Events Delete | 18:00 | . . . . Y . . | NETWORK
Command | RBN35002 |  |  |  |  | Packet History Delete | 18:00 | . . . . Y . . | NETWORK
Command | SYSJRNCHK | HOLD |  |  |  | Journal Monitor Program | 18:00 | Y Y Y Y Y Y Y
Command | SYSSAVARC |  |  |  |  | Archive check pts to hst | 18:00 | Y Y Y Y Y Y Y
Command | WHS_TRFR |  |  |  |  | DAILY TRFWKN FILE DATA | 18:00 | Y Y Y Y Y Y . | LEARN
Command | CHK_DUPPO |  |  |  |  | Check Duplicate PO/Sku | 18:30 | . . . . Y . . | BDAPPLN
Command | EMMISSW2 |  |  |  |  | Email Missing Rtl Sales | 18:30 | . . . . . Y Y | BDAPPS
Command | F_ETS_ORD |  |  | EVERY |  | Send Tec Ord to ETS Servr | 18:47 | Y Y Y Y Y Y Y | BDSYSPRF
Command | OVR_PRINTQ |  |  | EVERY |  | Override Store Printq | 18:47 | Y Y Y Y Y Y Y | BDSYSPRF
Command | BPS_OK_NO2 |  |  | EVERY |  | OTH-Refresh BPS Alloc Qty | 18:50 | . Y Y Y Y . .
Command | BPS_PCKEML |  |  | EVERY |  | Prt/Eml BOPIS Ord Pick Up | 18:50 | Y Y Y Y Y Y Y | BUSDEP
Command | CH_MSGT2F2 |  |  | EVERY |  | Check Job has MSGW-T2F-#2 | 18:50 | . Y Y Y Y . . | BD_APP
Command | CPP_KIOSK |  |  | EVERY |  | ***Copy & Print Kiosk Ord | 18:50 | Y Y Y Y Y Y Y | BDSYSPRF
Command | CPS_ORDRTV |  |  | EVERY |  | Extract C&P Orders for PR | 18:50 | Y Y Y Y Y Y Y | BD APPLN
Command | CXINVAUD |  |  | EVERY |  | Web Service Inventory UPD | 18:50 | Y Y Y Y Y Y Y | BD APPLN
Command | SBL_ORDER |  |  | EVERY |  | SBL Orders Generation | 18:50 | Y Y Y Y Y Y Y | BD APPLN
Command | SOSCFM |  |  | EVERY |  | *Spec Order Payment Confr | 18:50 | Y Y Y Y Y Y Y | BUSDEP
Command | STRPRT |  |  | EVERY |  | Start all printers | 18:50 | Y Y Y Y Y Y Y | OPS
Command | SYSCFSGET |  |  | EVERY |  | Trigger CFS get | 18:50 | Y Y Y Y Y Y Y
Command | SYSDLTSPLF |  |  | EVERY |  | Delete spool files | 18:51 | Y Y Y Y Y Y Y
Command | DCA1_SLSD3 |  |  | EVERY |  | CA Sales Fri-Sat *10 min | 18:52 | . . . . Y Y .
Command | @XMLSLS |  |  | EVERY |  | XML POS Process XPS=>USI* | 18:55 | Y Y Y Y Y Y Y | BD-APPLICA
Command | CPC_TXNPCK |  |  | EVERY |  | CPC Txn pickup Trigger PT | 18:55 | Y Y Y Y Y Y Y | BD
Command | SAI_DAILY |  |  | EVERY |  | SA Dly/SP E3@10pm Mon-Fri | 18:58 | Y Y Y Y Y Y . | BD APP
Command | AR_MSTUPD |  |  |  |  | Vendor Ar update | 19:00 | Y Y Y Y Y . . | BD-APPS
Command | AUT_OOSOPN |  |  |  |  | Auto Scan Batch Open | 19:00 | Y Y Y Y Y Y Y
Command | BELL_PORCV |  |  | EVERY |  | BELL PO Receive | 19:00 | Y Y Y Y Y Y Y
Command | CH_SSH |  |  | EVERY |  | Check SSH Connection | 19:00 | Y Y Y Y Y Y Y | BD_APP
Command | CPCDAILY |  |  | EVERY |  | CPC Txn & Tender process | 19:00 | Y Y Y Y Y Y Y | BD
Command | CPP_PO |  |  | EVERY |  | CPC PO creation #1 | 19:00 | Y Y Y Y Y Y Y | BDSYSPRF
Command | EXTSLSB1WK |  |  |  |  | *BLD Ext. Sls-1 Week Ago | 19:00 | . . . . . . Y | BDAPPS
Command | E3_DUP_PO |  |  | EVERY |  | Eml Dup E3 Rls Ord-DLY | 19:00 | Y Y Y Y Y . .
Command | IS4_AUTOPN | HOLD |  |  |  | H*Auto Scan Batch Open | 19:00 | Y Y Y Y Y Y Y
Command | MAWM_IN |  |  | EVERY |  | MAWM In bound Feeds | 19:00 | Y Y Y Y Y Y . | BD
Command | OF_OUT_AI |  |  | EVERY |  | *Invoice Interface Oracle | 19:00 | Y Y Y Y Y Y Y | BUSDEP
Command | RMAFTP |  |  | EVERY |  | RTV Get Inbound Email ATT | 19:00 | Y Y Y Y Y Y Y | BD APP SUP
Command | SAE_POCNL |  |  |  |  | SA Daily PO Auto Cancel | 19:00 | Y Y Y Y Y . . | BD APP
Command | SEND_EDI2 |  |  |  |  | EDI PO TRANSFERS | 19:00 | Y Y Y Y Y . Y | LEARN
Command | SKU_BPSFLG |  |  |  |  | SKU Bopisflag feed to PDB | 19:00 | Y Y Y Y Y Y Y | BUSDEP
Command | SPOOLS |  |  |  |  | Weekly Spool backup | 19:00 | . . . . . Y . | BRMS
Command | SYS_ORACLE |  |  |  |  | Clean up ORACLE Outq | 19:00 | . . . . . . Y
Command | SYSCHKJQE3 |  |  | EVERY |  | Check E3 resource jobqs | 19:00 | Y Y Y Y Y Y Y | BUSDEP
Group | SYSCHKSYS |  |  | EVERY |  | System Resource Checks | 19:00 | Y Y Y Y Y Y Y |  | SYSCHKSYS
Command | SYSPQMON |  |  | EVERY |  | fax queue monitor | 19:00 | Y Y Y Y Y Y Y
Command | SYSRSJOB1 | HOLD |  | DATE |  | Post Swap + 1 Day Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB2 | HOLD |  | DATE |  | Post Swap + 2 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB3 | HOLD |  | DATE |  | Post Swap + 3 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB4 | HOLD |  | DATE |  | Post Swap + 4 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB5 | HOLD |  | DATE |  | Post Swap + 5 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB6 | HOLD |  | DATE |  | Post Swap + 6 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB7 | HOLD |  | DATE |  | Post Swap + 7 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB8 | HOLD |  | DATE |  | Post Swap + 14 Days Tasks | 19:00 | . . . . . . .
Command | SYSRSJOB9 | HOLD |  | DATE |  | Post Swap + 30 Days Tasks | 19:00 | . . . . . . .
Command | SYSSAGET |  |  | EVERY |  | Trigger SAGET | 19:00 | Y Y Y Y Y Y Y
Command | SYSSIAMUID | HOLD |  |  |  | SIAM UID Update | 19:00 | Y Y Y Y Y Y Y
Command | VC_DAILY |  |  |  |  | Inbound invoice JDA AR | 19:00 | Y Y Y Y Y Y . | BUSDEP
Command | VRM_BLD_R |  |  |  |  | H*VRM Weekly HSTR & HSTCR | 19:00 | . . . . . Y .
Command | VRM_BLD_RY | HOLD |  |  |  | H*VRM Weekly HSTR & HSTCR | 19:00 | . . . . . Y .
Command | WK_DST_SUN |  |  |  |  | WKLY DISTRICT RESULTS-SUN | 19:00 | . . . . . . Y | LEARN
Command | SYSCHKCMT |  |  | EVERY |  | Check Open Commits | 19:01 | Y Y Y Y Y Y Y
Command | SYSCHK992 |  |  | EVERY |  | Check port 992 Close Wait | 19:01 | Y Y Y Y Y Y Y
Command | SYSDSTQCHK |  |  | EVERY |  | DSTQ monitor | 19:01 | Y Y Y Y Y Y Y
Command | DCA2_OTHER |  |  | EVERY |  | *CA DownStreamAps *60 min | 19:05 | Y Y Y Y Y Y Y
Command | CPP_SHIP |  |  | EVERY |  | CPC Ship Ack & Recv #2 | 19:15 | Y Y Y Y Y Y Y | BDSYSPRF
Command | E3_PO_01 |  |  |  |  | ELECTRONIC PO TRANSFER | 19:15 | Y Y Y Y Y . . | LEARN
Command | MAWM_OUT |  |  | EVERY |  | MAWM Outbound Feeds | 19:15 | Y Y Y Y Y Y . | BD
Command | OF_IN_CNF |  |  | EVERY |  | Confirmation File Retrvl | 19:15 | Y Y Y Y Y Y Y | BUSDEP
Command | EDISATRF |  |  |  |  | EDI S302 Transfer to SA | 19:25 | Y Y Y Y Y . . | BDAPPLICAT
Command | EML_DUPLNK |  |  |  |  | Check Dupl Recycle Fee | 19:30 | Y Y Y Y Y Y Y | BDAPPLN
Command | OF_OUT_GI |  |  | EVERY |  | Journal Interface Oracle | 19:30 | Y Y Y Y Y Y Y | BUSDEP
Command | SP_CHECK |  |  |  |  | StaplesPartners Check Dtl | 19:30 | . . . . Y . .
Command | ARP010CL |  |  |  |  | AUTO-REPLENISHMENT UPDATE | 19:35 | . . . . . Y . | UPDATE,
Command | FD15TSLSWP | HOLD |  |  |  | H*D15 TDay SL-Fill Rpt-WK | 19:45 | . . . . . Y Y | BD APPLN
Command | CLD_PRICE | HOLD |  |  |  | H*Feeds to Storage Pipe | 20:00 | Y Y Y Y Y Y Y
Command | CLR_OUTQSD |  |  |  |  | Daily Clear Out Queues | 20:00 | Y Y Y Y Y Y Y | CLR_QPRINT
Command | CPC_PRICE |  |  |  |  | *Copy Centre Payments | 20:00 | Y Y Y Y Y Y Y | BD-APPLICA
Command | CPC_RSPO |  |  |  |  | *Auto Resend CPC PO | 20:00 | Y Y Y Y Y Y Y | BD_APP
Command | E3_DUP_PO1 |  |  |  |  | Eml Dup E3 Rls Ord-WKN | 20:00 | . . . . . Y Y
Command | MAWM_DITEM |  |  |  |  | MAWM Daily Item Delta | 20:00 | Y Y Y Y Y Y Y | BD
Command | SEND_EDI3 |  |  |  |  | EDI PO TRANSFERS | 20:00 | Y Y Y Y Y . . | LEARN
Command | ST_TYPE27 |  |  |  |  | *Sell Thru Type 27 entry | 20:00 | Y Y Y Y Y Y Y | BD-APPS
Command | SVC_ACT |  |  |  |  | *SVC Card Batch Activate | 20:00 | Y Y Y Y Y Y Y | BD APP SUP
Command | SYSRMTSYNC | HOLD |  |  |  | Sync Robot ALert Files | 20:00 | Y Y Y Y Y Y Y
Command | SYSCHKCQ | HOLD |  | EVERY |  | Check RBNCQ record count | 0:00 | Y Y Y Y Y Y Y
Command | HBT_DCUP |  |  |  |  | DC.COM Upload | 20:30 | Y Y Y Y Y . . | HBT_DCUP
Command | SLCWEEKLY |  |  |  |  | Weekly Sales Contest | 20:30 | . Y . . . . . | SALEQRY
Command | ENDQINTWKE |  |  |  |  | ENDQINTWKE | 20:40 | . . . . . Y Y | LEARN
Command | UP_RELOC2N |  |  |  |  | Reloc Store POS Active=N | 20:45 | Y Y Y Y Y Y Y | BD_APP
Command | HLDJOBQS |  |  |  |  | Hold Job Queues | 20:50 | Y Y Y Y Y Y Y | HLDJOBQS
Command | ENDQINT |  |  |  |  | ENDQINT | 20:55 | Y Y Y Y Y . . | LEARN
Command | EMLPRCPR |  |  |  |  | Email Price Protection | 20:58 | Y Y Y Y Y Y Y | BDAPPLN
Command | DAYSTART |  | REACT |  |  | Day Start | 21:00 | Y Y Y Y Y . . | DAILY
Command | DAYSTARTW |  | REACT |  |  | Day Start | 21:00 | . . . . . Y Y | BD-APP
Command | E3EXCP_E |  |  |  |  | Exception Report EOW | 21:00 | . . . . . Y . | BD APP
Command | MAWM_ZITEM | HOLD |  |  |  | H*MAWM FULL Item Feed | 21:00 | Y . . . . . . | BD
Command | MAWM_ZSTOR | HOLD |  |  |  | H*MAWM FULL Store Feed | 21:00 | Y . . . . . . | BD
Command | MAWM_ZVEND |  |  |  |  | MAWM FULL Vendor Feed | 21:00 | . . . . . . Y | BD
Command | OF_PURGE | HOLD |  |  |  | H*Interface Data Purging | 21:00 | Y . . . . . . | BUSDEP
Command | PKSLIP_101 | HOLD |  | EVERY |  | H*Print Pick Slip-MinDDC | 0:00 | Y Y Y Y Y . . | BDAPPLN
Command | SYSAMLOUTQ | HOLD |  |  |  | AML OUTQ Load | 21:00 | Y Y Y Y Y Y Y
Command | CKDAYSTR |  |  |  |  | Check Resource RBDAYSTART | 21:01 | Y Y Y Y Y Y Y | RBC
Command | CHK_DAYSTR |  |  |  |  | Check DAYSTART/W Status | 21:15 | Y Y Y Y Y Y Y | BDAPPLN
Command | CH_E3_VND |  |  |  |  | Check E3 Vendor in E3SITM | 21:30 | Y Y Y Y Y Y Y | BD_APP
Command | CSH_XTN |  |  |  |  | Cash Bolt-on file-Daily | 21:30 | Y Y Y Y Y . . | BD APPLN
Command | PLNCHGFU | HOLD |  |  |  | H*Add/Del Follow Up Rpt | 21:30 | . . . . . Y . | BD APPLIC
Command | SYSAUDBKUP |  |  |  |  | Audit libraries backup | 21:30 | . . . . . . Y | BRMS
Command | AV_DAILY |  |  |  |  | Outbound Daily Feed to A | 22:00 | Y Y Y Y Y . . | BDAPPLICAT
Command | EM_REFPO |  |  |  |  | Reference PO Report | 22:00 | . . . . . Y .
Command | ESPCUI | HOLD |  |  |  | H*Upld Web ESP Cust Info | 22:00 | Y Y Y Y Y Y Y | BD APPS
Command | F_PDBPRD |  |  |  |  | *FTP Prod Master to PDB | 22:00 | Y Y Y Y Y Y Y | BD_APP
Command | HBT_GNRD |  |  |  |  | TXECCT records generation | 22:00 | Y Y Y Y Y Y Y | HBT_GNRD
Command | SAI_INRF |  |  |  |  | Weekly RF Feed From WIS | 22:00 | . . . . . . Y | BDAPPLICAT
Command | SP_STORE |  |  |  |  | StaplesPartners Store inf | 22:00 | Y Y Y Y Y Y Y
Command | SYSCLNQEZJ |  |  |  |  | Clean QEZJOBLOG | 22:00 | Y Y Y Y . . .
Command | SYSDLTIFS |  |  |  |  | Delete IFS files | 22:00 | . . . . . . Y
Command | SYSENDMMX |  |  |  |  | Special End of Mimix | 22:00 | . . . . Y . .
Command | SYSILMTHSC |  |  |  |  | ILMT Hardware Scan | 22:00 | Y Y Y Y Y Y Y
Command | UPD_CSTPLN |  |  |  |  | *Set CSTPLN for Tomorrow | 22:00 | Y Y Y Y Y Y Y | BD_APP
Command | CKRBTGNR |  |  |  |  | Check Resource RBRBT_GNRD | 22:01 | Y Y Y Y Y Y Y | RBC
Command | SSWINBND1 |  |  |  |  | FTP/In Store Signage WHSE | 22:10 | Y Y Y Y Y Y . | BDAPPLN
Command | SYSUSRAUD |  |  |  |  | User Auditing Set | 22:15 | Y Y Y Y Y Y Y
Command | EM_IMJCK |  |  |  |  | Email Import Jackie Rpt | 22:25 | . . . . . . Y | BDAPPLN
Command | SYSUSRAUD2 |  |  |  |  | User Auditing Remove | 22:25 | Y Y Y Y Y Y Y
Command | SAI_INFI |  |  |  |  | Weekly FB Feed From Alpha | 22:30 | . . . . . . Y | BDAPPLICAT
Command | SP_OPNPO |  |  |  |  | StaplesPartners opn PO | 22:30 | Y Y Y Y Y Y Y
Command | SYSSIAMAUT |  |  |  |  | SIAM GRTOBJAUT *ALL | 22:30 | Y Y Y Y Y Y Y
Command | FD15TSLSDP | HOLD |  |  |  | H*D15 TDay SL-Fill Rpt-DL | 22:45 | Y Y Y Y Y . . | BD APPLN
Command | DYNSKU_P | HOLD |  |  |  | H*FTP Dynamic Sku List | 22:55 | Y Y Y Y Y Y Y | BDAPPS
Command | CKQESLIN |  |  |  |  | Check Resource QESLINE | 23:00 | Y Y Y Y Y Y Y | SYSTEM
Command | CKQESPPL |  |  |  |  | Check Resource QESPPLIN | 23:00 | Y Y Y Y Y Y Y | SYSTEM
Command | CLRJDADEP |  |  |  |  | CLEAR JDA JOB DEPENDENCY | 23:00 | . . . . . . Y
Command | ENDQPGMRSA |  |  |  |  | ENDQPGMRSA | 23:00 | . . . . . Y Y | LEARN
Command | ESPCUO | HOLD |  |  |  | H*Dld AS400 ESP Cust Info | 23:00 | Y Y Y Y Y Y Y | BD APPS
Command | FRN_TRFCNL |  |  |  |  | Cancel outdated furniture | 23:00 | Y Y Y Y Y . . | BD-APPLI
Command | POSCLEANUP |  |  |  |  | POS IFS folder cleanup | 23:00 | Y Y Y Y Y Y Y | BD
Command | PROGRESPTF | HOLD |  | INDAY |  | H*Progress PTF SI14206 | 23:00 | . . . . . . .
Command | RBCSTRTMON |  |  |  |  | Re-start RBCQSYSOPR | 23:00 | Y Y Y Y Y Y Y
Command | RBT34504 |  |  |  |  | ROBOT Schedule of Jobs to | 23:00 | Y Y Y Y Y Y Y | ROBOT
Command | SAI_INFW |  |  |  |  | Weekly FW Feed From WIS | 23:00 | . . . . . . Y | BDAPPLICAT
Command | SPOOLSM | HOLD |  |  |  | H*Special spl files save | 23:00 | . . . . Y . . | BRMS
Command | AR_UPDATE |  |  |  |  | Update A/R Sub-ledger | 23:30 | Y Y Y Y Y Y Y | AR
Command | SAI_INVR |  |  | EVERY |  | SA Weekly Inventory | 0:00 | . . . . . Y . | BD APP
Command | SYSCLNALLS |  |  |  |  | Clean Alliance/SSH | 23:30 | Y Y Y Y Y Y Y
Command | SYSCLNIMAI |  |  |  |  | Clean IMAIL log files | 23:30 | Y Y Y Y Y Y Y
Command | SYSCLNRMA |  |  |  |  | Clean /APPS/RMA/IN | 23:30 | Y Y Y Y Y Y Y
Command | SYSCLNTOWN |  |  |  |  | Clean townsend archive | 23:30 | Y Y Y Y Y Y Y
Command | CH_SAE3SKU |  |  |  |  | Check SA E3 Sku Interface | 23:40 | Y Y Y Y Y . . | BD_APP
Command | DCA1_SLSWP |  |  | EVERY |  | *CA Sales Sunday *10 min | 0:00 | . . . . . . Y
Command | AUT_OOSCLS |  |  |  |  | Auto Scan Batch Close | 23:45 | Y Y Y Y Y Y Y
Command | CLR_HDMSG |  |  |  |  | Clear Msq Que HD33MSG | 23:45 | . . . . . . Y
Command | EMLPOSERR | HOLD |  |  |  | H*POS File Mering Error | 23:45 | Y Y Y Y Y Y Y | BDAPPLN
Command | N_MAR003JQ |  |  |  |  | End Merch Analzer Rpt | 23:45 | . . . . Y Y . | BD APPLN
Command | AV_HOLIDAY |  |  |  |  | Send Dummy AV CTL-Holiday | 23:50 | Y Y Y Y Y . . | BDAPPLICAT
Command | ENDQPGMRSU |  |  |  |  | ENDQPGMRSU | 23:50 | . . . . Y . . | LEARN
Command | SYSBKUPIPL |  |  |  |  | 3rd Week Shutdown PTF&IPL | 23:50 | . . . . 3 . .
Command | AUT_OOSMIS |  |  |  |  | Track-Create Missing OOS | 23:55 | Y Y Y Y Y Y Y
Command | BPS_OK_NMO |  |  | EVERY |  | MON-Refresh BPS Alloc Qty | 0:00 | Y . . . . . .
Command | BPS_OK_NSA |  |  | EVERY |  | SAT-Refresh BPS Alloc Qty | 0:00 | . . . . . Y .
Command | BPS_OK_NSU |  |  | EVERY |  | SUN-Refresh BPS Alloc Qty | 0:00 | . . . . . . Y
Command | CH_MSGMON2 |  |  | EVERY |  | Check Job has MSGW-MON-#2 | 0:00 | Y . . . . . . | BD_APP
Command | CH_MSGSAT2 |  |  | EVERY |  | Check Job has MSGW-SAT-#2 | 0:00 | . . . . . Y . | BD_APP
Command | CH_MSGSUN2 |  |  | EVERY |  | Check Job has MSGW-SUN-#2 | 0:00 | . . . . . . Y | BD_APP
Command | DCA1_SLSD1 |  |  | EVERY |  | CA Sales Mon-Thur*10 min | 0:00 | Y Y Y Y . . .
Command | SUNDAY1 |  |  |  |  | Initiate sunday process | 23:59 | . . . . . Y .
Command | SYSMODCHK |  |  | EVERY |  | check IPL mode | 0:00 | 1 1 1 1 1 1 1
Command | RBNPOLL | HOLD |  | EVERY |  | H*Poll systems in network | 0:00 | Y Y Y Y Y . .
Command | SETOFF_BU |  |  |  | GroupMember | Set BDBACKUP to blank | 99:99 | . . . . . . . | BACKUP
Command | SETON_BU |  |  |  | GroupMember | Set BDBACKUP to active | 99:99 | . . . . . . . | BACKUP
Patrick Town Send Active FTP Records before Switch |  |  |  |  | As of Oct 19 2023
| FTP Definations Active Records |  |  | Scan Dirs Active Records |  | Auto Scan Active Records
FDNAME | FDDESC | FDSTAT | DRNAME | DRDESC | DRSTAT | SCNAME | SCDESC | SCSTAT
AGILENCEPT | Agilence-Transfer/LP/Archive | 1 | AGILEOUT | Send from /Transfer/LP/Out CHG525200 | 1 | BELLKSSCNN | Bell Kiosk Trans files Scan- every minut | 1
BELLACK | Azure Send Copy Ack CHG490772 | 1 | BELLACK | Azure Copy - Send ACK file CHG000490772 | 1 | BELLSHPSCN | Bell Ship Confirm files Scan | 1
BELLKIOGTN | Azure Copy Kiosk-Get every min | 1 | BELLPO | Azure Copy Server PO/PC file | 1 | BOOMERSCAN | Scan corpdmz - CA_report* for boomerang | 1
BELLPO | Azure Copy PO files | 1 | BELLPOR | Azure Copy Server PO Received | 1 | CBTUPSSCAN | CBT UPS Scan file CHG000615788 | 1
BELLPOR | Bell PO Received | 1 | BELLPRI | Azure Copy Server - Send Pricing file | 1 | DATASCNSCN | DATASCAN - SCAN OF REMOTE FOLDER INBOUND | 1
BELLPRI | Azure Copy - Send Price file | 1 | BELLTXN | Azure Copy-Trigger for TXN FileCHG490772 | 1 | DENISSCN | DENIS SUPREME GET REMOTE SCAN | 1
BELLSHPGET | Azure Copy - Ship Confirm get | 1 | BOOMERPUT | Send CA_WHITELIST.CSV to CORPDMZ | 1 | HUBRPTSCN | Hub Report-Scan files CHG000427866 | 1
BELLTXN | Azure SL-Trigger_TXN CHG490772 | 1 | CBTUPSPUT | CBT to UPS Put file CHG000615778 | 1 | LVINGJDASC | Scan files from Livingston CHG000513581 | 1
BOOMERGET | Get CA_report from corpdmz | 1 | CFSGET | CFS - Receive files (GET). | 1 | POSRICOHSC | POS scan Ricoh system CHG000507933 | 1
BOOMERPUT | Send CA_WHITELIST - CORPDMZ | 1 | CFSPUT | CFS - Send files (Put). | 1 | SLSEMPWSCN | SLSEMPWK Scan - labour hour files | 1
CBTUPSGET | CBT UPS Get CHG000615788 | 1 | DATASCNPUT | DATASCAN PUT | 1 | SOLBUILDSC | Solution Builder scan CHG000526328 | 1
CBTUPSPUT | CBT UPS Put CHG000615788 | 1 | DENISPUT | DENIS SUPREME PUT SEND FILES | 1 | STPLEXCHSC | Scan Staples Exchange CHG000477713 | 1
CFSGET | CFS GET | 1 | HBTPUT | Put HBT to lmftpnasv01 | 1 | VENDPERF | Vendor Performance | 1
CFSPUT | CFS PUT | 1 | ILMTFEEDPT | ILMT file feed CHG000509976 | 1
DATASCNGET | DATASCAN GET DEF FOR AUTO SCAN | 1 | POSRICOHAU | Change Authority on /pos/XMLRCH/Tmp file | 1
DATASCNPUT | DATASCAN PUT DEFINITION | 1 | SAPGPIN | SA PGP IN - decrypt and move. | 1
DENISGET | DENIS SUPREME GET DEF OPT 14 | 1 | SAPUT | Staples Advantage (CE -CA) Put files. | 1
DENISPUT | DENIS SUPREME SEND DEF OPT 5 | 1 | SAPUTE3 | Staples Advantage (JDA E3) Put files | 1
HBTPUT | Put HBT to lmftpnasv01 | 1 | SAPUTPGP | Staples Advantage (CE-CA) Put PGP files. | 1
HUBRPTGET | Hub Report-Get files CHG435517 | 1 | SLSEMPW | SLSEMPW - Process Inbound files | 1
ILMTFEEDPT | ILMT file feed CHG000509976 | 1 | SPPUTNEW | Staples Partners push | 1
LVINGJDAGT | Get from Livingston CHG513581 | 1 | STGPSEND | Storage Pipe FTP trans Send file | 1
POSRICOHGT | POS from Ricoh CHG000507933 | 1 | STGPSSHAUT | Chance Authority /pos/XMLCLD/Tmp files | 1
SAGETSCN | Staples Advantage - Get files | 1 | XRXPUT | Push files from xeroxput to Xerox | 1
SAPUT | Staples Advantage Put. | 1
SAPUTE3 | SA JDA E3 FTP TO FTP SERVER | 1
SLSEMPWGET | SLSEMPWGET - labour hour | 1
SOLBUILDGT | SolBuilder get CHG000526328 | 1
SPPUTNEW | sppytnew | 1
STPLEXCHGT | Get from StaplesEx CHG00047771 | 1
VENDPERF | Vendor Peformance | 1
XRXPUT | Send files to Xerox | 1

## P3 BUSDEPHA SHUTDOWN SWITCHBACK
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
|  | 5:30AM |  |  | BUSDEPHA | Use HMC to connect in QCTL susbsystem.
[5 empty] | BUSDEPHA | Sign on using QSECOFR id
[5 empty] | BUSDEPHA | Type WRKJOBQ and ensure that no jobs are waiting to be run from all job queues.
[5 empty] | BUSDEPHA | Type WRKACTJOB to check if no jobs are running in the following batch subsystems: BRMSSBS, DCDIRECT, OPERATIONS, QBATCH, QBATCHE3, QBSDI, QWEEKEND, SYSMGMT
[5 empty] | BUSDEPHA | ADDLIBLE SECMANISH
[5 empty] | BUSDEPHA | Submit DRSHUTDOWN as follows to shutdown the system in a normal order.
[5 empty] | BUSDEPHA | SBMJOB CMD(CALL PGM(SECMANISH/DRSHUTDOWN)) JOB(DRSHUTDOWN) JOBQ(QCTL) LOGCLPGM(*YES) HOLD(*YES)
[5 empty] | BUSDEPHA | if ready to SHUTDOWN, release this job from QCTL jobq
[5 empty] | BUSDEPHA | Type ENDTCPIFC INTNETADR('10.19.240.76') to end the user connection TCP interface. This is to ensure that no users can sign on to BUSDEP using BUSDEP DNS name and to prevent any FTPs in and out of the box. |  |  | User connection Interface
[5 empty] | BUSDEPHA | Type RBTAUTOSTR AUTOSTART(*NO) so that RBTSLEEPER sbs will NOT start Robot Scheduler. On DR system, only Alert and Console is needed. |  |  | BUSDEPHA is going to be original DR system
[5 empty] | BUSDEPHA | Varry off all APPC cntl first for APPN control point to be able to change WRKCFGSTS CFGTYPE(*CTL) CFGD(*APPC) |  |  | WRKCFGSTS CFGTYPE(*CTL) CFGD(*APPC)
[5 empty] | BUSDEPHA | Type CHGNETA LCLCPNAME(BUSDEPHA) LCLLOCNAME(BUSDEPHA) Change local control point and local location name to BUSDEPHA |  |  | This is needed for SNA and APPC controllers
[5 empty] | BUSDEPHA | Change QSTRUPPGM system value to MIDRANGE/QSTRUPHA. This is to run same start up program as BUSDEPHA after role swap.
[5 empty] | BUSDEPHA | Type CHGIPLA STRTCP(*YES) - this is needed to start tcp after IPL on DR box since not managed by Robot job SYSBKUP2. |  |  | Original setting of BUSDEPHA
[5 empty] | BUSDEPHA | Release jobs from WRKJOBSCDE as follows:
[5 empty] | BUSDEPHA | Type WRKSBS and ensure that only the following subsystems are running.
RBTSLEEPER sbs is down due to MIMIX replicaiton tasks.Only RBT Alert and Console can be up
[5 empty] | BUSDEPHA | End AUD300DP job from QCTL before switch

## P3 BUSDEP SHUTDOWN SWITCHBACK
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
|  | 5:30AM |  |  | BUSDEP | Use HMC to connect in QCTL susbsystem.
[5 empty] | BUSDEP | Sign on using QSECOFR id
[5 empty] | BUSDEP | Type HLDJOBSCDE JOB(*ALL) to hold all job schedule entries from native job scheduler.
[5 empty] | BUSDEP | Type WRKJOBQ and ensure that no jobs are waiting to be run from all job queues.
[5 empty] | BUSDEP | Type WRKACTJOB to check if no jobs are running in the following batch subsystems: BRMSSBS, DCDIRECT, OPERATIONS, QBATCH, QBATCHE3, QBSDI, QWEEKEND, SYSMGMT
[5 empty] | BUSDEP | ADDLIBLE SECMANISH
[5 empty] | BUSDEP | Submit DRSHUTDOWN as follows to shutdown the system in a normal order.
[5 empty] | BUSDEP | SBMJOB CMD(CALL PGM(SECMANISH/DRSHUTDOWN)) JOB(DRSHUTDOWN) JOBQ(QCTL) LOGCLPGM(*YES) HOLD(*YES)
if ready to SHUTDOWN, release this job from QCTL jobq
[5 empty] | BUSDEP | Type WRKSBS and ensure that only the following subsystems are running. MIMIXSBS, QCTL, QSERVER, QSYSWRK
[5 empty] | BUSDEP | Type ENDTCPIFC INTNETADR('10.19.244.76') to end the user connection TCP interface. This is to ensure that no users can sign on to BUSDEP using BUSDEP DNS name and to prevent any FTPs in and out of the box. |  |  | User ip
[5 empty] | BUSDEP | Ensure that only below SBS running

## P3 DNS AND NETWORK SWITCHBACK
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
[5 empty] | Network | Contact Staples Network Support team to make DNS changes. DNS BUSDEP, BUSDEP.staplescan.com and BUSDEP.staples.com to point to BUSDEP ip 10.19.244.76.
[5 empty] | Network | Contact Staples AZURE team to make DNS changes for BUSDEP in AZURE prod environment to point to BUSDEP ip 10.19.244.76.
[5 empty] | MAR4DEV1/BUSDEP/BUSDEPHA | Flip BUSDEP ip to point to original BUSDEP IP 10.19.244.76, and BUSDEPHA to point to original BUSDEPHA IP 10.19.240.76 in the local host table entries.( CFGTCP option 10 ) | This is needed for all FTP to BUSDEP, SNADS, and IMPLEMENTOR code promotions
[5 empty] | BUSDEPHA | Chagne Domain Name name to BUSDEPHA from BUSDEP in CFGTCP option 12 ( if needed )
[5 empty] | BUSDEP | Chagne Domain Name name to BUSDEP from BUSDEPHA in CFGTCP option 12 ( if needed )

## P3 BUSDEP STARTUP SWITCHBACK
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
|  | 4:30AM |  | 1 | BUSDEP | Use MARKHAM HMC to connect in QCTL susbsystem.
|  |  |  | 10 | BUSDEP | Update system name as BUSDEP in ROBOT as follows: ROBOTLIB/RBTSWAPSYS SOURCESYS(BUSDEPHA) TARGETSYS(BUSDEP) | TGT system name should be same on where you run this command | Midrange
|  |  |  | 1 | BUSDEP | Type STRTCPIFC INTNETADR('10.19.244.76') to start the user connection TCP interface.
|  |  |  | 1 | BUSDEP | Varry off all APPC cntl first for APPN control point to be able to change WRKCFGSTS CFGTYPE(*CTL) CFGD(*APPC)
|  |  |  | 1 | BUSDEP | Type CHGNETA LCLCPNAME(BUSDEP) LCLLOCNAME(BUSDEP) Change local control point and local location name to BUSDEP |  |  | This is needed for SNA and APPC controllers
|  |  |  | 1 | BUSDEP | Type RBTAUTOSTR AUTOSTART(*NO) so that RBTSLEEPER sbs will NOT start Robot Scheduer | This is needed to hold the regular schedule jobs before missed jobs to be run
[5 empty] | BUSDEP | Confirm that ROBOT Scheduler is INACTIVE in RBO | Very Important that no jobs start running at this point on BUSDEP original system
· Type RBO
· Take option 1 Robot Schedule
· Take option 3 Control Menu
· Check the status at top right corner should be INACTIVE
|  |  | 441am | 5 | BUSDEP | Hold all Patrick Townsend FTP jobs: | Type SQL statement, press Enter. |  | HOLD PT
[6 empty] | · Sign on as QSECOFR | > UPDATE ALLFTM100/ANFTPD set FDSTAT = '2' |  | HOLD PT
[6 empty] | · Type STRSQL | 135 rows updated in ANFTPD in ALLFTM100. |  | HOLD PT
[6 empty] | · UPDATE ALLFTM100/ANFTPD set FDSTAT = '2' | > UPDATE ALLFTM100/ANDIRS SET DRSTAT= '2' |  | HOLD PT
[6 empty] | · UPDATE ALLFTM100/ANDIRS SET DRSTAT= '2' | 75 rows updated in ANDIRS in ALLFTM100. | Not needed | HOLD PT
[6 empty] | · UPDATE ALLFTM100/ANSCAN set SCSTAT = '2' | > UPDATE ALLFTM100/ANSCAN set SCSTAT = '2' |  | HOLD PT
[6 empty] | · Verify that all PT FTP definitions, Scan Directories/File Actions and Auto Scan records are in Inactive status. | 45 rows updated in ANSCAN in ALLFTM100. |  | HOLD PT
|  |  |  | 1 | BUSDEP | Type WRKJOBQ and check if all the job queues in Release status. | Completed
|  |  |  | 1 | BUSDEP | Change QSTRUPPGM system value to ITTOOLS/QSTRUP. This is to run same start up program as BUSDEP after role swap. | Completed
|  |  |  | 1 | BUSDEP | Comment out STRSBS QINTER command in ITTOOLS/STARTINTER file.
|  |  |  | 1 | BUSDEP | Comment out STRSBS QPGMR command in ITTOOLS/STARTBATCH file.
|  |  |  | 5 | BUSDEP | Change Or Confirm SMTP settings in Patrick Townsend, IMAIL and ROBOT Alert as follows:
PATRICK TOWNSEND FTP (ALLIANCE FTP MANAGER)
· ADDLIBLE ALLFTM100
· GO AMMAIN
· Option 31 Email menu
· Option 1 SNMP email menu
· Option 10 Application settings
· Change local host name to BUSDEP
This value is replicated and BUSDEPHA needs to be changed to BUSDEP
Completed
IMAIL
· Addlible iMail
· Go IMAIL
· Option 1
· Change Domain Name to Staplescan.com
· Press F10 to save
Completed. EMAIL test worked as is using BUSDEP name from HA box.
ROBOT ALERT
· ADDLIBLE ROBOTLIB
· ADDLIBLE RBTALRLIB
· ADDLIBLE RBTCONLIB
· Type RBO
· Take option 2 Robot Alert
· Take option 3 Directory Menu
· Take Option 1 Vendor Maintenance Menu
· Take Option 2 Maintain Existing Vendors
· Take Option 1 to Select SPLSEMAIL
· Change SMTP Host to SCASMTPINT.STAPLESCAN.COM
Completed
|  |  | 448 | 10 | BUSDEP | On BUSDEP, update hardcoded local IP in SUNRISE, SUNBEAM, MAR4DEV1, GALAXY APPC controllers to point to 10.19.244.76. (WRKCFGSTS, Vary off, Change IP, Vary On)
|  |  | 448 |  | SUNRISE, SUNBEAM, MAR4DEV1 and GALAXY | On SUNRISE, SUNBEAM, MAR4DEV1 and GALAXY, update hardcoded remote IP in BUSDEP APPC controller to point to 10.19.244.76 (WRKCFGSTS, Vary off, Change IP, Vary On) | Call iseries on call support at 508-253-3314
|  |  |  | 10 | BUSDEP | Start system as follow:
· Sign on as QSECOFR.
[6 empty] | · STRSBS QCTL (This should be running already). This will start QSYSWRK subsystem and will run STRTCP command | Already running
[6 empty] | · STRSBS QSERVER | Already running
[6 empty] | · STRSBS QUSRWRK | Already running
ADDLIBLE SECMANISH
[6 empty] | Submit DRSTARTSYS as follows to start the system in a normal order. | CALL RBT103 was commented in ITTOOLS/STRRBT CLto not start RBT Scheduler.
|  |  | 5:00AM |  |  | SBMJOB CMD(CALL PGM(SECMANISH/DRSTARTSYS)) JOB(DRSTARTSYS) JOBQ(QCTL) LOGCLPGM(*YES) HOLD(*YES) JOBD(QGPL/QDFTJOBD) USER(MISOPR) | STRSBS RBTSLEEPER sbs will start all robot products accept Robot scheduler
if ready to START SYSTEM, release this job from QCTL jobq
|  |  |  | 1 | BUSDEP | Type WRKSBS and verify that the following subsystems are running except QINTER and QPGMR subsystems from the list below.
|  |  |  | 1 | BUSDEP | Type WRKACTJOB SBS(QHTTPSVR) and verify that the following HTTP and IWS jobs are running. These are needed for IBM Web services.
|  |  |  | 1 | BUSDEP | Type WRKACTJOB SBS(QCMN) and verify that the E3COMSERV job is running. These are needed for E3 AWR and ASR application.
|  |  |  | 1 | BUSDEP | Type WRKACTJOB SBS(QUSRWRK) and verify that the M3005 and D3005 jobs are running. These are used by IMPLEMENTER receiver.
|  |  |  | 1 | BUSDEP | Type WRKACTJOB SBS(ZMHTTPSRV) and verify that the AS2 jobs are running. These are needed by AS2 application.
Run AS2RESTDP if below jobs are not started.
|  |  |  | 1 | BUSDEP | Type WRKACTJOB and verify that below jobs are running in ZPSE, ZPSSMON and ZALOG subsystems. These are needed by NetIQ Security application.
AS2 Proxi job did not start and had to DO on AS2RESETDP job from Robot
|  |  |  | 1 | BUSDEP | Type WRKACTJOB SBS(RBTSLEEPER) and verify that below jobs are running These are needed by ROBOT products.
|  |  |  | 1 | BUSDEP | Type WRKACTJOB SBS(ALFTM100) and verify that below jobs are running These are needed by Patrick Townsend FTP product.
|  |  |  | 1 | BUSDEP | Type CFGTCP and take option 1 to verify that the following interfaces are active.
5:16AM
|  |  |  | 1 | BUSDEP | Release all the Store Printer Output queues ( Pnnnnnnn )
|  |  |  | 1 | BUSDEP | Add supplememtal groups PROD and EMGPRO to developers id so they can do validations
|  |  |  | 1 | MIDRANGE | Ensure that enough tapes are loaded in MARKHAM LOCATION TAPE library that can accommodate daily and weekly backups from BUSDEPHA
|  |  |  | 5 | BUSDEP | Hold jobs from WRKJOBSCDE as follows as backups and BRMS jobs runs from Robot on BUSDEP in DR mode.
5:30AM
|  | Total |  | 66 | MIN
Note on G16: Tamakuwala, Manish: > UPDATE ALLFTM100/ANFTPD set FDSTAT = '2' 129 rows updated in ANFTPD in ALLFTM100. > UPDATE ALLFTM100/ANDIRS SET DRSTAT='2' 72 rows updated in ANDIRS in ALLFTM100. > UPDATE ALLFTM100/ANSCAN set SCSTAT = '2' 42 rows updated in ANSCAN in ALLFTM100. Remove trailing spaces to avoid Invaid Token

## P3 BUSDEP VALIDATION SWITCHBACK
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
1 | Sunday | 8:00AM | 9:00AM |  |  | Start POS FTPs services for a sample test store only ( 49 or 91 or 448 stores) | Before GO Validation | Alain Miron / Joyal | Alain / Joyal to confirm stores
2 | Sunday | 8:00AM | 9:00AM |  | BUSDEP | Add PROD and EMGPROG supplimentry groups to Developers profiles for production access to test | Before GO Validation | Manish
Run CL SECMANISH/DRGRTAUTH
3 |  |  |  |  | BUSDEP | Vendor Software Verification
4 | [5 empty] | · Verify Client Access / ACS functions |  | Manish
5 | [5 empty] | · Verify DBU functions |  | Masoud
6 | [5 empty] | · Verify IMAIL functions |  | Masoud/Manish
7 | Sunday | 8:00AM | 9:00AM |  |  | · Verify MARKMAGIC to be able to print Forms/labels | Before GO Validation | Masoud
8 | [5 empty] | · Verify TAATOOL functions |  | Manish
9 | [5 empty] | · Verify ROBOT Schedule, Alert and Robot Console functions |  | Manish
10 | [5 empty] | · Verify IMPLEMENTER functions to promote code from MAR4DEV1 |  | Masoud/Manish
11 |  |  | ` |  |  | · Verify NetIQ Pentasafe functions |  | Manish
12 | [5 empty] | · Verify OpenText Liaison functions (Peter to test) |  | Peter / Stephen
13 | [5 empty] | · Verify Gentran functions (Peter to test) |  | Peter / Stephen
14 | [5 empty] | · Verify Patrick TownSend functions (with Dennis and Supreem, Martin is the contact ) |  | Manish
15 |  |  |  |  | BUSDEP | Network Verification
16 | Sunday | 8:00AM | 9:00AM |  |  | · Verify store connection (store #49, 91 and 448) from Bell and TELUS Network as well as checkpoint / ISR routers | Before GO Validation | Wayne / Helpdesk / Bart / Haran
17 | [5 empty] | Store 49, Telus MPLS (Montreal) |  | Mustapha Medani GM 438-832-1509
18 | [5 empty] | Store 91, Bell MPLS (Nova Scotia) |  | Leanne Candelora at 902 565-1652 (cell #)
19 | [5 empty] | Store 448, Broadband (Toronto) |  | Joshua Cere Service mgr 905 246 2141 Frank Caruso General Manager Store 448 Frank Caruso General Manager Store 448
20 | [5 empty] | · Verify FC99 and FC351 FC connection on Monday due to FC not available on Weekends |  | Wayne / FC users | Patrick to follow up with FC99 and FC 351 for users, NOT required, FC not working on weekend
21 | [5 empty] | · Verify Mini-DDC (317) connection ( Converted to TCPIP printing from SNADS ) |  | Patrick | find a resource from 317
22 | [5 empty] | · Verify Client Access and Citrix connection using DRTESTxx sessions. Use 3 stores with different networks |  | Manish / Masoud / HelpDesk /Wayne | Haran to provide Helpdesk resource
23 | Sunday | 8:00AM | 9:00AM |  |  | · Verify store scanner functions (store #49,91,448). QPGMR or BUSDEP/SCANNERS SBS needs to be started for test | Before GO Validation | Masoud / Store Associate / Help Desk | Haran to provide Helpdesk resource, need stores that are opened. Need to get east coast stores for testing. Manish to turn on QPGMR SBS then turn off after test | Mukesh
24 | [5 empty] | · Verify home office and VPN connections |  | Wayne / Bart
25 |  |  |  |  | BUSDEP | JDA Basic Functions
26 | [5 empty] | · Verify BRMS Backup functions |  | Manish / Midrange
27 | Sunday | 8:00AM | 9:00AM |  |  | · Verify DDM, APPC, ICF file connections with Sunrise and Sunbeam. Need a CR for iSeries Engineering team support | Before GO Validation | Manish / Patrick / iSeries Team US | iSeries team US configure first, then Patrick's team to test
28 | [5 empty] | · Verify Emmergency profile check out tool works |  | Masoud / Manish
29 | [5 empty] | Verify labour hours entered on BUSDEP for store 462 replicated to BUSDEPHA |  | Stanley followup
30 | Sunday | 8:00AM | 9:00AM |  |  | · Verify Printer testing to store xxx | Before GO Validation | Masoud | Need to find a store that will be opened, tie to store scanner test (use the same store #)
31 | [5 empty] | · Verify Printer testing at home office |  | Masoud
32 | [5 empty] | · Verify FTP using port 21 (Various Contacts) |  | Masoud
33 | [5 empty] | · Verify RightFax Connection : Move a test fax spool file called REPORT from SECMANISH outputq to QGPL/PULSE output queue. Call MIKE Gee to confirm if he received the FAX. |  | Manish / Masoud / Michael Gee (US)
34 |  |  |  |  | BUSDEP | JDA Critical Functions
35 | [5 empty] | · Verify JDA MMS basic functions |  | Masoud / Zoya
36 | [5 empty] | · Verify User JDA MMS Menu function via Navigating the JDA MMS menu, access different screens without making any updates. |  | Masoud / Zoya | For Business Role Swap, needs Finance and Merch
37 | [5 empty] | Verify STRPATHR function ( this should work on BUSDEP ) |  | Manish
38 | [5 empty] | · Verify AS2 Proxy sever connection |  | Peter / Stephen
39 | [5 empty] | · Verify EDI connection |  | Peter / Stephen
40 | [5 empty] | · send 997 to external, one through AS2, one thrugh VAN
41 | [5 empty] | · Verify JDA E3 ASR/AWR connection |  | Curtis / Nasser / Manish
42 | Sunday | 8:00AM | 9:00AM |  |  | · Verify Price File FTP to CPC via Patrick Townsend. | Before GO Validation | Manish / Jun Ling / Carol | use dummy file to test
43 | [5 empty] | Put the trigger file in IFS using a menu option on MENIOD optin 26 | Before GO Validation
44 | [5 empty] | From PT, Run the BELLPRI ftp defination and Scan Dir to ACTIVE so file will be picked up and FTPed | Before GO Validation
45 | [5 empty] | · Verify Salesforce order processing |  | Masoud / Ken
46 | Sunday |  |  |  |  | · Verify FTP from BUSDEP to Access Via using Store 448 as test store, VIABATC, Uses scanner to request a print signage |  | Sonja / Rachael / Stanley
47 | Sunday | 8:00AM | 9:00AM |  |  | · Verify BOPIS inventory count / MLS Webservices | Before GO Validation | Masoud / Manish / Stuti / Jitendra (US Team) | Manish to call US team if any issues
48 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Kiosk Order ( Solution Builder ) | Before GO Validation | Carol / Ramya
49 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Online SalesPosting, Return and Refund (via EAI) | Before GO Validation | Ramya // Anson | Need to stop actual hellboy posting during roleswap
50 | Sunday | 8:00AM | 9:00AM |  |  | Ding / Anson will post an open transaction to validate the connection | Before GO Validation
51 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Store Return, Refund (via EAI) , | Before GO Validation | Ramya / Anson
52 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - BINQTY (from BUSDEP to POS) , | Before GO Validation | Yajun / Ramya
53 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - INVAUD (from BUSDEP to CMIS) | Before GO Validation | Yajun / Ramya
54 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - ECP Sync (from ETS to Busdep) | Before GO Validation | Yajun / Ramya
55 | Sunday | 8:00AM | 9:00AM |  |  | http://busdep:10021/web/services/ECPCaseStoreUpdService/ECPCaseStoreUpd | Before GO Validation
| Sunday | 8:00AM | 9:00AM |  |  | Verify ODBC connection from Sequel 16 to BUSDEP server | Before GO Validation | Kevin
| Sunday | 8:00AM | 9:00AM |  |  | Verify ODBC connection from Sequel 05 to BUSDEP server | Before GO Validation | Kevin
[6 empty] | Verify file generated and FTPed to SVS server ( depends on ECP IWS working ) | Before GO Validation | Kevin / Stanley
56 | Sunday | 8:00AM | 9:00AM |  |  | Verify IWS Web Service - HBT ( Host Based Tax ) ( via EAI ) | Before GO Validation | Ramya via Postman | Need resource from Alain
57 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Inventory Lookup (for CPC), | Before GO Validation | Ramya via Postman | similar to step 4.17 for same resource to do
58 | Sunday | 8:00AM | 9:00AM |  |  | http://BUSDEP.staples.com:8088/ws/WSIVS10/OnHand/15/934103/0/0 | Before GO Validation
59 | Sunday | 8:00AM | 9:00AM |  |  | · Verify IWS Web Service - Inventory Lookup (for POS), Can be tested from Postman | Before GO Validation | Alain / Haran / Joyal | Need resource from Alain, Chris to follow up with Tong
60 | Sunday | 8:00AM | 9:00AM |  |  | Verify Manhattan to Busdep: Resend: Item, Vendor, Store, Order, PO, ASN | Before GO Validation | Zoya
61 | Sunday | 8:00AM | 9:00AM |  |  | Verufy Busdep to Manhattan: Resend: Receipt, Verification, ShipConfirm, Adjustment, InventorySynch | Before GO Validation | Zoya
62 | Sunday | 8:00AM | 9:00AM |  |  | · Verify POS connectivity from Store (Price Download), Price file to be deleted after test is over | Before GO Validation | Masoud / Joyal
63 | Sunday | 8:00AM | 9:00AM |  |  | · Verify POS connectivity from Store (Sales Upload), store # 49,91,448) to be used | Before GO Validation | Masoud / Joyal
64 | [5 empty] | Test DATASCAN FTP |  | Manish
65 | [5 empty] | Test DenisSupreme |  | Manish
66 |  |  |  |  | BUSDEP | Receive Business sign off on validation test |  | Edward / Manish

## P3 BUSDEP GO LIVE
Step # | Start Date | Estimated Start Time | Estimated End Time | Duration | System | Activity | Status | Responsibility | Comments
[5 empty] | BUSDEP | Communicate to Busines when system will be available to all stores and home office users
[5 empty] | BUSDEP | Start all POS FTPs services |  | Alain Miron / Joyal | 905-716-3377
[5 empty] | BUSDEP | Start all FC Sales Feed |  | Devop team / Jerry
[5 empty] | BUSDEP | Start all Salesforce orders feed |  | Ken / Emma
[5 empty] | BUSDEP | Start all Copy and Print orders |  | Bonny / Carol
[5 empty] | BUSDEP | Start Zuora Transactions/ Allstate / TSS |  | Kevin Liang (Bo) / Jamie
[5 empty] | BUSDEP | Start Inventory Sync from Manhanton WMS |  | Karthik / Edward to send email
[5 empty] | BUSDEP | Use MARKHAM HMC to connect in QCTL susbsystem.
[5 empty] | BUSDEP | Allow all store users and home office users to sign on to BUSDEP
· Type STRSBS QINTER
· Type STRSBS QPGMR
· Type WRKACTJOB SBS(QINTER) and WRKACTJOB SBS(QPGMR) to verify users sessions.
[5 empty] | BUSDEP | Change the status of Patrick Town send jobs to ACTIVE to their actual matching status as follows: |  | Manish | P0 PREPERATION SWITCHBACK listing to be used for Business Role Swap
[6 empty] | Sign on as QSECOFR |  |  | This CL will run a SQL query from SECMANISH/QSQLSRC(DRUPDPTSTS)
[6 empty] | Run a CL using CALL SECMANISH/DRUPDPTSTS |  |  | Ensure that QSQLSRC(DRUPDPTSTS) has latest PT active records from P3 Prepration Switchback TAB
Take option 7 to start on all AUTO scan active jobs to start
Check in PT that all status are active for FTP Definations, SCAN dir and Auto Scan
[5 empty] | BUSDEP | Run VRINCOME manually. This jobs is dependant job for VRM_INVOIC job below. |  | Nasser | After completion of VRINCOME, remove VRM038CLC from MMBUSLIB. This version has commented code that Nasser changed before DR role swap.
[5 empty] | BUSDEP | Run VRM jobs CCL_WKLY, VRM_WKRPT, VRM_INVOIC and VRM_WKND that were held by Nasser on BUSDEPHA before roleswap. |  | Nasser
[5 empty] | BUSDEP | Run all jobs that were submitted from Robot that were missed on BUSDEP between 3AM to GO-LIVE. |  | Stanley / Nasser | Stanley has steps to run all job based on dependency
[5 empty] | BUSDEP | Make ROBOTScheduler ACTIVE in RBO to start running all jobs as per normal schedule |  |  | All jobs should have same status as BUSDEPHA due to replication on ROBOT libs
· Type RBO
· Take option 1 Robot Schedule
· Take option 3 Control Menu
· Take option 1 Start Robot
· Check the status at top right corner should be ACTIVE
[5 empty] | BUSDEP | Remove comments from STRSBS QINTER command in ITTOOLS/STARTNTER file.
[5 empty] | BUSDEP | Remove comment from STRSBS QPGMR command in ITTOOLS/STARTBATCH file.
[5 empty] | BUSDEP | Release SUNDAY2 job since it needs to go back to normal schedule
[5 empty] | BUSDEP | Remove comments from SUNDAY1 job for job 312 PRODSUDP submission since it needs to go back to normal schedule
[5 empty] | BUSDEP | Release SYSSTRSBS job since it needs to go back to normal schedule
[5 empty] | BUSDEP | Type RBTAUTOSTR AUTOSTART(*YES) so that RBTSLEEPER sbs start Robot Scheduler in a normal way |  |  | BUSDEP is a production system from here.
[5 empty] | BUSDEP | Update system name parameter for EMG Profile Inquiry MENIOD option 14 as follows: (1) CALL A, MENU MENMEN Option 1, Enter MENIOD and press Enter twice, then enter menu option to maintain to 14, change the system name to BUSDEP in Parameter 1 field. Press Enter to save.
[5 empty] | BUSDEP | Type CHGIPLA STRTCP(*NO) - this is NOT needed on production box since managed by Robot job SYSBKUP2. |  |  | Original setting of BUSDEP
[5 empty] | BUSDEPHA | Start RBT Alert and Console. ( NO Rbt Schedule should be started due to direct replication )
[5 empty] | BUSDEP | Remove PROD and EMGPROD groups from developers/testers profiles
Run CL SECMANISH/DRRVKAUTH
At this point,
· All store and home office users are able to sign on and update or send/receive files
· All ROBOT jobs are active to run at their scheduled date and time
· Patrick Town send jobs are active to run at their scheduled time
· All BRMS backup jobs to run as scheduled
END OF DR FAILOVER EXERCISE !!
to be removed later on after next role swap
[5 empty] | BUSDEP | Run CPC_TXNPCK trigger job for Carol/Jun Ling FTPs |  |  | This is just a priority job to run before running all jobs via Script
[5 empty] | BUSDEP | Upload DOJOBS file from the DOJOBS Upload Tab in this Excel to SECMANISH library on BUSDEP
[5 empty] | BUSDEP | Update DOJOBS file to inclue only jobs to run upto the time of the call to DRDOJOBS ( exampl 2AM to 9AM during the outage at that timestamp )
[5 empty] | BUSDEP | Run SECMANISH/DRDOJOBS cl run all jobs that were missed on BUSDEPHA during role swap. These jobs were identified in P0 Preperation Tab.
[5 empty] | BUSDEP | Run all E3xxxxxxxx jobs as follows: (1) E3_FREEZE to run as normal from DOJOBS list (2) E3_DAYEND to run after 15 mins of E3_FREEZE run (3) E3TWAIT to run after 15 mins of E3_DAYEND run |  | Stanley / Nasser
[5 empty] | BUSDEP | Run MOOSE3_WP job after all E3xxxxxxx jobs finished in above step. |  | Stanley / Nasser
[5 empty] | BUSDEP | Run reactive job RPL_SUGQTY job that was cancelled on BUSDEP before role swap |  | Stanley / Nasser
[5 empty] | BUSDEP | Run Call SECMANISH/DRRBTOVRR cl to release all ROBOT scheduled jobs to their actual status. |  |  | Ensure that SECMANISH/RBTOVRRIDE file exist from P0 Preperation for Switch Tab
[5 empty] | BUSDEP | After 12:00 MIDNIGHT on Sunday, Set Auto Run option to Y in Robot Scheduler as follows |  |  | This value to be only changed after DR test is complete and ready to resume with next day operation after midnight
· Type RBO
· Take option 1 Robot Schedule
· Take option 4 System Setup menu
· Take option 1 General System Defaults
· Change Run Auto work at Startup of ROBOT to value Y
· This option will ensure that no jobs will run that were missed after 12 midnight due to outage on BUSDEP during the role swap.

## Contact List and Communication
Company | Name (First/Last) | Category 1 | Role on Project | Email | Cell Phone #
MidRange | Phil Scharf | Sales | Account Manager Services | Pscharf@midrange.ca | 416-561-9362
MidRange | Patricia Dahmer | PMO | Project Manager | Pdahmer@midrange.ca | 519-716-9989
MidRange | Colin Siu | PMO | Project Coordinator | Csiu@midrange.ca | 416-707-1268
MidRange | Jason Blair | Technical | Mimix Logical Replication | Jblair@midrange.ca | 647-876-1212
MidRange | Sergey Shidlovsky | Technical | Mimix Logical Replication | Sshidlovsky@midrange.ca | 416-992-1858 | working or on call during April 17 Role Swap
MidRange | Kal Sidhu | Technical | Mimix Logical Replication | Ksidhu@midrange.ca | 416-995-6504
MidRange | Loretta Kotska | Technical | IBM I / BRMS | Lkotska@midrange.ca | 416-992-4906
MidRange | Cam Kerr | Technical | Data Centre | Ckerr@midrange.ca | 416-992-5310
MidRange | Ryan Tian | Technical | Network | RTian@midrange.ca | 416-894-2468
MidRange | Jeff Mowbray | Management | Managed Services | JMowbray@midrange.ca | 647-453-3000
MidRange | Bill Dong | Team Lead | Managed Services | bdong@midrange.ca | 416-992-5309
MidRange | Tim Lalonde | Management | Executive Sponsor | tlalonde@midrange.ca | 705 282-7329
Staples Canada | Edward Liu | Director |  | edward.liu@staples.ca | 416-998-3599
Staples Canada | Nasser Jalavand | Manager |  | nasser.jalavand@staples.ca | 416-729-2258
Staples Canada | Masoud Karampour |  |  | masoud.karampour@staples.ca | 416-994-7412
Staples Canada | Manish Tamakuwala |  |  | manish.tamakuwala@staples.ca | 647-985-4050
Staples Canada | Wayne Glen |  |  | wayne.glen@staples.ca | 416-809-3549
Staples Canada | Jeff Michea |  |  | jeff.michea@staples.ca | 416-770-2528
Staples Canada | Stanley Woo | Manager |  | stanley.woo@staples.ca | 416-735-4666
Staples Canada | Peter Lau |  |  | homanpeter.lau@staples.ca | 647-271-0927
Staples Canada | Patrick Shen | Manger |  | patrick.shen@staples.ca | 416-996-8505
Staples Canada | Rachael Rajaratnam |  |  | Rachael.Rajaratnam@staples.ca | 647-938-8126
Staples Canada | Stuti Taghavan |  | MLS India Team | Stuti.Raghavan@Staples.com | +91 – 9838917851
Staples Canada | Curtis Rap | Manager | Merch Ops Support |  | 647-916-5751
Staples Canada | Bart |  | Network | bart.trentadue@staples.ca | 416-735-5863
Staples Canada | Zoya Meyer |  |  | Zoya.meyer@staples.ca | 647-515-9008
Staples Canada | Ramya Alex |  | App Support | ramyaaline.alex@staples.ca | 437- 228- 5017
Staples Canada | Jerry Wang |  | DNS Azure/Copu and Prnt | jerry.wang@staples.ca | 416-908-3010
Staples Canada | Jamie Bowles | Manager |  | Jamie.Bowles@Staples.com | 416-986-2678
Staples Canada | Yaroslav Kyslov |  |  | Yaroslav.Kyslov@staples.ca | 647-284-0591
Staples Canada | Mukesh Vasi |  | Help Desk | Mukesh.Vashi@staples.ca | 647-526-5040
Staples Canada | Haran Viv | Manager |  | Haran.Viv@staples.ca | 416-890-1504
Staples Canada | Jiang Hong (Steve) |  |  | Hong.Jiang@staples.ca | 905-330-2708
Staples Canada | Grace Hua |  |  | Grace.Hu@Staples.ca | 905-787-1661
Staples Canada | Kadir Chauhan |  | Sunrise and Sunbeam | MohammedKadir.Chauhan@staples.ca | (647) 550 -7861
Staples Canada | Carol Huynh |  | Copy and Print | Carol.Huynh@staples.ca
Staples Canada | Tong Ciu |  | POS | Tong.Cui@staples.ca
Staples Canada | Anson Lam |  |  | Anson.Lam@staples.ca | 416-666-0336
Staples Canada | Jerry Wang |  | Azure FW/DNS changes | Jerry.Wang@staples.ca | 416-908-3010
Staples Canada | Shayan Ahmad |  | EAI Testing / FC Feed Start and Stop | Shayan.Ahmad@staples.ca | 416 275-5729
Staples Canada | Kevin(Bo) Liang |  | Zuora Transactions Start and Stop | Kevin.Liang@staples.ca | 647-291-1650
Staples Canada | Alain Miron | Manager | POS Start and Stop | Alain.Miron@staples.ca | 905-716-3377
Staples Canada | Jun Ling |  | Copy and Print | JunLing.Zhao@staples.ca | 647-201-7880
Staples Canada | Bonny Desai | Manager | Copy and Print | Bonny.Desai@staples.ca | 416.528.6660
Staples US | iSeries On Call |  | Sunrise and Sunbeam APPC IP changes | On call support Number to call | 508-253-3314
Staples US | Michael Kobos | Manager |  |  | 978-618-6078
Airmiles | Adrain Carvalho ( Airmiles Contact) |  |  | acarvalho@loyalty.com | 416-464-6174

## ALL SUNDAY JOBS NEW
ROBOT_JOB_NUMBER | ROBOT_JOB_NAME | ROBOT_JOB_DESC | SCHED_RUN_TIME_1 | ROBOT_JOB_TYPE | Action to take | SCHED_OVRRD | OS_JOB_DATE_VALUE | OS_JOB_DATE_CODE | OS_JOB_USER | ROBOT_JOB_NOTES | CALENDAR_NAME | DATE_OBJECT_NAME | START_TIME | SAVE_TIME | SCHED_RUN_TIME_2 | SCHED_RUN_TIME_3 | SCHED_RUN_TIME_4 | SCHED_RUN_TIME_5 | SCHED_RUN_TIME_6 | SCHED_RUN_TIME_7 | SCHED_RUN_TIME_8 | RUN_FLAG_MON | RUN_FLAG_TUE | RUN_FLAG_WED | RUN_FLAG_THU | RUN_FLAG_FRI | RUN_FLAG_SAT | RUN_FLAG_SUN | DAYNO_DAY_1 | DAYNO_DAY_2 | DAYNO_DAY_3 | DAYNO_DAY_4 | DAYNO_DAY_TYPE | OS_JOB_ACGCDE | IS_GROUP_MEMBER | ENV_NAME | OS_JOB_SWITCHES | OS_JOB_INQMSGRPY | OS_JOBD_NAME | OS_JOBD_LIB_NAME | OS_OUTQ_NAME | OS_OUTQ_LIB_NAME | SPLF_COPIES | OS_JOB_OUTPTY | LIBRARY_LIST_NAME | SPLF_PRINT_TEXT | OS_JOBQ_NAME | OS_JOBQ_LIB_NAME | OS_JOB_JOBPTY | OS_MSGQ_NAME | OS_MSGQ_LIB_NAME | OS_JOB_CURLIB | ADV_SCHED_CODE | SCHED_OVRRD_SAVED | ADV_SCHED_USED | RUN_ON_NONWORK_DAY | USE_REPORT_DIST | JOB_IS_REACTIVE | INDAY_START_DATE | EVERY_INTERVAL | INDAY_INTERVAL | INDAY_DAY_TYPE | AT_POOL_SIZE | ALERT_DEVICE_NAME | EVERY_RANGE_START | EVERY_RANGE_END | HIST_RETENTION | SYSTEM_CREATED_ON | TEMPORARY_JOB_CODE | LINK_JOB_NUMBER | OPAL_NAME | LINK_TYPE | SUBMIT_DELAY_TYPE | CMD_SET_OID | APP_OID | OS_JOB_INLASPGRP | LAST_UPDATE_TIME | LAST_UPDATE_USER | PRD_INSTANCE_ID | JOB_HAS_MONITOR | AGENT_OID | AGENT_OUTPUT | USER_NAME | WORKING_DIRECTORY | RUNTIME_OS | ENV_VAR_CONTROL | OPAL_TEMP_JICD | MAX_RUN_DURATION | MAX_RUN_ACTION | OS_ROUTING_DATA
58 | @SALESWEND | Sales Process WeekEnd | 0 | G |  |  | 0 | Q | BDSYSPRF | Monitor Upload lib for D* files and submit SALESsssss jobs | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBSDI_UPL | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | BUSDEP | [5 empty] | 0 | 2 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
282 | RPL_SUGQTY | CALCULATION OF ORDER QTY. | 0 | C |  |  | 0 | + | BDSYSPRF | React on XREF_UPDAT which depends on completion of WK_RPL??? | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | TSSA | BUSDEP | *RBTDFT |  |  | X | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
312 | PRODSUDP | Daily Sunday Backup | 0 | C | To be skipped from SUNDAY1 last line |  | 0 | + | MISOPR | Daily Production Backup for Sunday | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | BRMSJOBD | QGPL | PRODSOX | QGPL | 0 | 0 | *RBTDFT |  | BRMSJOBQ | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  | Y | Y | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 46 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
348 | PRODSOX2DP | PRODSOX to RPT2WEB | 0 | C |  |  | 0 |  | QSYSOPR | Backup reports from outq PRODSOX to RBT2WEB for Audit. | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | ITTOOLS | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 54 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
392 | SYSSTRSBS | Start System Sunday | 0 | C |  |  | 0 |  | QSYSOPR | Start QINTER/QPGMR/LASER/ICASRV & all JOBQ after DAY_CLS_RN | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *USRPRF |  | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
399 | SUNDAY2 | Post Sync-Point Jobs +HBT | 0 | C | To be run manually using DO since backups are skipped |  | 0 |  | QSYSOPR | ***Job#244(@00:45)=HBT_DWND_P(@00:15)**Stop it if FTP is DWN | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QSYSOPR | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT | 5 | 800 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
566 | SYSMAFSBMW | Submit Final weekly jobs | 0 | C |  |  | 0 |  | BDSYSPRF | final set of jobs that React on Sunday jobs completing. | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
578 | SYSMAFSBMM | Submit Final monthly jobs | 0 | C |  |  | 0 |  | BDSYSPRF | final set of jobs that React on Sunday jobs completing. | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSCCCAUTH | Run Agent resetauth.sh | 0 | C |  | H | 0 | + | MISOPR |  | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 480 | 0 |  | 0 | *RBTDFT | 1 | 2200 | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2011-04-08-09.34.44.949000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
816 | SYSOPSMAIL | EMAIL GOC after WKend Prc | 0 | C |  | H | 0 |  | BDSYSPRF | Email GOC after Sunday Process & CSG conversion are done | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
941 | RBL_LNDCT2 | Rebuild Store Landed Cost | 0 | C |  |  | 0 |  | BDSYSPRF | Rebld Store Landed Cost File SUNSLC (React on JDA Robot Job) | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1277 | HBT_CUS#WP | *Purge/Create TXECCT WKN | 1 | C |  |  | 0 |  | BDSYSPRF | Purge TXECCT & Create TXECCT Rec for New Tax Exemption Cust. | *RBTDFT |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
331 | PERFNAVDR | Data Reduction | 5 | C |  |  | 0 | + | MISOPR | Performance Navigator Data Reduction | *RBTDFT |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | PERFNAV | MPGLIB | MIS | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *CRTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 51 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSJOBTBL | Check job table size | 5 | C |  |  | 0 |  | QSYSOPR | CHG#38140 | *RBTDFT |  | 5 | 0 | 600 | 1200 | 1800 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | GALSYS | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
437 | ZAACL7701 | System Values | 5 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
439 | ZAACL7703 | Network Attributes | 10 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
441 | ZAACL7715 | Local Hardware | 15 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
440 | ZAACL7709 | Output Queue Descriptions | 20 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
452 | ZAACL93 | Network job entries | 25 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
451 | ZAACL88 | Dist direct entries | 30 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
897 | SYSILMTSSC | ILMT Software Scan | 100 | C |  |  | 0 |  | MISOPR | ILMT Software and Package Scan | *RBTDFT |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | MONASPSTS | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1249 | CH_MSGSUN1 | Check Job has MSGW-SUN-#1 | 0 | C |  |  | 0 |  | BDSYSPRF | PF:UTLMSGW3-Err;TBLFS10/OVOMSG-Sbs Name;TBLFLD/CELLA*-Phone# | *RBTDFT |  | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 1 | 129 | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
388 | SYSCHGTIME | DST TIME CHANGE -1 HR | 155 | C |  | H | 0 |  | MISOPR | Fall behind 1 hr | *RBTDFT |  | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | MANISH_CEL |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 3
629 | SYSUSRPRF2 | DSPUSRPRF to ITTOOLS | 200 | C |  |  | 0 |  | MISOPR | DSPUSRPRF to ITTOOLS/USRPRF | *RBTDFT |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
332 | PERFNAVDS | Lib and Obj Sizes | 330 | C |  |  | 0 | + | MISOPR | Performance Navigator Lib and Obj Sizes | *RBTDFT |  | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | PERFNAV | MPGLIB | MIS | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *CRTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 51 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
762 | BPS831CL | *Operational Excellence | 400 | C | Do |  | 0 |  | BDSYSPRF | BOPIS Retail Operational Excellence Reporting | *RBTDFT |  | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 91 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001339 | CATMANLSTD | Dly-Get CATMAN File LST | 405 | C | Do |  | 0 |  | MISOPR | GET BY SERVER FILE LIST VIA EMAIL FOR REPLENON/OFF BY->AS400 | *RBTDFT |  | 405 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y |  | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | MANISH_CEL |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 3
000000001342 | CATMANGETD | Dly-Get CATMAN Files | 405 | C | Do |  | 0 |  | MISOPR | GET BY FILES DAILY REPLENOFF AND REPLENON ONLY BY->AS400 | *RBTDFT |  | 405 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y |  | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | MANISH_CEL |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 3
254 | MOOSEAGGR2 | *MOOSE AGGREGATE UPD WKN | 410 | C | Do |  | 0 | + | BDSYSPRF |  | *RBTDFT |  | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
269 | E3_FREEZE | E3 DAY-END PROCESS | 415 | C | Do |  | 0 | + | BDSYSPRF | E3 DAY-END PROCESS | *RBTDFT |  | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | E3PROD | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
270 | E3_DAYEND | E3 DAY-END PROCESS | 430 | C | Do, Run After 15 min after E3_FREEZE |  | 0 | + | BDSYSPRF | E3 DAY-END PROCESS | *RBTDFT |  | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | E3PROD | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
528 | POS_PURGE | O*Purge Old Sales Data | 430 | C | Skip |  | 0 |  | BDSYSPRF | Purge old sales data | *RBTDFT |  | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 58 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1221 | INVBAX_API | API Call to update invbax | 445 | C | Do | H | 0 |  | *RBTDFT | Update INVBAX and call API for nonsalble | *RBTDFT |  | 445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 10 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
555 | PERFNAVIFS | IFS Size Collection | 500 | C | Skip |  | 0 | + | MISOPR | Performance Navigator IFS Size Collection | *RBTDFT |  | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | PERFNAV | MPGLIB | MIS | QGPL | 0 | 0 | *JOBD |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 51 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
724 | NONSALE_UP | Update the Status of | 500 | C | Do |  | 0 |  | BDSYSPRF | Update the Status of product hold system files | *RBTDFT |  | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
271 | E3TWAIT | E3 DAY-END PROCESS | 515 | C | DO, Run After 15 min after E3_DAYEND |  | 0 | + | E3USER | E3 DAY-END PROCESS | *RBTDFT |  | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | E3PROD | QGPL | E3PROD | QGPL | 0 | 0 | *RBTDFT |  | E3PROD | QGPL |  | E3USER | QUSRSYS | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
527 | SYSGENRBT | re-gen robot message file | 530 | C | Skip | H | 0 |  | MISOPR | Cancel if in error with ticket to iSeries Eng | *RBTDFT |  | 530 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Y |  |  |  | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | ITTOOLS |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
728 | CPS_DAILY | Extract Sales for C&P SO | 530 | C | Skip |  | 0 |  | BDSYSPRF | Create work files for C&P Reporting (Special Order) | *RBTDFT |  | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1188 | DCA3_DAILY | *CA Morning Setup *Once | 530 | C | Do |  | 0 |  | BDSYSPRF | .CA Daily Popluate Sales Reversal Table(DCANST) and ESPCRT | *RBTDFT |  | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | DCDIRECT | QGPL | 4 | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000757 | BPS_PCKEML | Prt/Eml BOPIS Ord Pick Up | 530 | C |  |  | 0 |  | BDSYSPRF | Select Ord in STS->Prt Pick List & Eml Store for Ord Picking | *RBTDFT |  | 1715 | 1715 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | BPSJOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0530 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
495 | SYSCHKSUN | check sunrise | 545 | C | Skip | H | 0 |  | MISOPR |  | *RBTDFT |  | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *USRPRF |  | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
759 | BPS_INVENT | Eml BPS Ord Activity Rpt | 545 | C | Do |  | 0 |  | BDSYSPRF | Second Lvl Submit Email Rpt BPS825 by Str in JOBQ SKU_UPDATE | *RBTDFT |  | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1192 | F_GXDLY2TB | *FTP Google Master TBL#2 | 550 | C | Do |  | 0 |  | BDSYSPRF | FTP Google Master Tables -> PC FTP Site/google ***Before 9AM | *RBTDFT |  | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1180 | F_GXDLY1TB | *FTP Google Master TBL#1 | 558 | C | Do |  | 0 |  | BDSYSPRF | FTP PC/google(MOOMST & MOOSUMD in MOOSEAGGR1/2)***Before 9AM | *RBTDFT |  | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
486 | SYSLOGFTP | FTP Network Transactions | 600 | C | Skip | H | 0 |  | MISOPR |  | *RBTDFT |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
497 | ST_TYPE27 | *Sell Thru Type 27 entry | 600 | C | Do |  | 0 |  | BDSYSPRF | Sell through type 27 entries | *RBTDFT |  | 600 | 0 | 655 | 2000 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 66 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
499 | SYSRRMTRAN | Capture all Network Trans | 600 | C | Skip | H | 0 |  | MISOPR |  | *RBTDFT |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
511 | MKB_REPORT | Market Basket Report | 600 | C | Do | H | 0 |  | BDSYSPRF | MKB Report runs daily | *RBTDFT |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
614 | SAI_MAC | *SA Daily MAC Interface | 600 | C | Do |  | 0 |  | BDSYSPRF | Outbound MAC Daily Feed To Alpha | *RBTDFT |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
642 | SYSODBCPNT | Check for ODBC Exit Prog | 600 | C | Skip |  | 0 | + | MISOPR |  | *RBTDFT |  | 600 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2011-05-11-10.51.40.559000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
834 | ETS_DAILY | ETS-WebErr & ESPtablesFTP | 600 | C | Do |  | 0 |  | BDSYSPRF | ETS-WebError & ESP-Tables to ETS | *RBTDFT |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
836 | SE_DAILY | *Send Daily Feeds for SE | 600 | C | Do |  | 0 |  | BDSYSPRF | Send Daily Feeds for SE Active SKU | *RBTDFT |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y |  | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
865 | SKUEXT2 | *Sku Master ext part 2 | 600 | C | Do |  | 0 |  | BDSYSPRF | SKU master extension file over to Sunrise, daily, | *RBTDFT |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
923 | UP_GCCOM | Refresh Gift Card Com% | 600 | C | Skip |  | 0 |  | BDSYSPRF | Refresh Giftcard Commission Rate base of reversal Sku Retail | *RBTDFT |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 83 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1185 | CBT_DAILY | *File feed transmission | 600 | C | Do |  | 0 |  | BDSYSPRF | Send daily feed to UPS CHG000615788 | *RBTDFT |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1035 | MPOS_330WP | *Send Full PLU-MPOS-330 | 600 | C | Do | H | 0 |  | BDSYSPRF | Send Full PLU Download Files to Mobile POS Server(Store 330) | *RBTDFT |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001296 | CLR_IFSALL | O*Clear IFS see IFSLIST | 600 | C |  |  | 0 |  | MISOPR | Submit jobs for each IFS folder from IFSLIST to clean up | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 83 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000760 | BPS_ALLOC | H*Bopis Allocation Bucket | 600 | C |  | H | 0 |  | BDSYSPRF | *Not Used - Bopis Reset Bopis Allocation Bucket | *RBTDFT |  | 1040 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | H | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0600 | 2340 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1170 | AGILENCEWP | *Send Agilence LP File WN | 615 | C | Do |  | 0 |  | BDSYSPRF | SEND POS XML Trn/Tnd to LP-Weekend, Create Trigger at ENDPGM | *RBTDFT |  | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
31 | AUTO_FTP | *Resend Missed POS Price | 625 | C | Skip |  | 0 | Q | BDSYSPRF | Automatically Resend Missing Pending Price Files to POS | *RBTDFT |  | 625 | 0 | 745 | 845 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBSDI_DWN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 50 | BUSDEP | [5 empty] | 0 | 3 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 1
888 | CLD_TXNPCK | StoragePipe Order Trigger | 630 | C | Nasser to confirm if to hold job,took DO | H | 0 |  | BDSYSPRF | Get Storage Pipe Order Detail(R41/50) - Can be run on demand | *RBTDFT |  | 630 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
211 | QA_REFRESH | QA Lab Daily PLU Updates | 630 | C | DO |  | 0 |  | BDSYSPRF |  | *RBTDFT |  | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 7 | BUSDEP | [5 empty] | 0 | 32 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
241 | RBT650001 | Completion Message Listin | 630 | C | Skip |  | 0 |  | *RBTDFT | Job Completion Report | *RBTDFT |  | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 16 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
245 | PPA_DATE | Roll Prepaid Activation D | 630 | C | DO |  | 0 | Q | BDSYSPRF | OK to Cancel and inform support person next day | *RBTDFT |  | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | BUSDEP | [5 empty] | 0 | 17 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
338 | RBT651DP | Good Morning Report | 630 | C | Skip |  | 0 |  | *RBTDFT | Good Morning Report | *RBTDFT |  | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 52 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
535 | SYSJRNACT | Log Journal Rcvr Activity | 630 | C | Skip | H | 0 |  | MIMIXOWN | Log Previous Day's Journal Receiver Transaction Activity | *RBTDFT |  | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QSYSNOMAX | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSSSHCHK | AML SSH Config Check | 630 | C | Skip |  | 0 | + | MISOPR |  | *RBTDFT |  | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | PENTATECHQ | QUSRSYS | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2010-10-15-11.47.55.336000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
948 | CLR_IFSWP | O*Clear IFS TMP Fldr-WN | 630 | C | Skip |  | 0 |  | MISOPR | Clear IFS tmp folder-Weekend | *RBTDFT |  | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1166 | CXTBLBDG | *Giftcard Reversal TBLMDG | 630 | C | Do |  | 0 | + | BDSYSPRF | Send Giftcard Reversal Table TBLMDG to CMIS | *RBTDFT |  | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | CMIS | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 14 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1172 | F_PDBRCLWP | *FTP RCL Fee-> Google WN | 645 | C | Do |  | 0 |  | BDSYSPRF | FTP Recycle Fee to Google Analytic (before 7:15am) (9am-5pm) | *RBTDFT |  | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1174 | F_PDBVNDWP | *FTP Vend Master-> PDB WN | 645 | C | Do |  | 0 |  | BDSYSPRF | FTP Vend Master to Product Data Base (before 7:15am) | *RBTDFT |  | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000624 | RMAFTP | RTV Get Inbound Email ATT | 645 | C |  |  | 0 |  | BDSYSPRF | Creates RMA# for email RTV | *RBTDFT |  | 1800 | 1800 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT | 0600 | 2000 | 20 | BUSDEP | [5 empty] | 0 | 76 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
367 | AS2RESETDP | *Reset AS2 Comm. Line | 655 | C | Do AS2 restart if needed |  | 0 |  | TRAILBLAZE | Reset AS2 Communication Line Everyday | *RBTDFT |  | 655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 56 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
419 | ESPCUA | *Upld AS400 WebESP Cust | 655 | C | Do | H | 0 |  | BDSYSPRF | Upload new AS400 ESP Cust Update Status to AS400 | *RBTDFT |  | 655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 64 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
684 | AIRM_DAILY | *Send Daily Feeds AIRMILE | 700 | C | Skip |  | 0 |  | BDSYSPRF | Send Daily Feeds for AirMiles(Sales Data sends last 14 days) | *RBTDFT |  | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
917 | CHKBAL_BLD | CHECK INVBAL REBUILD | 700 | C | Do |  | 0 | + | BDSYSPRF | CHECK FOR INVBAL REBUILD COMPLETION | *RBTDFT |  | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
925 | PPR_OH_WP | PPR On Hand - rolling-SUN | 700 | C | Do |  | 0 |  | BDSYSPRF | Update PPR On Hand - rolling 90 days (Sunday) | *RBTDFT |  | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 58 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1243 | UP_MEMCONT | *Upd Sku Memory Content | 700 | C | Do |  | 0 |  | BDSYSPRF | Upd Sku Memory Content Flag INVSKU->ebay Trf OL RTN,Ok Rerun | *RBTDFT |  | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1093 | FCHN_SKUWP | *CHN Sku Lst-Fill Rpt-WKN | 700 | C | Do | H | 0 |  | BDSYSPRF | Build Sku List for Store Fill Rpt-Run before FD??_SLS Job | *RBTDFT |  | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1285 | TSS_ORDPOP | Zuora Order Number Popula | 700 | C | Skip for now |  | 0 |  | BDSYSPRF | Call BUSDEP Application in case of MSGW | *RBTDFT |  | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000288 | RBT34504 | ROBOT Schedule of Jobs to | 700 | C |  |  | 0 |  | MISOPR | schedule of jobs to run | *RBTDFT |  | 2300 | 2300 | 700 | 1129 | 1500 | 2300 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 16 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000379 | RBCSTRTMON | Re-start RBCQSYSOPR | 700 | C |  |  | 0 |  | QSYSOPR |  | *RBTDFT |  | 2300 | 2300 | 700 | 1500 | 2300 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | RBTSLEEPER | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
260 | HAMILTON | *CREATE CITICORP FILES | 715 | C | Skip |  | 0 | + | BDSYSPRF | CREATE CITICORP FILES IN BUSDEP FOLDER | *RBTDFT |  | 715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
672 | DESJARDINS | *Outbound Line Item Dtl | 730 | C | Skip |  | 0 |  | BDSYSPRF | Create Line Item Detail file in STORE/INVOHQTY by 1:45PM | *RBTDFT |  | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1176 | F_ORDSTSYD | Copy FC Order Sts Journal | 730 | C | Do |  | 0 |  | BDSYSPRF | Copy FC Order Sts Journal Up to Yesterday Only from Sunrise | *RBTDFT |  | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1183 | EM_PDNVFO | Eml Pending Sell Thr Rpt | 730 | C | Do |  | 0 |  | BDSYSPRF | Offer Created on Yesterday only Speadr60:VFOPNDEML,MENSTM/8 | *RBTDFT |  | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001289 | EM_UIDCHWP | Eml User ID Chg Err -WKN | 730 | C |  |  | 0 |  | BDSYSPRF | Email User ID Change Error-EMPRETXT File(SPEADR60/USERIDCHG) | *RBTDFT |  | 730 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000055 | AR_UPDATE | Update A/R Sub-ledger | 745 | C |  |  | 0 | Q | BDSYSPRF | Read CSHINVL1 Sales Audit Invoice Interface file & upd A/R | *RBTDFT |  | 2330 | 2330 | 745 | 945 | 1145 | 2330 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBSDI_JB1 | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 30 | BUSDEP | [5 empty] | 0 | 9 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 1
351 | EM_PRC2DP | *Email Price Chg-Follw Up | 800 | C | Do |  | 0 |  | BDSYSPRF | Email the Daily Item Price Change to the Delivery Group. | *RBTDFT |  | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 57 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
505 | PCA_STRCNT | Sat/Sun inventory connt | 800 | C | Do | H | 0 |  | BDSYSPRF | Sat/Sun inventory count | *RBTDFT |  | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 70 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
596 | TRF_AUTRCV | Auto Rec. Old Trfs | 800 | C | DO |  | 0 |  | BDSYSPRF | Auto Receive Outdated Transfers. | *RBTDFT |  | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSSSLCHK | Check for SSL v2 | 800 | C | Skip |  | 0 | + | MISOPR | Disable SSL v2 and/or Weak Ciphers if enabled. | *RBTDFT |  | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | PENTATECHQ | QUSRSYS | 0 | 0 | *RBTDFT |  | QSYSNOMAX | QSYS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2010-04-30-07.47.07.564000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
747 | KRONOSWP | *WKLY:Store Data->Kronos | 800 | C | Do |  | 0 |  | BDSYSPRF | Send POS/PO REC/TRF/RTV To Kronos for Store Labour Schedule | *RBTDFT |  | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001338 | E3_RPLEN | *E3 Repln*Before E3_Frz | 800 | C |  |  | 0 | + | BDSYSPRF | FTP ReplenOn/ReplenOff Files from PC, Done before E3_Freeze | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | E3PROD | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 96 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
804 | SKU_TRNSLN | SKU French Translation | 800 | C | Do |  | 0 |  | BDSYSPRF | SKU French Translation Outbound & Inbound | *RBTDFT |  | 800 | 0 | 1100 | 1400 | 1700 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 92 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
814 | F_ESPTBL | FTP ESP TABLE TO ETS | 800 | C | Do | H | 0 |  | BDSYSPRF | FTP ESP TABLES TO ETS SYSTEM-To be removed | *RBTDFT |  | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
864 | EMPMSTWP | O*Upload Employee Mst-WP | 800 | C | Do |  | 0 | + | BDSYSPRF | PeopleSoft Extract Data @ 6 am - Ok to rerun if this fails | *RBTDFT |  | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
870 | CRT_R40CTL | Not Use-Run in CPCDaily | 800 | C | Do | H | 0 |  | BDSYSPRF | Auto Create Missing R40 (CPC) Control Record in /POS/XMLCPC | *RBTDFT |  | 800 | 0 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
972 | PRGE_PRCZN | Purge Expired PRCZNO rcds | 800 | C | Do |  | 0 |  | BDSYSPRF | Cancel the job and call BD Applications in a case of an issu | *RBTDFT |  | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 100 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1079 | CXDLYSUN | Daily SLS CMIS-Sunday | 800 | C | Do |  | 0 | + | BDSYSPRF | Daily SLS to CMIS - Include Create ESP Ord# & Cust# ESM150CL | *RBTDFT |  | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | CMIS | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 14 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001318 | SYSPRFDSP | DSPUSRPRF to BUSDEPUSRS | 800 | C |  |  | 0 |  | SECMANISH | DSPUSRPRF to SECMANISH/BUSDEPUSRS | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000916 | POSCLEANUP | POS IFS folder cleanup | 800 | C |  |  | 0 |  | BDSYSPRF | Process CPC Tender & Transactions | *RBTDFT |  | 2300 | 2300 | 800 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
264 | CSH900 | PRICE OVERRIDE REPORT | 815 | C | Do |  | 0 | + | BDSYSPRF | PRICE OVERRIDE REPORT TO ALL STORES | *RBTDFT |  | 815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
456 | CKMONSWAW | Check MONSWABRM for SLA | 815 | C | Skip |  | 0 |  | *RBTDFT | Check to see if there is a MONSWABRM job still running Sun | *RBTDFT |  | 815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP |  |  | CKMONSWA |  |  | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
701 | EMSLSVARWP | Email Sales Var Sum-WP | 815 | C | Do |  | 0 |  | BDSYSPRF | Email Sales Audit vs Inv Audit Variance - SPEADR60/EMLSTRVAR | *RBTDFT |  | 815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000725 | AS2_CHKCOM | H*Check AS2 Comm. Line | 815 | C |  | H | 0 |  | BDSYSPRF | OK to Cancel/ Inform Pager Support in Development Group | *RBTDFT |  | 815 | 0 | 815 | 915 | 1215 | 1615 | 1715 | 1915 | 2015 | 2130 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 87 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
783 | CPYAHS_P | *Upload Auto Hub&Spk Data | 815 | C | Do |  | 0 |  | BDSYSPRF | PT-Upl HS CPC->DLYHDR/DLYDTL(CCNCTL-Dly Ctl) SPEADR60/AUTOHS | *RBTDFT |  | 815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
461 | OF_IN_GA | Oracle Chart Accts JDA | 830 | C | Do |  | 0 | + | BDSYSPRF | GA-Oracle Chart of Accounts to JDA | *RBTDFT |  | 830 | 0 | 1230 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
462 | OF_IN_GL | Oracle Locations to JDA | 830 | C | Do |  | 0 | + | BDSYSPRF | Gl-Oracle locations to JDA | *RBTDFT |  | 830 | 0 | 1230 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
463 | OF_IN_GR | Oracle Exch Rates to JDA | 830 | C | Do |  | 0 | + | BDSYSPRF | GR-Oracle Exchange rates to JDA | *RBTDFT |  | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
466 | OF_IN_GT | Oracle GL TransactionsJDA | 830 | C | Do |  | 0 | + | BDSYSPRF | GT-Oracle GL Transactions to JDA | *RBTDFT |  | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
727 | HEAD_COUNT | *Head Count Sales file HD | 830 | C | Do |  | 0 |  | BDSYSPRF | Send Last 14 Day Sls (Err Log: MMBUSLIB/LPHCLOGS/SND_OUTPUT) | *RBTDFT |  | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1065 | MOOSE3_WP | M*Rebuild MOOSE3-Weekend | 830 | C | Do, Come back, Run after all E3xxxxx jobs completed in E3QBATCH sbs |  | 0 |  | BDSYSPRF | Rebuild MOOSE3-Weekend (MOOSEAGGR2 must be completed first) | *RBTDFT |  | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
975 | EM_HUGEQTY | Email Huge Inv Adj Qty | 830 | C | Skip |  | 0 |  | BDSYSPRF | Huge Inv Adj Qty>1000 (Typ 31-98 & <>71)(SPEADR60-HUBADJQTY) | *RBTDFT |  | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001292 | DST_SUN | SUNDAY DISTRICT STORE RES | 900 | C |  |  | 0 | + | BDSYSPRF | Weekly District Store Results on Sunday | *RBTDFT |  | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | STOREBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001322 | ALG_BAL_WP | *DailyAlgolia Invbal File | 900 | C |  |  | 0 | + | BDSYSPRF | *Daily Algolia Invbal File - Weekend | *RBTDFT |  | 900 | 0 | 900 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 14 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
895 | CSH_XTN_WK | Cash Bolt-on file-WKN | 845 | C | Do |  | 0 |  | BDSYSPRF | Online Rtn Inv Update. Email eBay Trf List:SPEADR/ONLRETRN. | *RBTDFT |  | 845 | 0 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
468 | OF_EML_CNF | Email Outstndng Confirms | 900 | C | Do |  | 0 | + | BDSYSPRF | Email Outstanding Confirmations | *RBTDFT |  | 900 | 0 | 1300 | 1600 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSSTPROLL | Dasd plus Rolling Survey | 900 | C | Skip | H | 0 | + | MISOPR | If in error, call iSeries Engineering | *RBTDFT |  | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | DASDPLUS | ETIDP | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | SYSNOMAX | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2011-09-22-10.59.14.926000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
826 | EMMISSW1 | Email Missing Rtl Sales | 900 | C | Do |  | 0 |  | BDSYSPRF | Email Miss Sls Tran-SPEADR CSHMISS(JobName End 1/2-SDI913JQ) | *RBTDFT |  | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
985 | EM_SKUADCH | Email Sku Add/Change Data | 900 | C | DO |  | 0 |  | BDSYSPRF | Email Sku Add/Change Data (SPEADR60-SKUADDCHG) | *RBTDFT |  | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1056 | CX_MST_WP | *Daily CMIS Master Files | 900 | C | DO |  | 0 | + | BDSYSPRF | Daily CMIS Master/Inv Bal/Price Files(No Sales) - Weekend | *RBTDFT |  | 900 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | CMIS | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 14 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1059 | EM_SLS_PCS | Email SLS Piece Count Rpt | 900 | C | DO | H | 0 |  | BDSYSPRF | Email Sales Piece Count Report (SPEADR60-SLSPCS) | *RBTDFT |  | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1287 | EM_EP_UNAP | Email Daily Emg Prf UnApr | 900 | C | DO |  | 0 |  | BDSYSPRF | Email Daily Unapproved Emergency Profile Rpt(TBLFS10/USREPA) | *RBTDFT |  | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1159 | OOSLBD15 | Prt Out of Stk Lbl D15 | 900 | C | DO | H | 0 |  | BDSYSPRF | Print Out of Stock Label-District 15 | *RBTDFT |  | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1266 | SUNIRF_WP | SUNRISE Inv Fresh Sat-Sun | 900 | C | Do |  | 0 |  | BDSYSPRF | SUNRISE Inv Fresh Sat-Sun | *RBTDFT |  | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | NGP_PRC | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
207 | SVC026CL | D*Prt SVS Settlement Rpt | 930 | P | DO |  | 0 |  | BDSYSPRF | OK cancel. Info IS Support in next business day. D*:Hamilton | *RBTDFT |  | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 30 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
469 | OF_IN_RC | Orcl Reconcil Ttls JDA | 930 | C | Do |  | 0 | + | BDSYSPRF | RC-Oracle Reconciliation Totals to JDA (AI and GI only) | *RBTDFT |  | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
902 | MONINVBL1A | INVBAL Refresh to Sunrise | 945 | C | Do | H | 0 |  | BDSYSPRF | Utility to Monitor INVBAL Refresh to Sunrise (Sun) 1st | *RBTDFT |  | 945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
490 | F_XEROXWP | *Send PO Rec RTV Info XRX | 1000 | C | Do |  | 0 |  | BDSYSPRF | Sun Only Send PO Receiving and RTV Info to Xerox Doc Folder | *RBTDFT |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
501 | POS_REJECT | reject POS trans report | 1000 | C | Do |  | 0 |  | BDSYSPRF | Email POS Reject Trans Report | *RBTDFT |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 66 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
697 | SYSSWPAUD | Audit swap profiles | 1000 | C | Skip |  | 0 |  | MISOPR | ticket to iseries, cancel if error, do not call out | *RBTDFT |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | SYSNOMAX | IBMMODS |  | *RBTDFT | *RBTDFT | ITTOOLS |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSBCKPRG | Purge backup audit log | 1000 | C | Skip |  | 0 | + | MISOPR | Cancel if in error, do not call out, ticket to iSeries Engin | *RBTDFT |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | SYSNOMAX | IBMMODS |  | *RBTDFT | *RBTDFT | ITTOOLS |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2012-09-21-10.09.20.809000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
829 | BLD_PRXFWK | Bld Program Ref-Wkend | 1000 | C | Skip |  | 0 |  | BDSYSPRF | Build Program Reference Database File (Replace Hawkeye) | *RBTDFT |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
846 | CK_E3EOD1A | O*Check E3 EOD(Sun)ASR | 1000 | C | Skip |  | 0 |  | BDSYSPRF | Send text alert if E3 ASR EOD runs late (Sunday) | *RBTDFT |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
935 | EM_PMWK | P&M Flash Sales-CPC Email | 1000 | C | Do | H | 0 |  | BDSYSPRF | Email WTD/PTD/YTD CPC Flash Sales | *RBTDFT |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
968 | F_OS_POTRW | FTP Unrec PO Trf-BTS Wk N | 1000 | C | Do |  | 0 |  | BDSYSPRF | FTP Unrec PO Trf include 3 months prior,12 months in future | *RBTDFT |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1227 | SYSCHKLKEY | Check license keys expire | 1000 | C | Skip |  | 0 |  | MISOPR | Can be cancelled with ticket to iSeries Platform Engineering | *RBTDFT |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
368 | SYSDDMAUDP | Add Users to IP DDM SV | 1001 | C | Skip |  | 0 |  | QSYSOPR | BUSDEP SNA to IP - Add Users to IP DDM SVR | *RBTDFT |  | 1001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 61 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSUSRPRF | DSPUSRPRF to ITTOOLS | 1001 | C | Skip | H | 0 |  | MISOPR | DSPUSRPRF to ITTOOLS/USRPRF | *RBTDFT |  | 1001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
493 | SYSRSFCHK | Check RSF communications | 0 | C | Skip | H | 0 |  | MISOPR | Check to see if RSF is waiting and kill if over 60 minutes | *RBTDFT |  | 1001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | ITTOOLS | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | ITTOOLS | EVERY |  | X | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
694 | EM_PRC3DP | Email Price Chg.-Init run | 1005 | C | Do |  | 0 |  | BDSYSPRF | Email the Daily Item Price Change to the Delivery Group.-Tue | *RBTDFT |  | 1005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y |  |  |  | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 57 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
794 | CH_LBL_OD | Check O/S On Demand Signs | 1030 | C | Skip |  | 0 |  | BDSYSPRF | Send TXT MSG:Pending On Demand Signs in AccessVia FTP Folder | *RBTDFT |  | 1030 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
849 | CK_E3EOD1W | O*Check E3 EOD(Sun)AWR | 1030 | C | Skip |  | 0 |  | BDSYSPRF | Send text alert if E3 AWR EOD runs late (Sunday) | *RBTDFT |  | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1096 | FD15YSLSWP | *D15 YDay SL-Fill Rpt-WKN | 1030 | C | Do | H | 0 |  | BDSYSPRF | Bld YDay SLS for Dst 15 Str Fill Rpt-Run after FCHN_SKU done | *RBTDFT |  | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1098 | FD20_SLSWP | *D20 YDay SL-Fill Rpt-WKN | 1030 | C | Do | H | 0 |  | BDSYSPRF | Bld YDay SLS for Dst 20 Str Fill Rpt-Run after FCHN_SKU done | *RBTDFT |  | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1289 | EM_UIDCHWP | Eml User ID Chg Err -WKN | 1030 | C | Do |  | 0 |  | BDSYSPRF | Email User ID Change Error-EMPRETXT File(SPEADR60/USERIDCHG) | *RBTDFT |  | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
552 | PRTLABELW | *Print Labels | 1040 | C | Do |  | 0 |  | BDSYSPRF | Submit DAY_LBLsss Job-Can't run before SSWINBND2(Create SKU) | *RBTDFT |  | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y |  |  |  | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 8 | BUSDEP | [5 empty] | 0 | 3 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
760 | BPS_ALLOC | H-Bopis Allocation Bucket | 600 | C | Do | H | 0 |  | BDSYSPRF | *Not Used - Bopis Reset Bopis Allocation Bucket | *RBTDFT |  | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 600 | 2340 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
547 | SYSDCMJBSC | crt dcm jobscde files | 1041 | C | Skip |  | 0 |  | MISOPR | can be cancelled with ticket to iseries, do not call out | *RBTDFT |  | 1041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | ITTOOLS | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
178 | EM_DSAW1 | *EMail Daily SLS All Str | 1100 | C | Do |  | 0 |  | BDSYSPRF | Email Daily Sls to SPEADR/EXECHH(*See SLS886JQ Char 8th = 1) | *RBTDFT |  | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
233 | MMEJOB | Run Weekly MME Project | 1100 | C | Do | H | 0 | + | HCHAN | Weekly MME | *RBTDFT |  | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | MMEJOBD | MMDEVCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | HCHAN | QUSRSYS | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 40 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
412 | PASS_CPY | *PASS Trans Dtl Feed | 1100 | C | Do |  | 0 |  | BDSYSPRF | PASS Trans details feed from BusDep to MARSQL5 | *RBTDFT |  | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 64 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1069 | CVM_CSAT1 | Send/Receive CVM Data | 1100 | C | Do | H | 0 |  | BDSYSPRF | Send/Receive CVM (Customer Service Satisfaction) Data | *RBTDFT |  | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 58 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1162 | F_PRECIMA | *FTP Precima Prc Data | 1100 | C | Do |  | 0 |  | BDSYSPRF | *FTP PRC/TLOG,Online Prc done on Sunrise KPRECPWK-FTP @ 12AM | *RBTDFT |  | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
687 | EMLCHBER#1 | Alert-CHub SLS Post ERR | 1130 | C | Do | H | 0 |  | BDSYSPRF | Send Email Alert for C-Hub Sales Posting Failure | *RBTDFT |  | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
746 | EMLCHBER#2 | EMail CHub Error Report | 1130 | C | Do |  | 0 |  | BDSYSPRF | EML CHub Err Rpt base on Dly Sales(ISTYPE=08,SPEADR=CHUBRPT) | *RBTDFT |  | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 87 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1085 | EM_DSTW1 | *EMail Daily SLS Transfrm | 1130 | C | Do |  | 0 |  | BDSYSPRF | TBLSTX/STTYP1=T, SPEADR/DLYSLSSTR (*See SLS886JQ Char 8th=1) | *RBTDFT |  | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
696 | VFOEMLWP | Email Sell Through Offer | 1200 | C | Do | H | 0 |  | BDSYSPRF | Email the Sell Through Offer Changes to Merch / Finance | *RBTDFT |  | 1200 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 57 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
754 | F_ESPOCS | FTP Open ESP Case->ECP | 1200 | C | Do | H | 0 |  | BDSYSPRF | FTP Open ESP Cases in Last 3 Days to PC Application(Andriy) | *RBTDFT |  | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1282 | EM_NOSGNWP | *Eml No Prc Chg Sign-WKN | 1201 | C | Do |  | 0 | Q | BDSYSPRF | Eml Str Miss Prc Chg Signage,PRTLABELW Job-SPEADR60/NOPRCSGN | *RBTDFT |  | 1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 8 | BUSDEP | [5 empty] | 0 | 96 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
154 | SP_VND_MET | *SPartners Vendor Metric | 1215 | C | Do, before 4PM ( US dependent job) |  | 0 | + | BDSYSPRF | StaplesPartner - Vendor Metric Feed | *RBTDFT |  | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH3 | *LIBL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
E3_PO+151:170+151:170_03 | MONINVBL1B | INVBAL Refresh to Sunrise | 1215 | C | Do | H | 0 |  | BDSYSPRF | Utility to Monitor INVBAL Refresh to Sunrise (Sun) 2nd | *RBTDFT |  | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
871 | CRT_R50CTL | Not Use-Run in CPCDaily | 1300 | C | Do | H | 0 |  | BDSYSPRF | Auto Create Missing R50 (SP) Control Record in /POS/XMLCLD | *RBTDFT |  | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
267 | DIVCLN | PURGE CANxxx DIVIDEND | 1300 | C | Nasser to confirm if to hold job |  | 0 | + | BDSYSPRF | PURGE CANxxx DIV FILES / Sunday SLS to CMIS /eBay Transfer | *RBTDFT |  | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QSYSOPR | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
664 | CLICKSDP | *CLICKS TRACKING | 1300 | C | Do |  | 0 |  | BDSYSPRF | FULL SERVER CLICK COUNT | *RBTDFT |  | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
524 | DRPSHPVNWP | Vendor File | 1300 | C | Do | H | 0 |  | BDSYSPRF | Create the Drop Ship Vendor File for Planogram Database | *RBTDFT |  | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 66 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1163 | CH_CSHXTN | Chk Unprocess BOLT On Rec | 1300 | C | Do |  | 0 |  | BDSYSPRF | Send TXT MSG:BOLT On Rec in CSHXTN/CXSTATUS=' '->Invalid Sku | *RBTDFT |  | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
735 | CRMIDLY | *Proc M/C Info from Comps | 1300 | C | Do |  | 0 |  | BDSYSPRF | Receive daily machine information from Compass | *RBTDFT |  | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
736 | CRMRDLY | Process last 2weeks data | 1330 | C | Do |  | 0 |  | BDSYSPRF | Receives AR summary and detail feeds from CFS system | *RBTDFT |  | 1330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
792 | CH_LBL_DE | Check O/S PRC CHG Signage | 1330 | C | Come back later on, skip |  | 0 |  | BDSYSPRF | Send TXT MSG:Pending PRC CHG Signage in AccessVia FTP Folder | *RBTDFT |  | 1330 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
806 | LWP_DAILY | *Lowest Price Daily | 1330 | C | Do |  | 0 |  | BDSYSPRF | Fine tune LWP for End of Day process | *RBTDFT |  | 1330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
922 | CH_E3POCWP | Check New E3 PO Count | 1345 | C | Do |  | 0 |  | BDSYSPRF | Send Text Alert-If > 7000 New E3 PO created today on Weekend | *RBTDFT |  | 1345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
929 | EBY_TRF_WK | *Send eBay transfer Wkend | 1400 | C | Do |  | 0 |  | BDSYSPRF | Send eBay transfers to eBay Instant Sales server - Weekend | *RBTDFT |  | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
274 | SLS_GM_RPT | SALES GROSS MARGIN REPORT | 1400 | C | Do |  | 0 | + | BDSYSPRF | SALES GROSS MARGIN REPORT | *RBTDFT |  | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
304 | BRMSMAINT | BRMS Maintenance | 1400 | C | Skip |  | 0 | + | *RBTDFT | BRMS Maintenance | *RBTDFT |  | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | BRMSRMT1 | QUSRSYS | 1 | 0 | *RBTDFT |  | BRMSJOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 46 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
407 | PURGELBL | purge signage spool file | 1400 | C | Do Nasser to confirm if to hold job |  | 0 |  | BDSYSPRF | Purge Store Signage Spool Files | *RBTDFT |  | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
666 | CLK_ERR | CLICKS ERROR REPORTS | 1400 | C | Do |  | 0 |  | BDSYSPRF | FULL SERVER AND SELF SERVER CLICKS ERROR REPORTS | *RBTDFT |  | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
947 | AIRM_RVRSE | *Air Mile Sales Reversal | 1400 | C | Skip |  | 0 |  | BDSYSPRF | Get IFS/Transfer/Airmiles/Reversal/STAPLES_IS*:SPEADR-AMRMSG | *RBTDFT |  | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1270 | CLR_OUTQS | Clear Output Queues | 1400 | C | Skip |  | 0 | + | BDSYSPRF | Weekly Cleanup of Output Queues | *RBTDFT |  | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
737 | CRMXDLY | *Send m/c data to compass | 1430 | C | Do |  | 0 |  | BDSYSPRF | Receive Xerox&Non-Xerox feed daily and send updated data | *RBTDFT |  | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 75 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
881 | EM_DSAW2 | *EMail Daily SLS All Str | 1500 | C | Do |  | 0 |  | BDSYSPRF | Email Daily Sls to SPEADR/EXECHH & SPEADR60/DLYSLSDIV*CHR8=2 | *RBTDFT |  | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1229 | BPS_AVLQTY | H-Refresh BOPIS Avail Qty | 0 | C |  | H | 0 | Q | BDSYSPRF | BLD OEBASLIB/OEBOPHDJ->QTEMP/OEBOPHDJBD->MMBUSLIB/OEBOPHDJBD | *RBTDFT |  | 1510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 430 | 2359 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
287 | E3_PO_03 | *ELECTRONIC PO TRANSFER | 1530 | C | Run after E3 EOD complete |  | 0 | + | MISOPR | ELECTRONIC PO TRANSFER | *RBTDFT |  | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD3 | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | PO | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1086 | EM_DSTW2 | *EMail Daily SLS Transfrm | 1530 | C | DO, Run after all E3xxxxx jobs completed in E3QBATCH sbs |  | 0 |  | BDSYSPRF | TBLSTX/STTYP1=T, SPEADR/DLYSLSSTR (*See SLS886JQ Char 8th=2) | *RBTDFT |  | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
748 | CH_PRCCHGC | Alert Sku Price Change CT | 1532 | C | Do |  | 0 |  | BDSYSPRF | Text Alert Sku Price Change Count if > 1000 (TBLFLD/CELLON) | *RBTDFT |  | 1532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
63 | RTVPENDING | Create RTV Pending record | 1600 | C | Do |  | 0 | Q | BDSYSPRF | Create RTV Pending (If failed - cancel; tell STAN on Monday) | *RBTDFT |  | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | BUSDEP | [5 empty] | 0 | 13 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSCHKBCK | Check Backup Job Logs | 1600 | C | skip |  | 0 | + | MISOPR | Ticket to iSeries if in error, do not call out | *RBTDFT |  | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | SYSNOMAX | IBMMODS |  | *RBTDFT | *RBTDFT | ITTOOLS |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2012-05-03-11.00.48.678000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
776 | EMLNOSL6 | Email No SLS List Batch 5 | 1600 | C | Do |  | 0 |  | BDSYSPRF | No Sls Str Lst Today-NLNBNSPIONPQSKMBABNTBCYT SPEADR/NOSALES | *RBTDFT |  | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
725 | AS2_CHKCOM | Check AS2 Comm. Line | 815 | C | Skip | H | 0 |  | BDSYSPRF | OK to Cancel/ Inform Pager Support in Development Group | *RBTDFT |  | 1615 | 0 | 915 | 1215 | 1615 | 1715 | 1915 | 2015 | 2130 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 87 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
927 | POS_TENDER | Populate AN# to CSHTND | 0 | C |  | H | 0 |  | BDSYSPRF | 1)XPSTND/XTAN#-->CSHTND/CSCRD# 2)PLCTND/AN#-->CSHTND/CSCRD# | *RBTDFT |  | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | POSDFILE | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 455 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
216 | CCF2SUNR | *Send Coupon to Sunrise | 1700 | C | Do |  | 0 | + | BDSYSPRF | !!! OK to Cancel. Please info Stanley Woo for error. !!! | *RBTDFT |  | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | QSYSOPR | *LIBL | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 35 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
284 | SEND_EDI2 | EDI PO TRANSFERS | 1700 | C | Do |  | 0 | + | MISOPR |  | *RBTDFT |  | 1700 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y |  | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD2 | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | PO | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
335 | PERFNAVPM | Monitor | 1700 | C | skip |  | 0 | + | MISOPR | Performance Navigator Monitor | *RBTDFT |  | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | PERFNAV | MPGLIB | MIS | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *CRTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 51 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
550 | BHN_DLYSTM | BHN statement posting | 1700 | C | Do |  | 0 |  | BDSYSPRF | Gift card Mall BHN STatement Posting | *RBTDFT |  | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1222 | INVBAX_API | API INVBAX | 0 | C |  | H | 0 |  | BDSYSPRF | API CALL for Nonsalable | *RBTDFT |  | 1755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | POSWALKER | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 455 | 2326 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
103 | DLTHSTLOG | Delete History | 1800 | C | skip | H | 0 | Q | QPGMR |  | FISCAL_21 |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *BLANK | 0 | STANDARD | 0 | *DFT | QBATCH | QGPL | QPRINT | QGPL | 0 | 0 | *JOBD |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | HELPSYS | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 1
275 | MICROSOFT | *EDI RUN FOR MICROSOFT | 1800 | C | Do |  | 0 | + | BDSYSPRF | EDI RUN FOR MICROSOFT | *RBTDFT |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | PO | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSSAVARC | Archive check pts to hst | 1800 | C | skip |  | 0 |  | QSYSOPR | Archive check point information to history member | *RBTDFT |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *USRPRF |  | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | GALSYS | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
405 | NPD_SLS | Weekly Sales Summary | 1800 | C | Do |  | 0 |  | BDSYSPRF | Weekly Sales Summary File to NPD Survey Company | *RBTDFT |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 64 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
533 | SYSJRNCHK | Journal Monitor Program | 5 | C | Skip | H | 0 |  | QSYSOPR | Journal Monitor Program | *RBTDFT |  | 1800 | 0 | 600 | 1200 | 1800 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
887 | JACKRTLRPT | *Print Retail Jackie Rpt | 1800 | C | Do |  | 0 |  | BDSYSPRF | Print Email Jackie Report | *RBTDFT |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
822 | EMLTRFVAR | Email Transfer Var Rpt | 1800 | C | Do |  | 0 |  | BDSYSPRF | Email Transfer Variance Report for Import-SPEADR60/TRFVARRPT | *RBTDFT |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
855 | EMMISSW2 | Email Missing Rtl Sales | 1830 | C | Do |  | 0 |  | BDSYSPRF | Email Miss Sls Tran-SPEADR CSHMISS(JobName End 1/2-SDI913JQ) | *RBTDFT |  | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
473 | SYS_ORACLE | Clean up ORACLE Outq | 1900 | C | Skip |  | 0 |  | ETIDP | Clean up ORACLE OutQ | *RBTDFT |  | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | ETIJOBD | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSSIAMUID | SIAM UID Update | 300 | C | Skip | H | 0 |  | MISOPR | Process SIAM UID updates | *RBTDFT |  | 1900 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
775 | EXTSLSB1WK | *BLD Ext. Sls-1 Week Ago | 1900 | C | Do |  | 0 |  | BDSYSPRF | Build Ext Sls (CLS Rebate)Sum File-1 Wk Ago & Run Reg 1 Rpt | *RBTDFT |  | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
868 | SKU_BPSFLG | SKU Bopisflag feed to PDB | 1900 | C | Do |  | 0 |  | BDSYSPRF | Update SKU Bopis flag in PDB from JDA feed | *RBTDFT |  | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1067 | WK_DST_SUN | WKLY DISTRICT RESULTS-SUN | 1900 | C | Do |  | 0 | + | BDSYSPRF | WKLY DISTRICT RESULTS RPT-Str Outq(Stopped)/PRTJSOARES DST | *RBTDFT |  | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | STOREBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
960 | IS4_AUTOPN | Auto Scan Batch Open | 1900 | C |  | H | 0 |  | *RBTDFT | Contact BD Applications for support | *RBTDFT |  | 1900 | 0 | 2000 | 2100 | 2200 | 2300 | 2345 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
831 | EML_DUPLNK | Check Dupl Recycle Fee | 1930 | C | Do |  | 0 |  | BDSYSPRF | Check Duplicate Recycle Fee Linkage (SPEADR60-DUPRCLLNK) | *RBTDFT |  | 1930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1158 | FD15TSLSWP | *D15 TDay SL-Fill Rpt-WKN | 1945 | C |  | H | 0 |  | BDSYSPRF | Bld YDay SLS for Dst 15 Str Fill Rpt-Run after FCHN_SKU done | *RBTDFT |  | 1945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
125 | E3_DUP_PO1 | Eml Dup E3 Rls Ord-WKN | 2000 | C | Run after E3 EOD complete |  | 0 | + | BDSYSPRF | E3 Rls Ord for Same Str/Sku-MERCHOPERATIONSCANADA@STAPLES.CA | *RBTDFT |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
681 | CLD_PRICE | *Feeds to Storage Pipe | 2000 | C |  | H | 0 |  | BDSYSPRF | Outbound Price & Coupon files to Storage Pipe | *RBTDFT |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
239 | CLR_QPRINT | Clear outq qprint | 2000 | C |  |  | 0 |  | QSYSOPR |  | *RBTDFT |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS | 5 | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 37 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
374 | SYSCHKSYS | System Resource Checks | 0 | G |  |  | 0 |  | *RBTDFT |  | *RBTDFT |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QSYSNOMAX | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 500 | 2000 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
549 | SYSRMTSYNC | Sync Robot ALert Files | 2000 | C |  | H | 0 |  | MIMIXOWN | Sync Robot Alert Device Files to the Mimix HA System | *RBTDFT |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QSYSNOMAX | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
459 | OF_OUT_AI | *Invoice Interface Oracle | 0 | C |  |  | 0 | + | BDSYSPRF | AI - AP Invoice Interface to Oracle (CSG Inv after CSG conv) | *RBTDFT |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEOUT | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT | 800 | 2000 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
563 | CPC_PRICE | *Copy Centre Payments | 2000 | C |  |  | 0 |  | BDSYSPRF | Copy Centre On-Line Payment Sales Transactions to JDA | *RBTDFT |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
624 | RMAFTP | RTV Get Inbound Email ATT | 645 | C |  |  | 0 |  | BDSYSPRF | Creates RMA# for email RTV | *RBTDFT |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT | 600 | 2000 | 20 | BUSDEP | [5 empty] | 0 | 76 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
631 | SVC_ACT | *SVC Card Batch Activate | 2000 | C |  |  | 0 |  | BDSYSPRF | SVC Card Batch Activation-Must be done by 10 pm | *RBTDFT |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 76 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
884 | CPC_RSPO | *Auto Resend CPC PO | 2000 | C |  |  | 0 |  | BDSYSPRF | Resend CPC PO if unacknowledged after 2 days-TBLFS10/CPPDAT | *RBTDFT |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
838 | SYSCHKCQ | Check RBNCQ record count | 0 | C |  | H | 0 |  | MISOPR | Check for RBNCQ records > 0 | *RBTDFT |  | 2001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 120 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
460 | OF_OUT_GI | Journal Interface Oracle | 0 | C |  |  | 0 | + | BDSYSPRF | GI - GL Journal Interface to Oracle | *RBTDFT |  | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEOUT | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT | 830 | 2030 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
299 | ENDQINTWKE | ENDQINTWKE | 2040 | C |  |  | 0 | + | QSYSOPR |  | *RBTDFT |  | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QSYSOPR | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QCTL | QSYS |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
467 | OF_IN_CNF | Confirmation File Retrvl | 0 | C |  |  | 0 | + | BDSYSPRF | Confirmation File Retrieval (.CNF) | *RBTDFT |  | 2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 30 | 0 |  | 0 | *RBTDFT | 845 | 2045 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
924 | UP_RELOC2N | Reloc Store POS Active=N | 2045 | C |  |  | 0 |  | BDSYSPRF | Set Reloc Store POS Active=N in POLSTR file for Str 401->419 | *RBTDFT |  | 2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
749 | EMLPRCPR | Email Price Protection | 2058 | C |  |  | 0 |  | BDSYSPRF | Email Price Protection Information to Merchants | *RBTDFT |  | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSAMLOUTQ | AML OUTQ Load | 2100 | C |  | H | 0 |  | MISOPR | Auditing, Logging, Monitoring - Read OUTQs and load the tool | *RBTDFT |  | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
554 | DAYSTARTW | Day Start | 2100 | C |  |  | 0 | Q | BDSYSPRF | Call DAYPRCCL then Submit DAYSTRCL job weekends | *RBTDFT |  | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  | X | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 8 | BUSDEP | [5 empty] | 0 | 58 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
341 | CKDAYSTR | Check Resource RBDAYSTART | 2101 | C |  |  | 0 |  | *RBTDFT |  | *RBTDFT |  | 2101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *JOBD |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 53 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
799 | CHK_DAYSTR | Check DAYSTART/W Status | 2115 | C |  |  | 0 |  | BDSYSPRF | Text Alert:Check DAYSTART/W Robot Job Status | *RBTDFT |  | 2115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
508 | SYSAUDBKUP | Audit libraries backup | 2130 | C |  |  | 0 | + | MISOPR | Audit libraries backup | *RBTDFT |  | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | BRMSJOBD | QGPL | PRODSOX | QGPL | 0 | 0 | *RBTDFT |  | BRMSJOBQ | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  | Y | Y | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 46 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
883 | CH_E3_VND | Check E3 Vendor in E3SITM | 2130 | C |  |  | 0 |  | BDSYSPRF | Send TXT MSG:Check / Delete Invalid E3 Vendor(1 ) in E3SITM | *RBTDFT |  | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
92 | SP_STORE | StaplesPartners Store inf | 2200 | C |  |  | 0 | + | BDSYSPRF | StaplesPartner - Store List | *RBTDFT |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
243 | HBT_GNRD | TXECCT records generation | 2200 | C |  |  | 0 | + | BDSYSPRF |  | *RBTDFT |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | QSYSOPR | *LIBL | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 42 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
896 | SYSILMTHSC | ILMT Hardware Scan | 2200 | C |  |  | 0 |  | MISOPR | ILMT Hardware Scan | *RBTDFT |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | ITTOOLS | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
417 | ESPCUI | Upload Web ESP Cust Info | 2200 | C |  | H | 0 |  | BDSYSPRF | Upload new Web ESP Customer Information | *RBTDFT |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 64 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
558 | SYSPQMON | fax queue monitor | 0 | C |  |  | 0 |  | MISOPR | Can be cancelled with ticket to iseries, do not call out | *RBTDFT |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | QSYS |  | *RBTDFT | *RBTDFT | ITTOOLS | EVERY |  | X | Y | N | 0 | 0 | 30 | 0 |  | 0 | *RBTDFT | 600 | 2200 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
590 | SYSCHKJQE3 | Check E3 resource jobqs | 0 | C |  |  | 0 |  | *RBTDFT | Check specific E3 jobqs different time frame than SYSCHKSYS | *RBTDFT |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *JOBD |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 1300 | 2200 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
648 | SAI_INRF | Weekly RF Feed From WIS | 2200 | C |  |  | 0 |  | BDSYSPRF | Accepts RTV status from WIS and post 71 and update JDA data. | *RBTDFT |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 79 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
926 | UPD_CSTPLN | *Set CSTPLN for Tomorrow | 2200 | C |  |  | 0 |  | BDSYSPRF | Run after DAYSTART/W to Set NEXTDATE as Tomorrow | *RBTDFT |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1175 | F_PDBPRD | *FTP Prod Master to PDB | 2200 | C |  |  | 0 |  | BDSYSPRF | FTP Prod Master to Product Data Base (before 11pm) | *RBTDFT |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
342 | CKRBTGNR | Check Resource RBRBT_GNRD | 2201 | C |  |  | 0 |  | *RBTDFT |  | *RBTDFT |  | 2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *JOBD |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 53 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
605 | SYSUSRAUD | User Auditing Set | 2215 | C |  |  | 0 |  | MISOPR | Turn on User Auditing for power users | *RBTDFT |  | 2215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
606 | SYSUSRAUD2 | User Auditing Remove | 2225 | C |  |  | 0 |  | MISOPR | Turn off User Auditing if not a power user | *RBTDFT |  | 2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
869 | EM_IMJCK | Email Import Jackie Rpt | 2225 | C |  |  | 0 |  | BDSYSPRF | Email Import Jackie Sales Report (SPEADR60-IJCKEMAIL) | *RBTDFT |  | 2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
90 | SP_OPNPO | StaplesPartners opn PO | 2230 | C |  |  | 0 | + | BDSYSPRF | StaplesPartner - Open PO feed | *RBTDFT |  | 2230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSSIAMAUT | SIAM GRTOBJAUT *ALL | 2230 | C |  |  | 0 |  | MISOPR | Omits 'Q' profiles and those in ITTOOLS/SIAM_OMIT | *RBTDFT |  | 2230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
649 | SAI_INFI | Weekly FB Feed From Alpha | 2230 | C |  |  | 0 |  | BDSYSPRF | Accepts final Inventory status and send variance to Finance. | *RBTDFT |  | 2230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 79 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1179 | OVR_PRINTQ | Override Store Printq | 0 | C |  |  | 0 |  | BDSYSPRF | Override Store Print Queue, PF:OVROUTQ, TBLFLD/PRTNAM | *RBTDFT |  | 2239 | 2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 1 | 0 |  | 0 | *RBTDFT | 600 | 2359 | 20 | BUSDEP | [5 empty] | 0 | 88 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1091 | F_ETS_ORD | Send Tec Ord to ETS Servr | 0 | C |  |  | 0 |  | MISOPR | Send Tec Order to ETS Server (FTP 10.18.9.46/ftp_ets_prd) | *RBTDFT |  | 2239 | 2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | JDAJOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 1 | 0 |  | 0 | *RBTDFT | 530 | 2330 | 20 | BUSDEP | [5 empty] | 0 | 88 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
357 | STRPRT | Start all printers | 0 | C |  |  | 0 |  | *RBTDFT | Start all rmt and prt writers | *RBTDFT |  | 2240 | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 10 | 0 |  | 0 | *RBTDFT | 500 | 2300 | 20 | BUSDEP | [5 empty] | 0 | 60 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
518 | @XMLSLS | XML POS Process XPS=>USI* | 0 | C |  |  | 0 |  | BDSYSPRF | XML POS Processing in Busdep | *RBTDFT |  | 2240 | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | POSWALKER | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 455 | 2326 | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
663 | SOSCFM | *Spec Order Payment Confr | 0 | C |  |  | 0 |  | MISOPR | Special Order Payment Confirmation | *RBTDFT |  | 2240 | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 530 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
723 | CPP_KIOSK | ***Copy & Print Kiosk Ord | 0 | C |  |  | 0 |  | MISOPR | Retreive Copy & Print Kiosk orders | *RBTDFT |  | 2240 | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | ETLJOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 530 | 2330 | 20 | BUSDEP | [5 empty] | 0 | 88 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
729 | CPS_ORDRTV | Extract C&P Orders for PR | 0 | C |  |  | 0 |  | BDSYSPRF | Process C&P orders | *RBTDFT |  | 2240 | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | CPPJOBQ | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 500 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
757 | BPS_PCKEML | Prt/Eml BOPIS Ord Pick Up | 530 | C |  |  | 0 |  | BDSYSPRF | Select Ord in STS->Prt Pick List & Eml Store for Ord Picking | *RBTDFT |  | 2240 | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | BPSJOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 530 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
867 | CPC_TXNPCK | CPC Txn pickup Trigger PT | 0 | C |  |  | 0 |  | MISOPR | Process CPC Tender transactions, Trigger - PT pick up Trans | *RBTDFT |  | 2240 | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 610 | 2330 | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
937 | SBL_ORDER | SBL Orders Generation | 0 | C |  |  | 0 |  | BDSYSPRF | Get SBL Order from CMIS Server -> IFS Transfer/Bell/In | *RBTDFT |  | 2240 | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | SBLJOBQ | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 500 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1099 | CXINVAUD | Web Service Inventory UPD | 0 | C |  |  | 0 |  | BDSYSPRF | Update Inventory in CMIS via Web Service frequently | *RBTDFT |  | 2240 | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | CMSJOBQ | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 455 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
966 | SYSDLTSPLF | delete spool files | 0 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 2241 | 2241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
682 | CPCDAILY | CPC Txn & Tender process | 0 | C |  |  | 0 |  | BDSYSPRF | Process CPC Tender & Transactions | *RBTDFT |  | 2245 | 2245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 515 | 2330 | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
818 | CPP_SHIP | CPC Ship Ack & Recv #2 | 0 | C |  |  | 0 |  | BDSYSPRF | CPC Ship Ack & create Receive | *RBTDFT |  | 2245 | 2245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | I3JOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 30 | 0 |  | 0 | *RBTDFT | 615 | 2301 | 20 | BUSDEP | [5 empty] | 0 | 88 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
722 | CPP_PO | CPC PO creation #1 | 0 | C |  |  | 0 |  | BDSYSPRF | Copy & Print Create PO | *RBTDFT |  | 2245 | 2245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | I3JOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 600 | 2301 | 20 | BUSDEP | [5 empty] | 0 | 88 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
598 | SYSSAGET | Trigger SAGET | 0 | C |  |  | 0 |  | MISOPR | Trigger the Patrick Townsend SAGET process-drop trigger file | *RBTDFT |  | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | ALLFTM100 | ALLFTM100 |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 405 | 2330 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
632 | SYSCFSGET | Trigger CFS get | 0 | C |  |  | 0 |  | MISOPR | Trigger the Patrick Townsend CFSget process. | *RBTDFT |  | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | ALLFTM100 | ALLFTM100 |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 405 | 2330 | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSDSTQCHK | DSTQ monitor | 0 | C |  |  | 0 |  | MISOPR | Per IS issue # 2569 | *RBTDFT |  | 2251 | 2251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *USRPRF |  | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 30 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
599 | SYSCHK992 | Check port 992 Close Wait | 0 | C |  |  | 0 |  | MISOPR | ticket to iseries engineering | *RBTDFT |  | 2251 | 2251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | SYSCHKCMT | Check Open Commits | 0 | C |  |  | 0 | + | MISOPR | Ticket to iSeries if in error, do not call out | *RBTDFT |  | 2251 | 2251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | QSYS |  | *RBTDFT | *RBTDFT | ITTOOLS | EVERY |  | X | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2012-10-17-14.12.43.953000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
753 | DYNSKU_P | FTP Dynamic Sku List | 2255 | C |  | H | 0 |  | BDSYSPRF | PT-Dynamic Sku List/Whitelist.CA (INVSKU/CH1X28='Y') | *RBTDFT |  | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
288 | RBT34504 | ROBOT Schedule of Jobs to | 700 | C |  |  | 0 |  | MISOPR | schedule of jobs to run | *RBTDFT |  | 2300 | 2300 | 1129 | 1500 | 2300 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 16 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
301 | ENDQPGMRSA | ENDQPGMRSA | 2300 | C |  |  | 0 | + | QSYSOPR | ENDSBS(QPGMR) for Saturday and Sunday @ 22:50 | *RBTDFT |  | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QSYSOPR | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QCTL | QSYS |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | CKQESLIN | Check Resource QESLINE | 1500 | C |  |  | 0 |  | *RBTDFT |  | *RBTDFT |  | 2300 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *JOBD |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | GALSYS | [5 empty] | 0 | 50 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000000 | CKQESPPL | Check Resource QESPPLIN | 1500 | C |  |  | 0 |  | *RBTDFT |  | *RBTDFT |  | 2300 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *JOBD |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | GALSYS | [5 empty] | 0 | 50 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
379 | RBCSTRTMON | Re-start RBCQSYSOPR | 700 | C |  |  | 0 |  | QSYSOPR |  | *RBTDFT |  | 2300 | 2300 | 1500 | 2300 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | RBTSLEEPER | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
418 | ESPCUO | Dwnld AS400 ESP Cust Info | 2300 | C |  | H | 0 |  | BDSYSPRF | Download new AS400 ESP Customer Information to Web Database | *RBTDFT |  | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 64 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
532 | CVM_CSAT | Send/Receive CVM Data | 20 | C |  | H | 0 |  | BDSYSPRF | Send/Receive CVM (Customer Service Satisfaction) Data | *RBTDFT |  | 2300 | 0 | 655 | 1300 | 1500 | 1700 | 1900 | 2100 | 2300 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 58 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
647 | SAI_INFW | Weekly FW Feed From WIS | 2300 | C |  |  | 0 |  | BDSYSPRF | Accepts final Inventory status and send variance to Finance. | *RBTDFT |  | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 79 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
916 | POSCLEANUP | POS IFS folder cleanup | 800 | C |  |  | 0 |  | BDSYSPRF | Process CPC Tender & Transactions | *RBTDFT |  | 2300 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
962 | AUT_OOSOPN | Auto Scan Batch Open | 1900 | C |  |  | 0 |  | BDSYSPRF | Contact BD Applications for support | *RBTDFT |  | 2300 | 2300 | 2000 | 2100 | 2200 | 2300 | 2345 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNINT1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1177 | CH_SSH | Check SSH Connection | 0 | C |  |  | 0 |  | BDSYSPRF | Check SSH Connection-POS and Copy Sales Posting-NETSTAT SSH | *RBTDFT |  | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 30 | 0 |  | 0 | *RBTDFT | 830 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1187 | DCA2_OTHER | *CA DownStreamAps *60 min | 0 | C |  |  | 0 |  | BDSYSPRF | .CA Other Posting 60 min | *RBTDFT |  | 2305 | 2305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | DCDIRECT | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT | 605 | 2315 | 72 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
55 | AR_UPDATE | Update A/R Sub-ledger | 745 | C |  |  | 0 | Q | BDSYSPRF | Read CSHINVL1 Sales Audit Invoice Interface file & upd A/R | *RBTDFT |  | 2330 | 2330 | 945 | 1145 | 2330 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBSDI_JB1 | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 30 | BUSDEP | [5 empty] | 0 | 9 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 1
227 | HLDJOBQS | Hold Job Queues | 230 | C |  |  | 0 | + | QSYSOPR | Executes HOLD1, HOLD2 or HOLD3 depending time and weekday | *RBTDFT |  | 2330 | 2330 | 2050 | 2330 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 38 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
512 | SYSCLNMAIL | Clean mail files | 2330 | C |  |  | 0 |  | MISOPR | Clean old imail files from IFS | *RBTDFT |  | 2330 | 2330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | TECSVCLIB |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
561 | SYSCLNTOWN | Clean townsend archive | 2330 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 2330 | 2330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | ALLFTMSTAP |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
730 | SYSCLNALLS | Clean Alliance/SSH | 2330 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 2330 | 2330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | ALLFTMSTAP |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1276 | SYSCLNRMA | Clean /APPS/RMA/IN | 2330 | C |  |  | 0 |  | MISOPR | Clean Excel files from /apps/rma/in folder keeping 90 days | *RBTDFT |  | 2330 | 2330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
231 | CLR_HDMSG | Clear Msq Que HD33MSG | 2345 | C |  |  | 0 |  | BDSYSPRF |  | *RBTDFT |  | 2345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL | 5 | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
769 | EMLPOSERR | POS File Mering Error | 2345 | C |  | H | 0 |  | BDSYSPRF | Email POS Download File Merging Err (SPEADR/POSERR) PRC812JQ | *RBTDFT |  | 2345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
963 | AUT_OOSCLS | Auto Scan Batch Close | 2345 | C |  |  | 0 |  | BDSYSPRF | Contact BD Applications for support | *RBTDFT |  | 2345 | 2345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNINT1 | IBMMODS |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1194 | DCA1_SLSWP | *CA Sales Sunday *10 min | 0 | C |  |  | 0 |  | BDSYSPRF | .CA Sales Posting 10 min | *RBTDFT |  | 2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | DCDIRECT | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 10 | 0 |  | 0 | *RBTDFT | 1200 | 2351 | 300 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
965 | AUT_OOSMIS | Track-Create Missing OOS | 2355 | C |  |  | 0 |  | BDSYSPRF | Please call BD-Applications on-call if any issues | *RBTDFT |  | 2355 | 2355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNINT1 | IBMMODS |  | TSSA | BUSDEP | *RBTDFT |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1231 | BPS_OK_NSU | SUN-Refresh BPS Alloc Qty | 0 | C |  |  | 0 | Q | BDSYSPRF | BLD OEBASLIB/OEBOPHDJ->QTEMP/OEBOPHDJBD->MMBUSLIB/OEBOPHDJBD | *RBTDFT |  | 2359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 130 | 2359 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
1250 | CH_MSGSUN2 | Check Job has MSGW-SUN-#2 | 0 | C |  |  | 0 |  | BDSYSPRF | PF:UTLMSGW3-Err;TBLFS10/OVOMSG-Sbs Name;TBLFLD/CELLA*-Phone# | *RBTDFT |  | 2359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 130 | 2359 | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2

## SUNJOBS_LATEST
SUN | ROBOT_JOB_NAME | ROBOT_JOB_DESC | SCHED_RUN_TIME_1 | ROBOT_JOB_TYPE | Action to take | SCHED_OVRRD | OS_JOB_DATE_VALUE | OS_JOB_DATE_CODE | OS_JOB_USER | ROBOT_JOB_NOTES | CALENDAR_NAME | DATE_OBJECT_NAME | START_TIME | SAVE_TIME | SCHED_RUN_TIME_1 | SCHED_RUN_TIME_2 | SCHED_RUN_TIME_3 | SCHED_RUN_TIME_4 | SCHED_RUN_TIME_5 | SCHED_RUN_TIME_6 | SCHED_RUN_TIME_7 | SCHED_RUN_TIME_8 | RUN_FLAG_MON | RUN_FLAG_TUE | RUN_FLAG_WED | RUN_FLAG_THU | RUN_FLAG_FRI | RUN_FLAG_SAT | RUN_FLAG_SUN | DAYNO_DAY_1 | DAYNO_DAY_2 | DAYNO_DAY_3 | DAYNO_DAY_4 | DAYNO_DAY_TYPE | OS_JOB_ACGCDE | IS_GROUP_MEMBER | ENV_NAME | OS_JOB_SWITCHES | OS_JOB_INQMSGRPY | OS_JOBD_NAME | OS_JOBD_LIB_NAME | OS_OUTQ_NAME | OS_OUTQ_LIB_NAME | SPLF_COPIES | OS_JOB_OUTPTY | LIBRARY_LIST_NAME | SPLF_PRINT_TEXT | OS_JOBQ_NAME | OS_JOBQ_LIB_NAME | OS_JOB_JOBPTY | OS_MSGQ_NAME | OS_MSGQ_LIB_NAME | OS_JOB_CURLIB | ADV_SCHED_CODE | SCHED_OVRRD_SAVED | ADV_SCHED_USED | SCHED_OVRRD | RUN_ON_NONWORK_DAY | USE_REPORT_DIST | JOB_IS_REACTIVE | INDAY_START_DATE | EVERY_INTERVAL | INDAY_INTERVAL | INDAY_DAY_TYPE | AT_POOL_SIZE | ALERT_DEVICE_NAME | EVERY_RANGE_START | EVERY_RANGE_END | HIST_RETENTION | SYSTEM_CREATED_ON | TEMPORARY_JOB_CODE | LINK_JOB_NUMBER | OPAL_NAME | LINK_TYPE | SUBMIT_DELAY_TYPE | CMD_SET_OID | APP_OID | OS_JOB_INLASPGRP | LAST_UPDATE_TIME | LAST_UPDATE_USER | PRD_INSTANCE_ID | JOB_HAS_MONITOR | AGENT_OID | AGENT_OUTPUT | USER_NAME | WORKING_DIRECTORY | RUNTIME_OS | ENV_VAR_CONTROL | OPAL_TEMP_JICD | MAX_RUN_DURATION | MAX_RUN_ACTION | OS_ROUTING_DATA
000000000058 | @SALESWEND | Sales Process WeekEnd | 0 | G |  |  | 0 | Q | BDSYSPRF | Monitor Upload lib for D* files and submit SALESsssss jobs | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBSDI_UPL | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | BUSDEP | [5 empty] | 0 | 2 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000282 | RPL_SUGQTY | CALCULATION OF ORDER QTY. | 0 | C |  |  | 0 | + | BDSYSPRF | React on XREF_UPDAT which depends on completion of WK_RPL??? | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | TSSA | BUSDEP | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000312 | PRODSUDP | Daily Sunday Backup | 0 | C |  |  | 0 | + | MISOPR | Daily Production Backup for Sunday | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | BRMSJOBD | QGPL | PRODSOX | QGPL | 0 | 0 | *RBTDFT |  | BRMSJOBQ | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  |  | Y | Y | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 46 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000348 | PRODSOX2DP | PRODSOX to RPT2WEB | 0 | C |  |  | 0 |  | QSYSOPR | Backup reports from outq PRODSOX to RBT2WEB for Audit. | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | ITTOOLS | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 54 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000392 | SYSSTRSBS | Start System Sunday | 0 | C |  |  | 0 |  | QSYSOPR | Start QINTER/QPGMR/LASER/ICASRV & all JOBQ after DAY_CLS_RN | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *USRPRF |  | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000399 | SUNDAY2 | Post Sync-Point Jobs +HBT | 0 | C |  |  | 0 |  | QSYSOPR | ***Job#244(@00:45)=HBT_DWND_P(@00:15)**Stop it if FTP is DWN | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QSYSOPR | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT | 0005 | 0800 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000400 | JDA | Unrestrict JDA | 0 | C |  |  | 0 |  | BDSYSPRF | This job will open JDA to users after Sunday processing | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QSYSOPR | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000566 | SYSMAFSBMW | Submit Final weekly jobs | 0 | C |  |  | 0 |  | BDSYSPRF | final set of jobs that React on Sunday jobs completing. | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000578 | SYSMAFSBMM | Submit Final monthly jobs | 0 | C |  |  | 0 |  | BDSYSPRF | final set of jobs that React on Sunday jobs completing. | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000242 | SYSCCCAUTH | Run Agent resetauth.sh | 0 | C |  | H | 0 | + | MISOPR |  | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | H | Y | N | 0 | 0 | 480 | 0 |  | 0 | *RBTDFT | 0001 | 2200 | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2011-04-08-09.34.44.949000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001337 | VRM_WKND | VRM Weekend run | 0 | C |  |  | 0 |  | BDSYSPRF | This job will run VRM Recalculation Weekend processing | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QSYSOPR | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000816 | SYSOPSMAIL | EMAIL GOC after WKend Prc | 0 | C |  | H | 0 |  | BDSYSPRF | Email GOC after Sunday Process & CSG conversion are done | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X | H | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000941 | RBL_LNDCT2 | Rebuild Store Landed Cost | 0 | C |  |  | 0 |  | BDSYSPRF | Rebld Store Landed Cost File SUNSLC (React on JDA Robot Job) | *RBTDFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001249 | CH_MSGSUN1 | Check Job has MSGW-SUN-#1 | 0 | C |  |  | 0 |  | BDSYSPRF | PF:UTLMSGW3-Err;TBLFS10/OVOMSG-Sbs Name;TBLFLD/CELLA*-Phone# | *RBTDFT |  | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0001 | 0129 | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000493 | SYSRSFCHK | Check RSF communications | 0 | C |  | H | 0 |  | MISOPR | Check to see if RSF is waiting and kill if over 60 minutes | *RBTDFT |  | 1001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | ITTOOLS | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | ITTOOLS | EVERY |  | X | H | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001229 | BPS_AVLQTY | H*Refresh BOPIS Avail Qty | 0 | C |  | H | 0 | Q | BDSYSPRF | BLD OEBASLIB/OEBOPHDJ->QTEMP/OEBOPHDJBD->MMBUSLIB/OEBOPHDJBD | *RBTDFT |  | 1510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | H | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0430 | 2359 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000927 | POS_TENDER | H*Populate AN# to CSHTND | 0 | C |  | H | 0 |  | BDSYSPRF | 1)XPSTND/XTAN#-->CSHTND/CSCRD# 2)PLCTND/AN#-->CSHTND/CSCRD# | *RBTDFT |  | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | POSDFILE | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | H | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 0455 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001179 | OVR_PRINTQ | Override Store Printq | 0 | C |  |  | 0 |  | BDSYSPRF | Override Store Print Queue, PF:OVROUTQ, TBLFLD/PRTNAM | *RBTDFT |  | 1713 | 1713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 1 | 0 |  | 0 | *RBTDFT | 0600 | 2359 | 20 | BUSDEP | [5 empty] | 0 | 88 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001091 | F_ETS_ORD | Send Tec Ord to ETS Servr | 0 | C |  |  | 0 |  | MISOPR | Send Tec Order to ETS Server (FTP 10.18.9.46/ftp_ets_prd) | *RBTDFT |  | 1713 | 1713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | JDAJOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 1 | 0 |  | 0 | *RBTDFT | 0530 | 2330 | 20 | BUSDEP | [5 empty] | 0 | 88 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000682 | CPCDAILY | CPC Txn & Tender process | 0 | C |  |  | 0 |  | BDSYSPRF | Process CPC Tender & Transactions | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 0515 | 2330 | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000374 | SYSCHKSYS | System Resource Checks | 0 | G |  |  | 0 |  | *RBTDFT |  | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QSYSNOMAX | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 0500 | 2000 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000467 | OF_IN_CNF | Confirmation File Retrvl | 0 | C |  |  | 0 | + | BDSYSPRF | Confirmation File Retrieval (.CNF) | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 30 | 0 |  | 0 | *RBTDFT | 0845 | 2045 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000590 | SYSCHKJQE3 | Check E3 resource jobqs | 0 | C |  |  | 0 |  | *RBTDFT | Check specific E3 jobqs different time frame than SYSCHKSYS | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *JOBD |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 1300 | 2200 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000818 | CPP_SHIP | CPC Ship Ack & Recv #2 | 0 | C |  |  | 0 |  | BDSYSPRF | CPC Ship Ack & create Receive | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | I3JOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 30 | 0 |  | 0 | *RBTDFT | 0615 | 2301 | 20 | BUSDEP | [5 empty] | 0 | 88 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000663 | SOSCFM | *Spec Order Payment Confr | 0 | C |  |  | 0 |  | MISOPR | Special Order Payment Confirmation | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0530 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000722 | CPP_PO | CPC PO creation #1 | 0 | C |  |  | 0 |  | BDSYSPRF | Copy & Print Create PO | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | I3JOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 0600 | 2301 | 20 | BUSDEP | [5 empty] | 0 | 88 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000723 | CPP_KIOSK | ***Copy & Print Kiosk Ord | 0 | C |  |  | 0 |  | MISOPR | Retreive Copy & Print Kiosk orders | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | ETLJOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0530 | 2330 | 20 | BUSDEP | [5 empty] | 0 | 88 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000729 | CPS_ORDRTV | Extract C&P Orders for PR | 0 | C |  |  | 0 |  | BDSYSPRF | Process C&P orders | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | CPPJOBQ | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0500 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000937 | SBL_ORDER | SBL Orders Generation | 0 | C |  |  | 0 |  | BDSYSPRF | Get SBL Order from CMIS Server -> IFS Transfer/Bell/In | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | SBLJOBQ | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0500 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001099 | CXINVAUD | Web Service Inventory UPD | 0 | C |  |  | 0 |  | BDSYSPRF | Update Inventory in CMIS via Web Service frequently | *RBTDFT |  | 1715 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | CMSJOBQ | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0455 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000599 | SYSCHK992 | Check port 992 Close Wait | 0 | C |  |  | 0 |  | MISOPR | ticket to iseries engineering | *RBTDFT |  | 1716 | 1716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000966 | SYSDLTSPLF | delete spool files | 0 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 1716 | 1716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000357 | STRPRT | Start all printers | 0 | C |  |  | 0 |  | *RBTDFT | Start all rmt and prt writers | *RBTDFT |  | 1720 | 1720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 10 | 0 |  | 0 | *RBTDFT | 0500 | 2300 | 20 | BUSDEP | [5 empty] | 0 | 60 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000598 | SYSSAGET | Trigger SAGET | 0 | C |  |  | 0 |  | MISOPR | Trigger the Patrick Townsend SAGET process-drop trigger file | *RBTDFT |  | 1720 | 1720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | ALLFTM100 | ALLFTM100 |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 0405 | 2330 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000632 | SYSCFSGET | Trigger CFS get | 0 | C |  |  | 0 |  | MISOPR | Trigger the Patrick Townsend CFSget process. | *RBTDFT |  | 1720 | 1720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | ALLFTM100 | ALLFTM100 |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 0405 | 2330 | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000518 | @XMLSLS | XML POS Process XPS=>USI* | 0 | C |  |  | 0 |  | BDSYSPRF | XML POS Processing in Busdep | *RBTDFT |  | 1725 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | POSWALKER | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 0455 | 2326 | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000867 | CPC_TXNPCK | CPC Txn pickup Trigger PT | 0 | C |  |  | 0 |  | MISOPR | Process CPC Tender transactions, Trigger - PT pick up Trans | *RBTDFT |  | 1725 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 0610 | 2330 | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000460 | OF_OUT_GI | Journal Interface Oracle | 0 | C |  |  | 0 | + | BDSYSPRF | GI - GL Journal Interface to Oracle | *RBTDFT |  | 1730 | 1730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEOUT | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT | 0830 | 2030 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000558 | SYSPQMON | fax queue monitor | 0 | C |  |  | 0 |  | MISOPR | Can be cancelled with ticket to iseries, do not call out | *RBTDFT |  | 1730 | 1730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | QSYS |  | *RBTDFT | *RBTDFT | ITTOOLS | EVERY |  | X |  | Y | N | 0 | 0 | 30 | 0 |  | 0 | *RBTDFT | 0600 | 2200 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001177 | CH_SSH | Check SSH Connection | 0 | C |  |  | 0 |  | BDSYSPRF | Check SSH Connection-POS and Copy Sales Posting-NETSTAT SSH | *RBTDFT |  | 1730 | 1730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 30 | 0 |  | 0 | *RBTDFT | 0830 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000197 | SYSDSTQCHK | DSTQ monitor | 0 | C |  |  | 0 |  | MISOPR | Per IS issue # 2569 | *RBTDFT |  | 1731 | 1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *USRPRF |  | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 30 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001222 | INVBAX_API | H*API INVBAX | 0 | C |  | H | 0 |  | BDSYSPRF | API CALL for Nonsalable | *RBTDFT |  | 1755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | POSWALKER | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | H | Y | N | 0 | 0 | 15 | 0 |  | 0 | *RBTDFT | 0455 | 2326 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000459 | OF_OUT_AI | *Invoice Interface Oracle | 0 | C |  |  | 0 | + | BDSYSPRF | AI - AP Invoice Interface to Oracle (CSG Inv after CSG conv) | *RBTDFT |  | 1800 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEOUT | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT | 0800 | 2000 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000255 | SYSCHKCMT | Check Open Commits | 0 | C |  |  | 0 | + | MISOPR | Ticket to iSeries if in error, do not call out | *RBTDFT |  | 1801 | 1801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | QSYS |  | *RBTDFT | *RBTDFT | ITTOOLS | EVERY |  | X |  | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2012-10-17-14.12.43.953000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001187 | DCA2_OTHER | *CA DownStreamAps *60 min | 0 | C |  |  | 0 |  | BDSYSPRF | .CA Other Posting 60 min | *RBTDFT |  | 1805 | 1805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | DCDIRECT | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT | 0605 | 2315 | 72 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000838 | SYSCHKCQ | Check RBNCQ record count | 0 | C |  | H | 0 |  | MISOPR | Check for RBNCQ records > 0 | *RBTDFT |  | 2001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | H | Y | N | 0 | 0 | 120 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001194 | DCA1_SLSWP | *CA Sales Sunday *10 min | 0 | C |  |  | 0 |  | BDSYSPRF | .CA Sales Posting 10 min | *RBTDFT |  | 2343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | DCDIRECT | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 10 | 0 |  | 0 | *RBTDFT | 1200 | 2345 | 300 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001231 | BPS_OK_NSU | SUN-Refresh BPS Alloc Qty | 0 | C |  |  | 0 | Q | BDSYSPRF | BLD OEBASLIB/OEBOPHDJ->QTEMP/OEBOPHDJBD->MMBUSLIB/OEBOPHDJBD | *RBTDFT |  | 2359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0130 | 2359 | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001250 | CH_MSGSUN2 | Check Job has MSGW-SUN-#2 | 0 | C |  |  | 0 |  | BDSYSPRF | PF:UTLMSGW3-Err;TBLFS10/OVOMSG-Sbs Name;TBLFLD/CELLA*-Phone# | *RBTDFT |  | 2359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0130 | 2359 | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001277 | HBT_CUS#WP | *Purge/Create TXECCT WKN | 1 | C |  |  | 0 |  | BDSYSPRF | Purge TXECCT & Create TXECCT Rec for New Tax Exemption Cust. | *RBTDFT |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000331 | PERFNAVDR | Data Reduction | 5 | C |  | H | 0 | + | MISOPR | Performance Navigator Data Reduction | *RBTDFT |  | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | PERFNAV | MPGLIB | MIS | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *CRTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 51 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000437 | ZAACL7701 | System Values | 5 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000192 | SYSJOBTBL | Check job table size | 5 | C |  |  | 0 |  | QSYSOPR | CHG#38140 | *RBTDFT |  | 1800 | 1800 | 5 | 600 | 1200 | 1800 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | GALSYS | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000533 | SYSJRNCHK | Journal Monitor Program | 5 | C |  | H | 0 |  | QSYSOPR | Journal Monitor Program | *RBTDFT |  | 1800 | 0 | 5 | 600 | 1200 | 1800 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000439 | ZAACL7703 | Network Attributes | 10 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000441 | ZAACL7715 | Local Hardware | 15 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000440 | ZAACL7709 | Output Queue Descriptions | 20 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000532 | CVM_CSAT | H*Send/Receive CVM Data | 20 | C | Do | H | 0 |  | BDSYSPRF | Send/Receive CVM (Customer Service Satisfaction) Data | *RBTDFT |  | 655 | 0 | 20 | 655 | 1300 | 1500 | 1700 | 1900 | 2100 | 2300 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 58 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000452 | ZAACL93 | Network job entries | 25 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000451 | ZAACL88 | Dist direct entries | 30 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | AAJOBD | PSAUDIT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | SBMSYSH | [5 empty] | 0 | 67 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001349 | PERFNAVDR | Perf Nav Data Reduction | 30 | C |  | H | 0 |  | MPGSCHRUN |  | *RBTDFT |  | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | PERFNAV | MPGLIB | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QSYSNOMAX | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 105 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000897 | SYSILMTSSC | ILMT Software Scan | 100 | C |  |  | 0 |  | SECMANISH | ILMT Software and Package Scan | *RBTDFT |  | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | ITTOOLS | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001352 | PERFNAVPM | Perf Nav Monitor | 100 | C |  | H | 0 |  | MPGSCHRUN |  | *RBTDFT |  | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | PERFNAV | MPGLIB | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QSYSNOMAX | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 105 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000388 | SYSCHGTIME | DST TIME CHANGE -1 HR | 155 | C |  | H | 0 |  | MISOPR | Fall behind 1 hr | *RBTDFT |  | 155 | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | MANISH_CEL |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 3
000000000629 | SYSUSRPRF2 | DSPUSRPRF to ITTOOLS | 200 | C |  |  | 0 |  | MISOPR | DSPUSRPRF to ITTOOLS/USRPRF | *RBTDFT |  | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000227 | HLDJOBQS | Hold Job Queues | 230 | C |  |  | 0 | + | QSYSOPR | Executes HOLD1, HOLD2 or HOLD3 depending time and weekday | *RBTDFT |  | 2050 | 2050 | 230 | 2050 | 2330 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 38 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000233 | SYSSIAMUID | SIAM UID Update | 300 | C |  | H | 0 |  | MISOPR | Process SIAM UID updates | *RBTDFT |  | 1900 | 0 | 300 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000332 | PERFNAVDS | Lib and Obj Sizes | 330 | C |  | H | 0 | + | MISOPR | Performance Navigator Lib and Obj Sizes | *RBTDFT |  | 330 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | PERFNAV | MPGLIB | MIS | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *CRTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 51 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001351 | PERFNAVDS | PN Lib and obj sizes | 330 | C |  | H | 0 |  | MPGSCHRUN |  | *RBTDFT |  | 330 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | PERFNAV | MPGLIB | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QSYSNOMAX | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 105 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000762 | BPS831CL | *Operational Excellence | 400 | C |  |  | 0 |  | BDSYSPRF | BOPIS Retail Operational Excellence Reporting | *RBTDFT |  | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 91 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001339 | CATMANLSTD | Dly-Get CATMAN File LST | 405 | C |  |  | 0 |  | MISOPR | GET BY SERVER FILE LIST VIA EMAIL FOR REPLENON/OFF BY->AS400 | *RBTDFT |  | 405 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y |  | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | MANISH_CEL |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 3
000000001342 | CATMANGETD | Dly-Get CATMAN Files | 405 | C |  |  | 0 |  | MISOPR | GET BY FILES DAILY REPLENOFF AND REPLENON ONLY BY->AS400 | *RBTDFT |  | 405 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y |  | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | MANISH_CEL |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 3
000000000254 | MOOSEAGGR2 | *MOOSE AGGREGATE UPD WKN | 410 | C |  |  | 0 | + | BDSYSPRF |  | *RBTDFT |  | 410 | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000269 | E3_FREEZE | *E3 DAY-END PROCESS | 415 | C |  |  | 0 | + | BDSYSPRF | E3 DAY-END PROCESS | *RBTDFT |  | 415 | 0 | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | E3PROD | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000270 | E3_DAYEND | *E3 DAY-END PROCESS | 430 | C |  |  | 0 | + | BDSYSPRF | E3 DAY-END PROCESS | *RBTDFT |  | 430 | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | E3PROD | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000528 | POS_PURGE | O*Purge Old Sales Data | 430 | C |  |  | 0 |  | BDSYSPRF | Purge old sales data | *RBTDFT |  | 430 | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 58 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001221 | INVBAX_API | H*API Call to upd invbax | 445 | C |  | H | 0 |  | *RBTDFT | Update INVBAX and call API for nonsalble | *RBTDFT |  | 445 | 0 | 445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | H | Y | N | 0 | 0 | 10 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000555 | PERFNAVIFS | IFS Size Collection | 500 | C |  | H | 0 | + | MISOPR | Performance Navigator IFS Size Collection | *RBTDFT |  | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | PERFNAV | MPGLIB | MIS | QGPL | 0 | 0 | *JOBD |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 51 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000724 | NONSALE_UP | Update the Status of | 500 | C |  |  | 0 |  | BDSYSPRF | Update the Status of product hold system files | *RBTDFT |  | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001353 | PERFNAVIFS | Perf Nav IFS size coll | 500 | C |  | H | 0 |  | MPGSCHRUN |  | *RBTDFT |  | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | PERFNAV | MPGLIB | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QSYSNOMAX | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 105 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000271 | E3TWAIT | *E3 DAY-END PROCESS | 515 | C |  |  | 0 | + | E3USER | E3 DAY-END PROCESS | *RBTDFT |  | 515 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | E3PROD | QGPL | E3PROD | QGPL | 0 | 0 | *RBTDFT |  | E3PROD | QGPL |  | E3USER | QUSRSYS | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000527 | SYSGENRBT | re-gen robot message file | 530 | C |  | H | 0 |  | MISOPR | Cancel if in error with ticket to iSeries Eng | *RBTDFT |  | 530 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Y |  |  |  | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | ITTOOLS |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000728 | CPS_DAILY | Extract Sales for C&P SO | 530 | C |  |  | 0 |  | BDSYSPRF | Create work files for C&P Reporting (Special Order) | *RBTDFT |  | 530 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001188 | DCA3_DAILY | *CA Morning Setup *Once | 530 | C |  |  | 0 |  | BDSYSPRF | .CA Daily Popluate Sales Reversal Table(DCANST) and ESPCRT | *RBTDFT |  | 530 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | DCDIRECT | QGPL | 4 | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000757 | BPS_PCKEML | Prt/Eml BOPIS Ord Pick Up | 530 | C |  |  | 0 |  | BDSYSPRF | Select Ord in STS->Prt Pick List & Eml Store for Ord Picking | *RBTDFT |  | 1715 | 1715 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | BPSJOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0530 | 2345 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000170 | POSLOG | Monitoring POS Polling | 545 | C |  |  | 0 | + | BDSYSPRF |  | *RBTDFT |  | 545 | 0 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 4 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000495 | SYSCHKSUN | check sunrise | 545 | C |  | H | 0 |  | MISOPR |  | *RBTDFT |  | 545 | 0 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *USRPRF |  | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000759 | BPS_INVENT | Eml BPS Ord Activity Rpt | 545 | C |  |  | 0 |  | BDSYSPRF | Second Lvl Submit Email Rpt BPS825 by Str in JOBQ SKU_UPDATE | *RBTDFT |  | 545 | 0 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001192 | F_GXDLY2TB | *FTP Google Master TBL#2 | 550 | C |  |  | 0 |  | BDSYSPRF | FTP Google Master Tables -> PC FTP Site/google ***Before 9AM | *RBTDFT |  | 550 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001180 | F_GXDLY1TB | *FTP Google Master TBL#1 | 558 | C |  |  | 0 |  | BDSYSPRF | FTP PC/google(MOOMST & MOOSUMD in MOOSEAGGR1/2)***Before 9AM | *RBTDFT |  | 558 | 0 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000486 | SYSLOGFTP | FTP Network Transactions | 600 | C |  | H | 0 |  | MISOPR |  | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000499 | SYSRRMTRAN | Capture all Network Trans | 600 | C |  | H | 0 |  | MISOPR |  | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000511 | MKB_REPORT | H*Market Basket Report | 600 | C |  | H | 0 |  | BDSYSPRF | MKB Report runs daily | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000614 | SAI_MAC | *SA Daily MAC Interface | 600 | C |  |  | 0 |  | BDSYSPRF | Outbound MAC Daily Feed To Alpha | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000834 | ETS_DAILY | ETS-WebErr & ESPtablesFTP | 600 | C |  |  | 0 |  | BDSYSPRF | ETS-WebError & ESP-Tables to ETS | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000836 | SE_DAILY | *Send Daily Feeds for SE | 600 | C |  |  | 0 |  | BDSYSPRF | Send Daily Feeds for SE Active SKU | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y |  | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000865 | SKUEXT2 | *Sku Master ext part 2 | 600 | C |  |  | 0 |  | BDSYSPRF | SKU master extension file over to Sunrise, daily, | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000923 | UP_GCCOM | Refresh Gift Card Com% | 600 | C |  |  | 0 |  | BDSYSPRF | Refresh Giftcard Commission Rate base of reversal Sku Retail | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 83 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001185 | CBT_DAILY | *File feed transmission | 600 | C |  |  | 0 |  | BDSYSPRF | Send daily feed to UPS CHG000615788 | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001035 | MPOS_330WP | H*Send Full PLU-MPOS-330 | 600 | C |  | H | 0 |  | BDSYSPRF | Send Full PLU Download Files to Mobile POS Server(Store 330) | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001296 | CLR_IFSALL | O*Clear IFS see IFSLIST | 600 | C |  |  | 0 |  | MISOPR | Submit jobs for each IFS folder from IFSLIST to clean up | *RBTDFT |  | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 83 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000760 | BPS_ALLOC | H*Bopis Allocation Bucket | 600 | C |  | H | 0 |  | BDSYSPRF | *Not Used - Bopis Reset Bopis Allocation Bucket | *RBTDFT |  | 1040 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X | H | Y | N | 0 | 0 | 5 | 0 |  | 0 | *RBTDFT | 0600 | 2340 | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000642 | SYSODBCPNT | Check for ODBC Exit Prog | 600 | C |  |  | 0 | + | MISOPR |  | *RBTDFT |  | 1800 | 1800 | 600 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2011-05-11-10.51.40.559000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000497 | ST_TYPE27 | *Sell Thru Type 27 entry | 600 | C |  |  | 0 |  | BDSYSPRF | Sell through type 27 entries | *RBTDFT |  | 2000 | 2000 | 600 | 655 | 2000 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 66 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001170 | AGILENCEWP | *Send Agilence LP File WN | 615 | C |  |  | 0 |  | BDSYSPRF | SEND POS XML Trn/Tnd to LP-Weekend, Create Trigger at ENDPGM | *RBTDFT |  | 615 | 0 | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000031 | AUTO_FTP | *Resend Missed POS Price | 625 | C |  |  | 0 | Q | BDSYSPRF | Automatically Resend Missing Pending Price Files to POS | *RBTDFT |  | 625 | 0 | 625 | 745 | 845 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBSDI_DWN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 50 | BUSDEP | [5 empty] | 0 | 3 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 1
000000000888 | CLD_TXNPCK | H*StoragePipe Ord Trigger | 630 | C |  | H | 0 |  | BDSYSPRF | Get Storage Pipe Order Detail(R41/50) - Can be run on demand | *RBTDFT |  | 630 | 0 | 630 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000211 | QA_REFRESH | QA Lab Daily PLU Updates | 630 | C |  |  | 0 |  | BDSYSPRF |  | *RBTDFT |  | 630 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 7 | BUSDEP | [5 empty] | 0 | 32 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000241 | RBT650001 | Completion Message Listin | 630 | C |  |  | 0 |  | *RBTDFT | Job Completion Report | *RBTDFT |  | 630 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 16 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000245 | PPA_DATE | Roll Prepaid Activation D | 630 | C |  |  | 0 | Q | BDSYSPRF | OK to Cancel and inform support person next day | *RBTDFT |  | 630 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | BUSDEP | [5 empty] | 0 | 17 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000338 | RBT651DP | Good Morning Report | 630 | C |  |  | 0 |  | *RBTDFT | Good Morning Report | *RBTDFT |  | 630 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 52 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000535 | SYSJRNACT | Log Journal Rcvr Activity | 630 | C |  | H | 0 |  | MIMIXOWN | Log Previous Day's Journal Receiver Transaction Activity | *RBTDFT |  | 630 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QSYSNOMAX | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000239 | SYSSSHCHK | AML SSH Config Check | 630 | C |  |  | 0 | + | MISOPR |  | *RBTDFT |  | 630 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | PENTATECHQ | QUSRSYS | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2010-10-15-11.47.55.336000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000948 | CLR_IFSWP | O*Clear IFS TMP Fldr-WN | 630 | C |  |  | 0 |  | MISOPR | Clear IFS tmp folder-Weekend | *RBTDFT |  | 630 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001166 | CXTBLBDG | *Giftcard Reversal TBLMDG | 630 | C |  |  | 0 | + | BDSYSPRF | Send Giftcard Reversal Table TBLMDG to CMIS | *RBTDFT |  | 630 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | CMIS | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 14 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001172 | F_PDBRCLWP | *FTP RCL Fee-> Google WN | 645 | C |  |  | 0 |  | BDSYSPRF | FTP Recycle Fee to Google Analytic (before 7:15am) (9am-5pm) | *RBTDFT |  | 645 | 0 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001174 | F_PDBVNDWP | *FTP Vend Master-> PDB WN | 645 | C |  |  | 0 |  | BDSYSPRF | FTP Vend Master to Product Data Base (before 7:15am) | *RBTDFT |  | 645 | 0 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000624 | RMAFTP | RTV Get Inbound Email ATT | 645 | C |  |  | 0 |  | BDSYSPRF | Creates RMA# for email RTV | *RBTDFT |  | 1800 | 1800 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT | EVERY |  | X |  | Y | N | 0 | 0 | 60 | 0 |  | 0 | *RBTDFT | 0600 | 2000 | 20 | BUSDEP | [5 empty] | 0 | 76 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000367 | AS2RESETDP | *Reset AS2 Comm. Line | 655 | C |  |  | 0 |  | TRAILBLAZE | Reset AS2 Communication Line Everyday | *RBTDFT |  | 655 | 0 | 655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 56 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000419 | ESPCUA | H*Upld AS400 WebESP Cust | 655 | C |  | H | 0 |  | BDSYSPRF | Upload new AS400 ESP Cust Update Status to AS400 | *RBTDFT |  | 655 | 0 | 655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 64 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000684 | AIRM_DAILY | H*Send Daily Feed AIRMILE | 700 | C |  | H | 0 |  | BDSYSPRF | Send Daily Feeds for AirMiles(Sales Data sends last 14 days) | *RBTDFT |  | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000864 | EMPMSTWP | *Upl Empl Mst SLSEMPWK-WP | 700 | C |  |  | 0 | + | MISOPR | PeopleSoft Extract Data @ 6 am - Ok to rerun if this fails | *RBTDFT |  | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000917 | CHKBAL_BLD | CHECK INVBAL REBUILD | 700 | C |  |  | 0 | + | BDSYSPRF | CHECK FOR INVBAL REBUILD COMPLETION | *RBTDFT |  | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000925 | PPR_OH_WP | PPR On Hand - rolling-SUN | 700 | C |  |  | 0 |  | BDSYSPRF | Update PPR On Hand - rolling 90 days (Sunday) | *RBTDFT |  | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 58 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001243 | UP_MEMCONT | *Upd Sku Memory Content | 700 | C |  |  | 0 |  | BDSYSPRF | Upd Sku Memory Content Flag INVSKU->ebay Trf OL RTN,Ok Rerun | *RBTDFT |  | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001093 | FCHN_SKUWP | H*CHN Sku Lst-Fill Rpt-WN | 700 | C |  | H | 0 |  | BDSYSPRF | Build Sku List for Store Fill Rpt-Run before FD??_SLS Job | *RBTDFT |  | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001285 | TSS_ORDPOP | Zuora Order Number Popula | 700 | C |  |  | 0 |  | BDSYSPRF | Call BUSDEP Application in case of MSGW | *RBTDFT |  | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000288 | RBT34504 | ROBOT Schedule of Jobs to | 700 | C |  |  | 0 |  | MISOPR | schedule of jobs to run | *RBTDFT |  | 2300 | 2300 | 700 | 1129 | 1500 | 2300 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 16 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000379 | RBCSTRTMON | Re-start RBCQSYSOPR | 700 | C |  |  | 0 |  | QSYSOPR |  | *RBTDFT |  | 2300 | 2300 | 700 | 1500 | 2300 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | RBTSLEEPER | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000260 | HAMILTON | *CREATE CITICORP FILES | 715 | C |  |  | 0 | + | BDSYSPRF | CREATE CITICORP FILES IN BUSDEP FOLDER | *RBTDFT |  | 715 | 0 | 715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000672 | DESJARDINS | *Outbound Line Item Dtl | 730 | C |  |  | 0 |  | BDSYSPRF | Create Line Item Detail file in STORE/INVOHQTY by 1:45PM | *RBTDFT |  | 730 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001176 | F_ORDSTSYD | Copy FC Order Sts Journal | 730 | C |  |  | 0 |  | BDSYSPRF | Copy FC Order Sts Journal Up to Yesterday Only from Sunrise | *RBTDFT |  | 730 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001183 | EM_PDNVFO | Eml Pending Sell Thr Rpt | 730 | C |  |  | 0 |  | BDSYSPRF | Offer Created on Yesterday only Speadr60:VFOPNDEML,MENSTM/8 | *RBTDFT |  | 730 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001289 | EM_UIDCHWP | Eml User ID Chg Err -WKN | 730 | C |  |  | 0 |  | BDSYSPRF | Email User ID Change Error-EMPRETXT File(SPEADR60/USERIDCHG) | *RBTDFT |  | 730 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000055 | AR_UPDATE | Update A/R Sub-ledger | 745 | C |  |  | 0 | Q | BDSYSPRF | Read CSHINVL1 Sales Audit Invoice Interface file & upd A/R | *RBTDFT |  | 2330 | 2330 | 745 | 945 | 1145 | 2330 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBSDI_JB1 | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 30 | BUSDEP | [5 empty] | 0 | 9 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 1
000000000351 | EM_PRC2DP | *Email Price Chg-Follw Up | 800 | C |  |  | 0 |  | BDSYSPRF | Email the Daily Item Price Change to the Delivery Group. | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 57 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000212 | SYSUSRPRF | DSPUSRPRF to ITTOOLS | 800 | C |  | H | 0 |  | MISOPR | DSPUSRPRF to SECMANISH/BUSDEPUSRS | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000505 | PCA_STRCNT | Thur->Sun Inventory Count | 800 | C |  |  | 0 |  | BDSYSPRF | Thur->Sun Inventory Count | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 70 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000596 | TRF_AUTRCV | Auto Rec. Old Trfs | 800 | C |  |  | 0 |  | BDSYSPRF | Auto Receive Outdated Transfers. | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000011 | SYSSSLCHK | Check for SSL v2 | 800 | C |  |  | 0 | + | MISOPR | Disable SSL v2 and/or Weak Ciphers if enabled. | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | PENTATECHQ | QUSRSYS | 0 | 0 | *RBTDFT |  | QSYSNOMAX | QSYS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2010-04-30-07.47.07.564000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000747 | KRONOSWP | *WKLY:Store Data->Kronos | 800 | C |  |  | 0 |  | BDSYSPRF | Send POS/PO REC/TRF/RTV To Kronos for Store Labour Schedule | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001338 | E3_RPLEN | *E3 Repln*Before E3_Frz | 800 | C |  |  | 0 | + | BDSYSPRF | FTP ReplenOn/ReplenOff Files from PC, Done before E3_Freeze | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | E3PROD | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 96 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000804 | SKU_TRNSLN | SKU French Translation | 800 | C |  |  | 0 |  | BDSYSPRF | SKU French Translation Outbound & Inbound | *RBTDFT |  | 800 | 0 | 800 | 1100 | 1400 | 1700 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 92 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000814 | F_ESPTBL | H*FTP ESP TABLE TO ETS | 800 | C |  | H | 0 |  | BDSYSPRF | FTP ESP TABLES TO ETS SYSTEM-To be removed | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000870 | CRT_R40CTL | H*Not Use-Run in CPCDaily | 800 | C |  | H | 0 |  | BDSYSPRF | Auto Create Missing R40 (CPC) Control Record in /POS/XMLCPC | *RBTDFT |  | 800 | 0 | 800 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000972 | PRGE_PRCZN | Purge Expired PRCZNO rcds | 800 | C |  |  | 0 |  | BDSYSPRF | Cancel the job and call BD Applications in a case of an issu | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 100 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001079 | CXDLYSUN | Daily SLS CMIS-Sunday | 800 | C |  |  | 0 | + | BDSYSPRF | Daily SLS to CMIS - Include Create ESP Ord# & Cust# ESM150CL | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | CMIS | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 14 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001318 | SYSPRFDSP | DSPUSRPRF to BUSDEPUSRS | 800 | C |  |  | 0 |  | SECMANISH | DSPUSRPRF to SECMANISH/BUSDEPUSRS | *RBTDFT |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000916 | POSCLEANUP | POS IFS folder cleanup | 800 | C |  |  | 0 |  | BDSYSPRF | Process CPC Tender & Transactions | *RBTDFT |  | 2300 | 2300 | 800 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000264 | CSH900 | PRICE OVERRIDE REPORT | 815 | C |  |  | 0 | + | BDSYSPRF | PRICE OVERRIDE REPORT TO ALL STORES | *RBTDFT |  | 815 | 0 | 815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000456 | CKMONSWAW | Check MONSWABRM for SLA | 815 | C |  |  | 0 |  | *RBTDFT | Check to see if there is a MONSWABRM job still running Sun | *RBTDFT |  | 815 | 0 | 815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP |  |  | CKMONSWA |  |  | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000701 | EMSLSVARWP | Email Sales Var Sum-WP | 815 | C |  |  | 0 |  | BDSYSPRF | Email Sales Audit vs Inv Audit Variance - SPEADR60/EMLSTRVAR | *RBTDFT |  | 815 | 0 | 815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000725 | AS2_CHKCOM | H*Check AS2 Comm. Line | 815 | C |  | H | 0 |  | BDSYSPRF | OK to Cancel/ Inform Pager Support in Development Group | *RBTDFT |  | 815 | 0 | 815 | 915 | 1215 | 1615 | 1715 | 1915 | 2015 | 2130 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 87 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000783 | CPYAHS_P | *Upload Auto Hub&Spk Data | 815 | C |  |  | 0 |  | BDSYSPRF | PT-Upl HS CPC->DLYHDR/DLYDTL(CCNCTL-Dly Ctl) SPEADR60/AUTOHS | *RBTDFT |  | 815 | 0 | 815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000461 | OF_IN_GA | Oracle Chart Accts JDA | 830 | C |  |  | 0 | + | BDSYSPRF | GA-Oracle Chart of Accounts to JDA | *RBTDFT |  | 830 | 0 | 830 | 1230 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000462 | OF_IN_GL | Oracle Locations to JDA | 830 | C |  |  | 0 | + | BDSYSPRF | Gl-Oracle locations to JDA | *RBTDFT |  | 830 | 0 | 830 | 1230 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000463 | OF_IN_GR | Oracle Exch Rates to JDA | 830 | C |  |  | 0 | + | BDSYSPRF | GR-Oracle Exchange rates to JDA | *RBTDFT |  | 830 | 0 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000466 | OF_IN_GT | Oracle GL TransactionsJDA | 830 | C |  |  | 0 | + | BDSYSPRF | GT-Oracle GL Transactions to JDA | *RBTDFT |  | 830 | 0 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000727 | HEAD_COUNT | H*Head Count Sales file | 830 | C |  | H | 0 |  | BDSYSPRF | Send Last 14 Day Sls (Err Log: MMBUSLIB/LPHCLOGS/SND_OUTPUT) | *RBTDFT |  | 830 | 0 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001065 | MOOSE3_WP | Rebuild MOOSE3-Weekend | 830 | C |  |  | 0 |  | BDSYSPRF | Rebuild MOOSE3-Weekend (MOOSEAGGR2 must be completed first) | *RBTDFT |  | 830 | 0 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000975 | EM_HUGEQTY | Email Huge Inv Adj Qty | 830 | C |  |  | 0 |  | BDSYSPRF | Huge Inv Adj Qty>1000 (Typ 31-98 & <>71)(SPEADR60-HUBADJQTY) | *RBTDFT |  | 830 | 0 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000895 | CSH_XTN_WK | Cash Bolt-on file-WKN | 845 | C |  |  | 0 |  | BDSYSPRF | Online Rtn Inv Update. Email eBay Trf List:SPEADR/ONLRETRN. | *RBTDFT |  | 845 | 0 | 845 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000468 | OF_EML_CNF | Email Outstndng Confirms | 900 | C |  |  | 0 | + | BDSYSPRF | Email Outstanding Confirmations | *RBTDFT |  | 900 | 0 | 900 | 1300 | 1600 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000251 | SYSSTPROLL | Dasd plus Rolling Survey | 900 | C |  | H | 0 | + | MISOPR | If in error, call iSeries Engineering | *RBTDFT |  | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | DASDPLUS | ETIDP | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | SYSNOMAX | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2011-09-22-10.59.14.926000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000826 | EMMISSW1 | Email Missing Rtl Sales | 900 | C |  |  | 0 |  | BDSYSPRF | Email Miss Sls Tran-SPEADR CSHMISS(JobName End 1/2-SDI913JQ) | *RBTDFT |  | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000985 | EM_SKUADCH | Email Sku Add/Change Data | 900 | C |  |  | 0 |  | BDSYSPRF | Email Sku Add/Change Data (SPEADR60-SKUADDCHG) | *RBTDFT |  | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001056 | CX_MST_WP | *Daily CMIS Master Files | 900 | C |  |  | 0 | + | BDSYSPRF | Daily CMIS Master/Inv Bal/Price Files(No Sales) - Weekend | *RBTDFT |  | 900 | 0 | 900 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | CMIS | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 14 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001059 | EM_SLS_PCS | H*Eml SLS Piece Count Rpt | 900 | C |  | H | 0 |  | BDSYSPRF | Email Sales Piece Count Report (SPEADR60-SLSPCS) | *RBTDFT |  | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001292 | DST_SUN | SUNDAY DISTRICT STORE RES | 900 | C |  |  | 0 | + | BDSYSPRF | Weekly District Store Results on Sunday | *RBTDFT |  | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | STOREBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001322 | ALG_BAL_WP | *DailyAlgolia Invbal File | 900 | C |  |  | 0 | + | BDSYSPRF | *Daily Algolia Invbal File - Weekend | *RBTDFT |  | 900 | 0 | 900 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 14 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001159 | OOSLBD15 | H*Prt Out of Stk Lbl D15 | 900 | C |  | H | 0 |  | BDSYSPRF | Print Out of Stock Label-District 15 | *RBTDFT |  | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001266 | SUNIRF_WP | SUNRISE Inv Fresh Sat-Sun | 900 | C |  |  | 0 |  | BDSYSPRF | SUNRISE Inv Fresh Sat-Sun | *RBTDFT |  | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | NGP_PRC | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000207 | SVC026CL | D*Prt SVS Settlement Rpt | 930 | P |  |  | 0 |  | BDSYSPRF | OK cancel. Info IS Support in next business day. D*:Hamilton | *RBTDFT |  | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 30 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000469 | OF_IN_RC | Orcl Reconcil Ttls JDA | 930 | C |  |  | 0 | + | BDSYSPRF | RC-Oracle Reconciliation Totals to JDA (AI and GI only) | *RBTDFT |  | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | ORACLE | QUSRSYS | 0 | 0 | *RBTDFT |  | ORACLEIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000902 | MONINVBL1A | H*INVBAL Refresh to Sunrs | 945 | C |  | H | 0 |  | BDSYSPRF | Utility to Monitor INVBAL Refresh to Sunrise (Sun) 1st | *RBTDFT |  | 945 | 0 | 945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000490 | F_XEROXWP | *Send PO Rec RTV Info XRX | 1000 | C |  |  | 0 |  | BDSYSPRF | Sun Only Send PO Receiving and RTV Info to Xerox Doc Folder | *RBTDFT |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000501 | POS_REJECT | H*Eml Reject POS Trans Rp | 1000 | C |  | H | 0 |  | BDSYSPRF | Reject POS Tran Come after Period End-CSHPPT - SPEADR/CSHPPT | *RBTDFT |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 66 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000697 | SYSSWPAUD | Audit swap profiles | 1000 | C |  |  | 0 |  | MISOPR | ticket to iseries, cancel if error, do not call out | *RBTDFT |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | SYSNOMAX | IBMMODS |  | *RBTDFT | *RBTDFT | ITTOOLS |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000254 | SYSBCKPRG | Purge backup audit log | 1000 | C |  |  | 0 | + | MISOPR | Cancel if in error, do not call out, ticket to iSeries Engin | *RBTDFT |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | SYSNOMAX | IBMMODS |  | *RBTDFT | *RBTDFT | ITTOOLS |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2012-09-21-10.09.20.809000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000829 | BLD_PRXFWK | Bld Program Ref-Wkend | 1000 | C |  |  | 0 |  | BDSYSPRF | Build Program Reference Database File (Replace Hawkeye) | *RBTDFT |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000846 | CK_E3EOD1A | O*Check E3 EOD(Sun)ASR | 1000 | C |  |  | 0 |  | BDSYSPRF | Send text alert if E3 ASR EOD runs late (Sunday) | *RBTDFT |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000935 | EM_PMWK | H*P&M Flash Sales-CPC Eml | 1000 | C |  | H | 0 |  | BDSYSPRF | Email WTD/PTD/YTD CPC Flash Sales | *RBTDFT |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000968 | F_OS_POTRW | FTP Unrec PO Trf-BTS Wk N | 1000 | C |  |  | 0 |  | BDSYSPRF | FTP Unrec PO Trf include 3 months prior,12 months in future | *RBTDFT |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001227 | SYSCHKLKEY | Check license keys expire | 1000 | C |  |  | 0 |  | MISOPR | Can be cancelled with ticket to iSeries Platform Engineering | *RBTDFT |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001287 | EM_EP_UNAP | Email Daily Emg Prf UnApr | 1000 | C |  |  | 0 |  | BDSYSPRF | Email Daily Unapproved Emergency Profile Rpt(TBLFS10/USREPA) | *RBTDFT |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000368 | SYSDDMAUDP | Add Users to IP DDM SV | 1001 | C |  |  | 0 |  | QSYSOPR | BUSDEP SNA to IP - Add Users to IP DDM SVR | *RBTDFT |  | 1001 | 0 | 1001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 61 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000694 | EM_PRC3DP | Email Price Chg.-Init run | 1005 | C |  |  | 0 |  | BDSYSPRF | Email the Daily Item Price Change to the Delivery Group.-Tue | *RBTDFT |  | 1005 | 0 | 1005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y |  |  |  | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 57 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001345 | EXTSLSB1DW | Build Ext. Sls-1 Week Ago | 1005 | C |  |  | 0 |  | BDSYSPRF | Build Extended Sales (Supreme)Summary File-1 Week Ago | *RBTDFT |  | 1005 | 0 | 1005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000794 | CH_LBL_OD | Check O/S On Demand Signs | 1030 | C |  |  | 0 |  | BDSYSPRF | Send TXT MSG:Pending On Demand Signs in AccessVia FTP Folder | *RBTDFT |  | 1030 | 0 | 1030 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000849 | CK_E3EOD1W | O*Check E3 EOD(Sun)AWR | 1030 | C |  |  | 0 |  | BDSYSPRF | Send text alert if E3 AWR EOD runs late (Sunday) | *RBTDFT |  | 1030 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001096 | FD15YSLSWP | H*D15 YDay SL-Fill Rpt-WN | 1030 | C |  | H | 0 |  | BDSYSPRF | Bld YDay SLS for Dst 15 Str Fill Rpt-Run after FCHN_SKU done | *RBTDFT |  | 1030 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001098 | FD20_SLSWP | H*D20 YDay SL-Fill Rpt-WK | 1030 | C |  | H | 0 |  | BDSYSPRF | Bld YDay SLS for Dst 20 Str Fill Rpt-Run after FCHN_SKU done | *RBTDFT |  | 1030 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000552 | PRTLABELW | *Print Labels | 1040 | C |  |  | 0 |  | BDSYSPRF | Submit DAY_LBLsss Job-Can't run before SSWINBND2(Create SKU) | *RBTDFT |  | 1040 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y |  |  |  | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 8 | BUSDEP | [5 empty] | 0 | 3 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000547 | SYSDCMJBSC | crt dcm jobscde files | 1041 | C |  |  | 0 |  | MISOPR | can be cancelled with ticket to iseries, do not call out | *RBTDFT |  | 1041 | 0 | 1041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | ITTOOLS | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000178 | EM_DSAW1 | *EMail Daily SLS All Str | 1100 | C |  |  | 0 |  | BDSYSPRF | Email Daily Sls to SPEADR/EXECHH(*See SLS886JQ Char 8th = 1) | *RBTDFT |  | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000233 | MMEJOB | H*Run Weekly MME Project | 1100 | C |  | H | 0 | + | HCHAN | Weekly MME | *RBTDFT |  | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | MMEJOBD | MMDEVCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | HCHAN | QUSRSYS | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 40 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000412 | PASS_CPY | *PASS Trans Dtl Feed | 1100 | C |  |  | 0 |  | BDSYSPRF | PASS Trans details feed from BusDep to MARSQL5 | *RBTDFT |  | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 64 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001069 | CVM_CSAT1 | H*Send/Receive CVM Data | 1100 | C |  | H | 0 |  | BDSYSPRF | Send/Receive CVM (Customer Service Satisfaction) Data | *RBTDFT |  | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 58 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001314 | MAWM_SYNCH | MAWM Inventory Synch ** | 1100 | C |  |  | 0 |  | BDSYSPRF | MAWM INVENTORY Sync up process | *RBTDFT |  | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | MAWMOUT | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001162 | F_PRECIMA | *FTP Precima Prc Data | 1100 | C |  |  | 0 |  | BDSYSPRF | *FTP PRC/TLOG,Online Prc done on Sunrise KPRECPWK-FTP @ 12AM | *RBTDFT |  | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000687 | EMLCHBER#1 | H*Alert-CHub SLS Post ER | 1130 | C |  | H | 0 |  | BDSYSPRF | Send Email Alert for C-Hub Sales Posting Failure | *RBTDFT |  | 1130 | 0 | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000746 | EMLCHBER#2 | EMail CHub Error Report | 1130 | C |  |  | 0 |  | BDSYSPRF | EML CHub Err Rpt base on Dly Sales(ISTYPE=08,SPEADR=CHUBRPT) | *RBTDFT |  | 1130 | 0 | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 87 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001085 | EM_DSTW1 | *EMail Daily SLS Transfrm | 1130 | C |  |  | 0 |  | BDSYSPRF | TBLSTX/STTYP1=T, SPEADR/DLYSLSSTR (*See SLS886JQ Char 8th=1) | *RBTDFT |  | 1130 | 0 | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000696 | VFOEMLWP | H*Eml Sell Through Offer | 1200 | C |  | H | 0 |  | BDSYSPRF | Email the Sell Through Offer Changes to Merch / Finance | *RBTDFT |  | 1200 | 0 | 1200 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 57 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000754 | F_ESPOCS | H*FTP Open ESP Case->ECP | 1200 | C |  | H | 0 |  | BDSYSPRF | FTP Open ESP Cases in Last 3 Days to PC Application(Andriy) | *RBTDFT |  | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001282 | EM_NOSGNWP | *Eml No Prc Chg Sign-WKN | 1201 | C |  |  | 0 | Q | BDSYSPRF | Eml Str Miss Prc Chg Signage,PRTLABELW Job-SPEADR60/NOPRCSGN | *RBTDFT |  | 1201 | 0 | 1201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 8 | BUSDEP | [5 empty] | 0 | 96 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000154 | SP_VND_MET | *SPartners Vendor Metric | 1215 | C |  |  | 0 | + | BDSYSPRF | StaplesPartner - Vendor Metric Feed | *RBTDFT |  | 1215 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH3 | *LIBL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000903 | MONINVBL1B | H*INVBAL Refresh to Sunrs | 1215 | C |  | H | 0 |  | BDSYSPRF | Utility to Monitor INVBAL Refresh to Sunrise (Sun) 2nd | *RBTDFT |  | 1215 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000871 | CRT_R50CTL | H*Not Use-Run in CPCDaily | 1300 | C |  | H | 0 |  | BDSYSPRF | Auto Create Missing R50 (SP) Control Record in /POS/XMLCLD | *RBTDFT |  | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000267 | DIVCLN | PURGE CANxxx DIVIDEND | 1300 | C |  |  | 0 | + | BDSYSPRF | PURGE CANxxx DIV FILES / Sunday SLS to CMIS /eBay Transfer | *RBTDFT |  | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QSYSOPR | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000664 | CLICKSDP | *CLICKS TRACKING | 1300 | C |  |  | 0 |  | BDSYSPRF | FULL SERVER CLICK COUNT | *RBTDFT |  | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000524 | DRPSHPVNWP | H*Vendor File | 1300 | C |  | H | 0 |  | BDSYSPRF | Create the Drop Ship Vendor File for Planogram Database | *RBTDFT |  | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 66 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001163 | CH_CSHXTN | Chk Unprocess BOLT On Rec | 1300 | C |  |  | 0 |  | BDSYSPRF | Send TXT MSG:BOLT On Rec in CSHXTN/CXSTATUS=' '->Invalid Sku | *RBTDFT |  | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000735 | CRMIDLY | *Proc M/C Info from Comps | 1300 | C |  |  | 0 |  | BDSYSPRF | Receive daily machine information from Compass | *RBTDFT |  | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000736 | CRMRDLY | Process last 2weeks data | 1330 | C |  |  | 0 |  | BDSYSPRF | Receives AR summary and detail feeds from CFS system | *RBTDFT |  | 1330 | 0 | 1330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000792 | CH_LBL_DE | Check O/S PRC CHG Signage | 1330 | C |  |  | 0 |  | BDSYSPRF | Send TXT MSG:Pending PRC CHG Signage in AccessVia FTP Folder | *RBTDFT |  | 1330 | 0 | 1330 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000806 | LWP_DAILY | *Lowest Price Daily | 1330 | C |  |  | 0 |  | BDSYSPRF | Fine tune LWP for End of Day process | *RBTDFT |  | 1330 | 0 | 1330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000922 | CH_E3POCWP | Check New E3 PO Count | 1345 | C |  |  | 0 |  | BDSYSPRF | Send Text Alert-If > 7000 New E3 PO created today on Weekend | *RBTDFT |  | 1345 | 0 | 1345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000929 | EBY_TRF_WK | *Send eBay transfer Wkend | 1400 | C |  |  | 0 |  | BDSYSPRF | Send eBay transfers to eBay Instant Sales server - Weekend | *RBTDFT |  | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000274 | SLS_GM_RPT | SALES GROSS MARGIN REPORT | 1400 | C |  |  | 0 | + | BDSYSPRF | SALES GROSS MARGIN REPORT | *RBTDFT |  | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000304 | SYSBRMSMNT | Run BRMS Maintenance | 1400 | C |  |  | 0 | + | *RBTDFT | Run BRMS Maintenance | *RBTDFT |  | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | BRMSRMT1 | QUSRSYS | 1 | 0 | *RBTDFT |  | BRMSJOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 46 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000407 | PURGELBL | purge signage spool file | 1400 | C |  |  | 0 |  | BDSYSPRF | Purge Store Signage Spool Files | *RBTDFT |  | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 65 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000666 | CLK_ERR | CLICKS ERROR REPORTS | 1400 | C |  |  | 0 |  | BDSYSPRF | FULL SERVER AND SELF SERVER CLICKS ERROR REPORTS | *RBTDFT |  | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000947 | AIRM_RVRSE | H*Air Mile Sales Reversal | 1400 | C |  | H | 0 |  | BDSYSPRF | Get IFS/Transfer/Airmiles/Reversal/STAPLES_IS*:SPEADR-AMRMSG | *RBTDFT |  | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001270 | CLR_OUTQSW | Weekly Clear Out Queues | 1400 | C |  |  | 0 | + | BDSYSPRF | Weekly Cleanup of Output Queues | *RBTDFT |  | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000737 | CRMXDLY | *Send m/c data to compass | 1430 | C |  |  | 0 |  | BDSYSPRF | Receive Xerox&Non-Xerox feed daily and send updated data | *RBTDFT |  | 1430 | 0 | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 75 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001331 | SYSBKUPRPT | MOVE BRMS BACKUP REPORTS | 1500 | C |  |  | 0 | + | QSYSOPR | MOVE BACKUP REPORTS TO SECMANISH OUTQ FROM QEZJOBLOG OUTQ | *RBTDFT |  | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | BRMSBKUP | SECMANISH | 1 | 0 | *RBTDFT |  | BRMSJOBQ | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 46 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000881 | EM_DSAW2 | *EMail Daily SLS All Str | 1500 | C |  |  | 0 |  | BDSYSPRF | Email Daily Sls to SPEADR/EXECHH & SPEADR60/DLYSLSDIV*CHR8=2 | *RBTDFT |  | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001332 | MAWM_PURGE | MAWM file Purge | 1500 | C |  |  | 0 |  | BDSYSPRF | MAWM OutFile Purge | *RBTDFT |  | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | MAWMOUT | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001212 | SAI_DPRNT | H* Dly SBA Digital Print | 1500 | C |  | H | 0 |  | BDSYSPRF | Daily SBA Digital Price-Create Virtual Sales for Print Hubs | *RBTDFT |  | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 79 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000158 | CKQESLIN | Check Resource QESLINE | 1500 | C |  |  | 0 |  | *RBTDFT |  | *RBTDFT |  | 2300 | 2300 | 1500 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *JOBD |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | GALSYS | [5 empty] | 0 | 50 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000159 | CKQESPPL | Check Resource QESPPLIN | 1500 | C |  |  | 0 |  | *RBTDFT |  | *RBTDFT |  | 2300 | 2300 | 1500 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *JOBD |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | GALSYS | [5 empty] | 0 | 50 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000287 | E3_PO_03 | *ELECTRONIC PO TRANSFER | 1530 | C |  |  | 0 | + | MISOPR | ELECTRONIC PO TRANSFER | *RBTDFT |  | 1530 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD3 | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | PO | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001086 | EM_DSTW2 | *EMail Daily SLS Transfrm | 1530 | C |  |  | 0 |  | BDSYSPRF | TBLSTX/STTYP1=T, SPEADR/DLYSLSSTR (*See SLS886JQ Char 8th=2) | *RBTDFT |  | 1530 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000748 | CH_PRCCHGC | Alert Sku Price Change CT | 1532 | C |  |  | 0 |  | BDSYSPRF | Text Alert Sku Price Change Count if > 1000 (TBLFLD/CELLON) | *RBTDFT |  | 1532 | 0 | 1532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH2 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000063 | RTVPENDING | Create RTV Pending record | 1600 | C |  |  | 0 | Q | BDSYSPRF | Create RTV Pending (If failed - cancel; tell STAN on Monday) | *RBTDFT |  | 1600 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | BUSDEP | [5 empty] | 0 | 13 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000253 | SYSCHKBCK | Check Backup Job Logs | 1600 | C |  |  | 0 | + | MISOPR | Ticket to iSeries if in error, do not call out | *RBTDFT |  | 1600 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | SYSNOMAX | IBMMODS |  | *RBTDFT | *RBTDFT | ITTOOLS |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2012-05-03-11.00.48.678000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000776 | EMLNOSL6 | Email No SLS List Batch 5 | 1600 | C |  |  | 0 |  | BDSYSPRF | No Sls Str Lst Today-NLNBNSPIONPQSKMBABNTBCYT SPEADR/NOSALES | *RBTDFT |  | 1600 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000216 | CCF2SUNR | *Send Coupon to Sunrise | 1700 | C |  |  | 0 | + | BDSYSPRF | !!! OK to Cancel. Please info Stanley Woo for error. !!! | *RBTDFT |  | 1700 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | QSYSOPR | *LIBL | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 35 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000335 | PERFNAVPM | Monitor | 1700 | C |  | H | 0 | + | MISOPR | Performance Navigator Monitor | *RBTDFT |  | 1700 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | PERFNAV | MPGLIB | MIS | QGPL | 0 | 0 | *RBTDFT |  | QWKNBCH4 | *LIBL |  | *RBTDFT | *RBTDFT | *CRTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 51 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000550 | BHN_DLYSTM | BHN statement posting | 1700 | C |  |  | 0 |  | BDSYSPRF | Gift card Mall BHN STatement Posting | *RBTDFT |  | 1700 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000284 | SEND_EDI2 | EDI PO TRANSFERS | 1700 | C |  |  | 0 | + | MISOPR |  | *RBTDFT |  | 1900 | 1900 | 1700 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y |  | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD2 | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | PO | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000103 | DLTHSTLOG | H*Delete History | 1800 | C |  | H | 0 | Q | QPGMR |  | FISCAL_21 |  | 1800 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *BLANK | 0 | STANDARD | 0 | *DFT | QBATCH | QGPL | QPRINT | QGPL | 0 | 0 | *JOBD |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | HELPSYS | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 1
000000000275 | MICROSOFT | *EDI RUN FOR MICROSOFT | 1800 | C |  |  | 0 | + | BDSYSPRF | EDI RUN FOR MICROSOFT | *RBTDFT |  | 1800 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | PO | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000171 | SYSSAVARC | Archive check pts to hst | 1800 | C |  |  | 0 |  | QSYSOPR | Archive check point information to history member | *RBTDFT |  | 1800 | 1800 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *USRPRF |  | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | GALSYS | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000405 | NPD_SLS | Weekly Sales Summary | 1800 | C |  |  | 0 |  | BDSYSPRF | Weekly Sales Summary File to NPD Survey Company | *RBTDFT |  | 1800 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 64 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000887 | JACKRTLRPT | *Print Retail Jackie Rpt | 1800 | C |  |  | 0 |  | BDSYSPRF | Print Email Jackie Report | *RBTDFT |  | 1800 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000822 | EMLTRFVAR | Email Transfer Var Rpt | 1800 | C |  |  | 0 |  | BDSYSPRF | Email Transfer Variance Report for Import-SPEADR60/TRFVARRPT | *RBTDFT |  | 1800 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000855 | EMMISSW2 | Email Missing Rtl Sales | 1830 | C |  |  | 0 |  | BDSYSPRF | Email Miss Sls Tran-SPEADR CSHMISS(JobName End 1/2-SDI913JQ) | *RBTDFT |  | 1830 | 0 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000473 | SYS_ORACLE | Clean up ORACLE Outq | 1900 | C |  |  | 0 |  | ETIDP | Clean up ORACLE OutQ | *RBTDFT |  | 1900 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | ETIJOBD | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000775 | EXTSLSB1WK | *BLD Ext. Sls-1 Week Ago | 1900 | C |  |  | 0 |  | BDSYSPRF | Build Ext Sls (CLS Rebate)Sum File-1 Wk Ago & Run Reg 1 Rpt | *RBTDFT |  | 1900 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000868 | SKU_BPSFLG | SKU Bopisflag feed to PDB | 1900 | C |  |  | 0 |  | BDSYSPRF | Update SKU Bopis flag in PDB from JDA feed | *RBTDFT |  | 1900 | 1900 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 47 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001067 | WK_DST_SUN | WKLY DISTRICT RESULTS-SUN | 1900 | C |  |  | 0 | + | BDSYSPRF | WKLY DISTRICT RESULTS RPT-Str Outq(Stopped)/PRTJSOARES DST | *RBTDFT |  | 1900 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | STOREBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000960 | IS4_AUTOPN | H*Auto Scan Batch Open | 1900 | C |  | H | 0 |  | *RBTDFT | Contact BD Applications for support | *RBTDFT |  | 1900 | 0 | 1900 | 2000 | 2100 | 2200 | 2300 | 2345 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000962 | AUT_OOSOPN | Auto Scan Batch Open | 1900 | C |  |  | 0 |  | BDSYSPRF | Contact BD Applications for support | *RBTDFT |  | 1900 | 1900 | 1900 | 2000 | 2100 | 2200 | 2300 | 2345 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNINT1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000831 | EML_DUPLNK | Check Dupl Recycle Fee | 1930 | C |  |  | 0 |  | BDSYSPRF | Check Duplicate Recycle Fee Linkage (SPEADR60-DUPRCLLNK) | *RBTDFT |  | 1930 | 1930 | 1930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001158 | FD15TSLSWP | H*D15 TDay SL-Fill Rpt-WK | 1945 | C |  | H | 0 |  | BDSYSPRF | Bld YDay SLS for Dst 15 Str Fill Rpt-Run after FCHN_SKU done | *RBTDFT |  | 1945 | 0 | 1945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 86 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000125 | E3_DUP_PO1 | Eml Dup E3 Rls Ord-WKN | 2000 | C |  |  | 0 | + | BDSYSPRF | E3 Rls Ord for Same Str/Sku-MERCHOPERATIONSCANADA@STAPLES.CA | *RBTDFT |  | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000681 | CLD_PRICE | H*Feeds to Storage Pipe | 2000 | C |  | H | 0 |  | BDSYSPRF | Outbound Price & Coupon files to Storage Pipe | *RBTDFT |  | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000239 | CLR_OUTQSD | Daily Clear Out Queues | 2000 | C |  |  | 0 |  | QSYSOPR | Daily clean up of output queues | *RBTDFT |  | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS | 5 | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 37 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000549 | SYSRMTSYNC | Sync Robot ALert Files | 2000 | C |  | H | 0 |  | MIMIXOWN | Sync Robot Alert Device Files to the Mimix HA System | *RBTDFT |  | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QDFTJOBD | QGPL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QSYSNOMAX | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000563 | CPC_PRICE | *Copy Centre Payments | 2000 | C |  |  | 0 |  | BDSYSPRF | Copy Centre On-Line Payment Sales Transactions to JDA | *RBTDFT |  | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 72 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000631 | SVC_ACT | *SVC Card Batch Activate | 2000 | C |  |  | 0 |  | BDSYSPRF | SVC Activation-Done by 10pm - SVCLOG,SVCBAT.P12MMDD BDPGC602 | *RBTDFT |  | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 76 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000884 | CPC_RSPO | *Auto Resend CPC PO | 2000 | C |  |  | 0 |  | BDSYSPRF | Resend CPC PO if unacknowledged after 2 days-TBLFS10/CPPDAT | *RBTDFT |  | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001306 | MAWM_DITEM | MAWM Daily Item Delta | 2000 | C |  |  | 0 |  | BDSYSPRF | MAWM Item incremental Feed | *RBTDFT |  | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | MAWMIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000299 | ENDQINTWKE | ENDQINTWKE | 2040 | C |  |  | 0 | + | QSYSOPR |  | *RBTDFT |  | 2040 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QSYSOPR | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QCTL | QSYS |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000924 | UP_RELOC2N | Reloc Store POS Active=N | 2045 | C |  |  | 0 |  | BDSYSPRF | Set Reloc Store POS Active=N in POLSTR file for Str 401->419 | *RBTDFT |  | 2045 | 2045 | 2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000749 | EMLPRCPR | Email Price Protection | 2058 | C |  |  | 0 |  | BDSYSPRF | Email Price Protection Information to Merchants | *RBTDFT |  | 2058 | 2058 | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000235 | SYSAMLOUTQ | AML OUTQ Load | 2100 | C |  | H | 0 |  | MISOPR | Auditing, Logging, Monitoring - Read OUTQs and load the tool | *RBTDFT |  | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000554 | DAYSTARTW | Day Start | 2100 | C |  |  | 0 | Q | BDSYSPRF | Call DAYPRCCL then Submit DAYSTRCL job weekends | *RBTDFT |  | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *RQD | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  | X |  | Y | N | 1 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 8 | BUSDEP | [5 empty] | 0 | 58 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001308 | MAWM_ZVEND | MAWM FULL Vendor Feed | 2100 | C |  |  | 0 |  | BDSYSPRF | MAWM FULL Vendor incremental Feed | *RBTDFT |  | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | MAWMIN | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 84 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000341 | CKDAYSTR | Check Resource RBDAYSTART | 2101 | C |  |  | 0 |  | *RBTDFT |  | *RBTDFT |  | 2101 | 2101 | 2101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *JOBD |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 53 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000799 | CHK_DAYSTR | Check DAYSTART/W Status | 2115 | C |  |  | 0 |  | BDSYSPRF | Text Alert:Check DAYSTART/W Robot Job Status | *RBTDFT |  | 2115 | 2115 | 2115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | N | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000508 | SYSAUDBKUP | Audit libraries backup | 2130 | C |  |  | 0 | + | MISOPR | Audit libraries backup | *RBTDFT |  | 2130 | 0 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | BRMSJOBD | QGPL | PRODSOX | QGPL | 0 | 0 | *RBTDFT |  | BRMSJOBQ | QGPL |  | QSYSOPR | QSYS | *RBTDFT |  |  |  |  | Y | Y | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 46 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000883 | CH_E3_VND | Check E3 Vendor in E3SITM | 2130 | C |  |  | 0 |  | BDSYSPRF | Send TXT MSG:Check / Delete Invalid E3 Vendor(1 ) in E3SITM | *RBTDFT |  | 2130 | 2130 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000092 | SP_STORE | StaplesPartners Store inf | 2200 | C |  |  | 0 | + | BDSYSPRF | StaplesPartner - Store List | *RBTDFT |  | 2200 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000243 | HBT_GNRD | TXECCT records generation | 2200 | C |  |  | 0 | + | BDSYSPRF |  | *RBTDFT |  | 2200 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | QSYSOPR | *LIBL | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 42 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000896 | SYSILMTHSC | ILMT Hardware Scan | 2200 | C |  |  | 0 |  | SECMANISH | ILMT Hardware Scan | *RBTDFT |  | 2200 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | ITTOOLS | ITTOOLS | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QCTL | *LIBL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000417 | ESPCUI | H*Upld Web ESP Cust Info | 2200 | C |  | H | 0 |  | BDSYSPRF | Upload new Web ESP Customer Information | *RBTDFT |  | 2200 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 64 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000648 | SAI_INRF | Weekly RF Feed From WIS | 2200 | C |  |  | 0 |  | BDSYSPRF | Accepts RTV status from WIS and post 71 and update JDA data. | *RBTDFT |  | 2200 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 79 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000926 | UPD_CSTPLN | *Set CSTPLN for Tomorrow | 2200 | C |  |  | 0 |  | BDSYSPRF | Run after DAYSTART/W to Set NEXTDATE as Tomorrow | *RBTDFT |  | 2200 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001175 | F_PDBPRD | *FTP Prod Master to PDB | 2200 | C |  |  | 0 |  | BDSYSPRF | FTP Prod Master to Product Data Base (before 11pm) | *RBTDFT |  | 2200 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH1 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 85 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000342 | CKRBTGNR | Check Resource RBRBT_GNRD | 2201 | C |  |  | 0 |  | *RBTDFT |  | *RBTDFT |  | 2201 | 2201 | 2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | RBCJOBD | RBTCONLIB | *RBTDFT | *RBTDFT | 0 | 0 | *JOBD |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 53 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000605 | SYSUSRAUD | User Auditing Set | 2215 | C |  |  | 0 |  | MISOPR | Turn on User Auditing for power users | *RBTDFT |  | 2215 | 2215 | 2215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000606 | SYSUSRAUD2 | User Auditing Remove | 2225 | C |  |  | 0 |  | MISOPR | Turn off User Auditing if not a power user | *RBTDFT |  | 2225 | 2225 | 2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000869 | EM_IMJCK | Email Import Jackie Rpt | 2225 | C |  |  | 0 |  | BDSYSPRF | Email Import Jackie Sales Report (SPEADR60-IJCKEMAIL) | *RBTDFT |  | 2225 | 0 | 2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000090 | SP_OPNPO | StaplesPartners opn PO | 2230 | C |  |  | 0 | + | BDSYSPRF | StaplesPartner - Open PO feed | *RBTDFT |  | 2230 | 2230 | 2230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | BDBUS | 0 | *DFT | JDAJOBD | MMBUSCTL | QPRINT | QGPL | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
990000000236 | SYSSIAMAUT | SIAM GRTOBJAUT *ALL | 2230 | C |  |  | 0 |  | MISOPR | Omits 'Q' profiles and those in ITTOOLS/SIAM_OMIT | *RBTDFT |  | 2230 | 2230 | 2230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 10 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000649 | SAI_INFI | Weekly FB Feed From Alpha | 2230 | C |  |  | 0 |  | BDSYSPRF | Accepts final Inventory status and send variance to Finance. | *RBTDFT |  | 2230 | 0 | 2230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 79 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000753 | DYNSKU_P | H*FTP Dynamic Sku List | 2255 | C |  | H | 0 |  | BDSYSPRF | PT-Dynamic Sku List/Whitelist.CA (INVSKU/CH1X28='Y') | *RBTDFT |  | 2255 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 68 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000301 | ENDQPGMRSA | ENDQPGMRSA | 2300 | C |  |  | 0 | + | QSYSOPR | ENDSBS(QPGMR) for Saturday and Sunday @ 22:50 | *RBTDFT |  | 2300 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | QSYSOPR | MMBUSCTL | QSYSOPR | QGPL | 0 | 0 | *RBTDFT |  | QCTL | QSYS |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 20 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000418 | ESPCUO | H*Dld AS400 ESP Cust Info | 2300 | C |  | H | 0 |  | BDSYSPRF | Download new AS400 ESP Customer Information to Web Database | *RBTDFT |  | 2300 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 64 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000647 | SAI_INFW | Weekly FW Feed From WIS | 2300 | C |  |  | 0 |  | BDSYSPRF | Accepts final Inventory status and send variance to Finance. | *RBTDFT |  | 2300 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 79 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001301 | CLRJDADEP | CLEAR JDA JOB DEPENDENCY | 2300 | C |  |  | 0 |  | MISOPR | CLEAR JDA JOB DEPENDENCY CODES | *RBTDFT |  | 2300 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | *RBTDFT | *RBTDFT |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000512 | SYSCLNIMAI | Clean IMAIL log files | 2330 | C |  |  | 0 |  | MISOPR | Clean Current day IMAIL log files from IFS iMail Folder | *RBTDFT |  | 2330 | 2330 | 2330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000561 | SYSCLNTOWN | Clean townsend archive | 2330 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 2330 | 2330 | 2330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | ALLFTMSTAP |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000730 | SYSCLNALLS | Clean Alliance/SSH | 2330 | C |  |  | 0 |  | MISOPR |  | *RBTDFT |  | 2330 | 2330 | 2330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | ALLFTMSTAP |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000001276 | SYSCLNRMA | Clean /APPS/RMA/IN | 2330 | C |  |  | 0 |  | MISOPR | Clean Excel files from /apps/rma/in folder keeping 90 days | *RBTDFT |  | 2330 | 2330 | 2330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH3 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000231 | CLR_HDMSG | Clear Msq Que HD33MSG | 2345 | C |  |  | 0 |  | BDSYSPRF |  | *RBTDFT |  | 2345 | 0 | 2345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *DFT | *RBTDFT | *RBTDFT | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QBATCH | QGPL | 5 | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 6 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 2009-09-26-01.46.52.068000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000769 | EMLPOSERR | H*POS File Mering Error | 2345 | C |  | H | 0 |  | BDSYSPRF | Email POS Download File Merging Err (SPEADR/POSERR) PRC812JQ | *RBTDFT |  | 2345 | 0 | 2345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RQD | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNBCH4 | IBMMODS |  | *RBTDFT | *RBTDFT | *RBTDFT |  |  |  | H | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 89 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000963 | AUT_OOSCLS | Auto Scan Batch Close | 2345 | C |  |  | 0 |  | BDSYSPRF | Contact BD Applications for support | *RBTDFT |  | 2345 | 2345 | 2345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNINT1 | IBMMODS |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2
000000000965 | AUT_OOSMIS | Track-Create Missing OOS | 2355 | C |  |  | 0 |  | BDSYSPRF | Please call BD-Applications on-call if any issues | *RBTDFT |  | 2355 | 2355 | 2355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Y | Y | Y | Y | Y | Y | 0 | 0 | 0 | 0 |  | *RBTDFT | 0 | STANDARD | 0 | *RBTDFT | JDAJOBD | MMBUSCTL | *RBTDFT | *RBTDFT | 0 | 0 | *RBTDFT |  | QWKNINT1 | IBMMODS |  | TSSA | BUSDEP | *RBTDFT |  |  |  |  | Y | N | 0 | 0 | 0 | 0 |  | 0 | *RBTDFT |  |  | 20 | BUSDEP | [5 empty] | 0 | 0 | *RBTDFT | 0001-01-01-00.00.00.000000 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 2

## VLookup
SUNJOBS LATEST 4 to 10 AM | LAST DR LIST 4 to 10AM | New Jobs found
BPS831CL | BPS831CL | BPS831CL
CATMANLSTD | MOOSEAGGR2 | #N/A
CATMANGETD | E3_FREEZE | #N/A
MOOSEAGGR2 | E3_DAYEND | MOOSEAGGR2
E3_FREEZE | POS_PURGE | E3_FREEZE
E3_DAYEND | INVBAX_API | E3_DAYEND
POS_PURGE | PERFNAVIFS | POS_PURGE
INVBAX_API | NONSALE_UP | INVBAX_API
PERFNAVIFS | E3TWAIT | PERFNAVIFS
NONSALE_UP | SYSGENRBT | NONSALE_UP
PERFNAVIFS | CPS_DAILY | PERFNAVIFS
E3TWAIT | DCA3_DAILY | E3TWAIT
SYSGENRBT | POSLOG | SYSGENRBT
CPS_DAILY | SYSCHKSUN | CPS_DAILY
DCA3_DAILY | BPS_INVENT | DCA3_DAILY
BPS_PCKEML | F_GXDLY2TB | #N/A
POSLOG | F_GXDLY1TB | POSLOG
SYSCHKSUN | SYSLOGFTP | SYSCHKSUN
BPS_INVENT | ST_TYPE27 | BPS_INVENT
F_GXDLY2TB | SYSRRMTRAN | F_GXDLY2TB
F_GXDLY1TB | MKB_REPORT | F_GXDLY1TB
SYSLOGFTP | SAI_MAC | SYSLOGFTP
SYSRRMTRAN | SYSODBCPNT | SYSRRMTRAN
MKB_REPORT | ETS_DAILY | MKB_REPORT
SAI_MAC | SE_DAILY | SAI_MAC
ETS_DAILY | SKUEXT2 | ETS_DAILY
SE_DAILY | UP_GCCOM | SE_DAILY
SKUEXT2 | CBT_DAILY | SKUEXT2
UP_GCCOM | MPOS_330WP | UP_GCCOM
CBT_DAILY | AGILENCEWP | CBT_DAILY
MPOS_330WP | AUTO_FTP | MPOS_330WP
CLR_IFSALL | CLD_TXNPCK | #N/A
BPS_ALLOC | QA_REFRESH | #N/A
SYSODBCPNT | RBT650001 | SYSODBCPNT
ST_TYPE27 | PPA_DATE | ST_TYPE27
AGILENCEWP | RBT651DP | AGILENCEWP
AUTO_FTP | SYSJRNACT | AUTO_FTP
CLD_TXNPCK | SYSSSHCHK | CLD_TXNPCK
QA_REFRESH | CLR_IFSWP | QA_REFRESH
RBT650001 | CXTBLBDG | RBT650001
PPA_DATE | F_PDBRCLWP | PPA_DATE
RBT651DP | F_PDBVNDWP | RBT651DP
SYSJRNACT | AS2RESETDP | SYSJRNACT
SYSSSHCHK | ESPCUA | SYSSSHCHK
CLR_IFSWP | AIRM_DAILY | CLR_IFSWP
CXTBLBDG | CHKBAL_BLD | CXTBLBDG
F_PDBRCLWP | PPR_OH_WP | F_PDBRCLWP
F_PDBVNDWP | UP_MEMCONT | F_PDBVNDWP
RMAFTP | FCHN_SKUWP | #N/A
AS2RESETDP | TSS_ORDPOP | AS2RESETDP
ESPCUA | HAMILTON | ESPCUA
AIRM_DAILY | DESJARDINS | AIRM_DAILY
EMPMSTWP | F_ORDSTSYD | EMPMSTWP
CHKBAL_BLD | EM_PDNVFO | CHKBAL_BLD
PPR_OH_WP | EM_PRC2DP | PPR_OH_WP
UP_MEMCONT | PCA_STRCNT | UP_MEMCONT
FCHN_SKUWP | TRF_AUTRCV | FCHN_SKUWP
TSS_ORDPOP | SYSSSLCHK | TSS_ORDPOP
RBT34504 | KRONOSWP | #N/A
RBCSTRTMON | SKU_TRNSLN | #N/A
HAMILTON | F_ESPTBL | HAMILTON
DESJARDINS | EMPMSTWP | DESJARDINS
F_ORDSTSYD | CRT_R40CTL | F_ORDSTSYD
EM_PDNVFO | PRGE_PRCZN | EM_PDNVFO
EM_UIDCHWP | CXDLYSUN | #N/A
AR_UPDATE | CSH900 | #N/A
EM_PRC2DP | CKMONSWAW | EM_PRC2DP
SYSUSRPRF | EMSLSVARWP | SYSUSRPRF
PCA_STRCNT | CPYAHS_P | PCA_STRCNT
TRF_AUTRCV | OF_IN_GA | TRF_AUTRCV
SYSSSLCHK | OF_IN_GL | SYSSSLCHK
KRONOSWP | OF_IN_GR | KRONOSWP
E3_RPLEN | OF_IN_GT | #N/A
SKU_TRNSLN | HEAD_COUNT | SKU_TRNSLN
F_ESPTBL | MOOSE3_WP | F_ESPTBL
CRT_R40CTL | EM_HUGEQTY | CRT_R40CTL
PRGE_PRCZN | CSH_XTN_WK | PRGE_PRCZN
CXDLYSUN | OF_EML_CNF | CXDLYSUN
SYSPRFDSP | SYSSTPROLL | #N/A
POSCLEANUP | EMMISSW1 | #N/A
CSH900 | EM_SKUADCH | CSH900
CKMONSWAW | CX_MST_WP | CKMONSWAW
EMSLSVARWP | EM_SLS_PCS | EMSLSVARWP
AS2_CHKCOM | EM_EP_UNAP | #N/A
CPYAHS_P | OOSLBD15 | CPYAHS_P
OF_IN_GA | SUNIRF_WP | OF_IN_GA
OF_IN_GL | SVC026CL | OF_IN_GL
OF_IN_GR | OF_IN_RC | OF_IN_GR
OF_IN_GT | MONINVBL1A | OF_IN_GT
HEAD_COUNT | F_XEROXWP | HEAD_COUNT
MOOSE3_WP | POS_REJECT | MOOSE3_WP
EM_HUGEQTY | SYSSWPAUD | EM_HUGEQTY
CSH_XTN_WK | SYSBCKPRG | CSH_XTN_WK
OF_EML_CNF | BLD_PRXFWK | OF_EML_CNF
SYSSTPROLL | CK_E3EOD1A | SYSSTPROLL
EMMISSW1 | EM_PMWK | EMMISSW1
EM_SKUADCH | F_OS_POTRW | EM_SKUADCH
CX_MST_WP | SYSCHKLKEY | CX_MST_WP
EM_SLS_PCS | SYSDDMAUDP | EM_SLS_PCS
DST_SUN | SYSUSRPRF | #N/A
ALG_BAL_WP | SYSRSFCHK | #N/A
OOSLBD15 |  | OOSLBD15
SUNIRF_WP |  | SUNIRF_WP
SVC026CL |  | SVC026CL
OF_IN_RC |  | OF_IN_RC
MONINVBL1A |  | MONINVBL1A
F_XEROXWP |  | F_XEROXWP
POS_REJECT |  | POS_REJECT
SYSSWPAUD |  | SYSSWPAUD
SYSBCKPRG |  | SYSBCKPRG
BLD_PRXFWK |  | BLD_PRXFWK
CK_E3EOD1A |  | CK_E3EOD1A
EM_PMWK |  | EM_PMWK
F_OS_POTRW |  | F_OS_POTRW
SYSCHKLKEY |  | SYSCHKLKEY
EM_EP_UNAP |  | EM_EP_UNAP

## DOJOBS UPLOAD
JOBNO | JOBNAME | JOBDES | STRTIME | JOBTYPE | JOBACTION
762 | BPS831CL | *Operational Excellence | 400 | C | Do
000000001339 | CATMANLSTD | Dly-Get CATMAN File LST | 405 | C | Do
000000001342 | CATMANGETD | Dly-Get CATMAN Files | 405 | C | Do
254 | MOOSEAGGR2 | *MOOSE AGGREGATE UPD WKN | 410 | C | Do
269 | E3_FREEZE | E3 DAY-END PROCESS | 415 | C | Do
270 | E3_DAYEND | E3 DAY-END PROCESS | 430 | C | Do, Run After 15 min after E3_FREEZE
528 | POS_PURGE | O*Purge Old Sales Data | 430 | C | Skip
1221 | INVBAX_API | API Call to update invbax | 445 | C | Do
555 | PERFNAVIFS | IFS Size Collection | 500 | C | Skip
724 | NONSALE_UP | Update the Status of | 500 | C | Do
271 | E3TWAIT | E3 DAY-END PROCESS | 515 | C | DO, Run After 15 min after E3_DAYEND
527 | SYSGENRBT | re-gen robot message file | 530 | C | Skip
728 | CPS_DAILY | Extract Sales for C&P SO | 530 | C | Skip
1188 | DCA3_DAILY | *CA Morning Setup *Once | 530 | C | Do
000000000757 | BPS_PCKEML | Prt/Eml BOPIS Ord Pick Up | 530 | C | Do
495 | SYSCHKSUN | check sunrise | 545 | C | Skip
759 | BPS_INVENT | Eml BPS Ord Activity Rpt | 545 | C | Do
1192 | F_GXDLY2TB | *FTP Google Master TBL#2 | 550 | C | Do
1180 | F_GXDLY1TB | *FTP Google Master TBL#1 | 558 | C | Do
486 | SYSLOGFTP | FTP Network Transactions | 600 | C | Skip
497 | ST_TYPE27 | *Sell Thru Type 27 entry | 600 | C | Do
499 | SYSRRMTRAN | Capture all Network Trans | 600 | C | Skip
511 | MKB_REPORT | Market Basket Report | 600 | C | Do
614 | SAI_MAC | *SA Daily MAC Interface | 600 | C | Do
642 | SYSODBCPNT | Check for ODBC Exit Prog | 600 | C | Skip
834 | ETS_DAILY | ETS-WebErr & ESPtablesFTP | 600 | C | Do
836 | SE_DAILY | *Send Daily Feeds for SE | 600 | C | Do
865 | SKUEXT2 | *Sku Master ext part 2 | 600 | C | Do
923 | UP_GCCOM | Refresh Gift Card Com% | 600 | C | Skip
1185 | CBT_DAILY | *File feed transmission | 600 | C | Do
1035 | MPOS_330WP | *Send Full PLU-MPOS-330 | 600 | C | Do
000000001296 | CLR_IFSALL | O*Clear IFS see IFSLIST | 600 | C | Do
000000000760 | BPS_ALLOC | H*Bopis Allocation Bucket | 600 | C | Do
1170 | AGILENCEWP | *Send Agilence LP File WN | 615 | C | Do
31 | AUTO_FTP | *Resend Missed POS Price | 625 | C | Skip
888 | CLD_TXNPCK | StoragePipe Order Trigger | 630 | C | Nasser to confirm if to hold job,took DO
211 | QA_REFRESH | QA Lab Daily PLU Updates | 630 | C | DO
241 | RBT650001 | Completion Message Listin | 630 | C | Skip
245 | PPA_DATE | Roll Prepaid Activation D | 630 | C | DO
338 | RBT651DP | Good Morning Report | 630 | C | Skip
535 | SYSJRNACT | Log Journal Rcvr Activity | 630 | C | Skip
990000000000 | SYSSSHCHK | AML SSH Config Check | 630 | C | Skip
948 | CLR_IFSWP | O*Clear IFS TMP Fldr-WN | 630 | C | Skip
1166 | CXTBLBDG | *Giftcard Reversal TBLMDG | 630 | C | Do
1172 | F_PDBRCLWP | *FTP RCL Fee-> Google WN | 645 | C | Do
1174 | F_PDBVNDWP | *FTP Vend Master-> PDB WN | 645 | C | Do
000000000624 | RMAFTP | RTV Get Inbound Email ATT | 645 | C | Do
367 | AS2RESETDP | *Reset AS2 Comm. Line | 655 | C | Do AS2 restart if needed
419 | ESPCUA | *Upld AS400 WebESP Cust | 655 | C | Do
684 | AIRM_DAILY | *Send Daily Feeds AIRMILE | 700 | C | Skip
917 | CHKBAL_BLD | CHECK INVBAL REBUILD | 700 | C | Do
925 | PPR_OH_WP | PPR On Hand - rolling-SUN | 700 | C | Do
1243 | UP_MEMCONT | *Upd Sku Memory Content | 700 | C | Do
1093 | FCHN_SKUWP | *CHN Sku Lst-Fill Rpt-WKN | 700 | C | Do
1285 | TSS_ORDPOP | Zuora Order Number Popula | 700 | C | Skip for now
000000000288 | RBT34504 | ROBOT Schedule of Jobs to | 700 | C | Skip
000000000379 | RBCSTRTMON | Re-start RBCQSYSOPR | 700 | C | Skip
260 | HAMILTON | *CREATE CITICORP FILES | 715 | C | Skip
672 | DESJARDINS | *Outbound Line Item Dtl | 730 | C | Skip
1176 | F_ORDSTSYD | Copy FC Order Sts Journal | 730 | C | Do
1183 | EM_PDNVFO | Eml Pending Sell Thr Rpt | 730 | C | Do
000000001289 | EM_UIDCHWP | Eml User ID Chg Err -WKN | 730 | C | Do
000000000055 | AR_UPDATE | Update A/R Sub-ledger | 745 | C | Do
351 | EM_PRC2DP | *Email Price Chg-Follw Up | 800 | C | Do
505 | PCA_STRCNT | Sat/Sun inventory connt | 800 | C | Do
596 | TRF_AUTRCV | Auto Rec. Old Trfs | 800 | C | DO
990000000000 | SYSSSLCHK | Check for SSL v2 | 800 | C | Skip
747 | KRONOSWP | *WKLY:Store Data->Kronos | 800 | C | Do
000000001338 | E3_RPLEN | *E3 Repln*Before E3_Frz | 800 | C | Do
804 | SKU_TRNSLN | SKU French Translation | 800 | C | Do
814 | F_ESPTBL | FTP ESP TABLE TO ETS | 800 | C | Do
864 | EMPMSTWP | O*Upload Employee Mst-WP | 800 | C | Do
870 | CRT_R40CTL | Not Use-Run in CPCDaily | 800 | C | Do
972 | PRGE_PRCZN | Purge Expired PRCZNO rcds | 800 | C | Do
1079 | CXDLYSUN | Daily SLS CMIS-Sunday | 800 | C | Do
000000001318 | SYSPRFDSP | DSPUSRPRF to BUSDEPUSRS | 800 | C | Skip
000000000916 | POSCLEANUP | POS IFS folder cleanup | 800 | C | Do
264 | CSH900 | PRICE OVERRIDE REPORT | 815 | C | Do
456 | CKMONSWAW | Check MONSWABRM for SLA | 815 | C | Skip
701 | EMSLSVARWP | Email Sales Var Sum-WP | 815 | C | Do
000000000725 | AS2_CHKCOM | H*Check AS2 Comm. Line | 815 | C | Do
783 | CPYAHS_P | *Upload Auto Hub&Spk Data | 815 | C | Do
461 | OF_IN_GA | Oracle Chart Accts JDA | 830 | C | Do
462 | OF_IN_GL | Oracle Locations to JDA | 830 | C | Do
463 | OF_IN_GR | Oracle Exch Rates to JDA | 830 | C | Do
466 | OF_IN_GT | Oracle GL TransactionsJDA | 830 | C | Do
727 | HEAD_COUNT | *Head Count Sales file HD | 830 | C | Do
1065 | MOOSE3_WP | M*Rebuild MOOSE3-Weekend | 830 | C | Do, Come back, Run after all E3xxxxx jobs completed in E3QBATCH sbs
975 | EM_HUGEQTY | Email Huge Inv Adj Qty | 830 | C | Skip
000000001292 | DST_SUN | SUNDAY DISTRICT STORE RES | 900 | C | Do
000000001322 | ALG_BAL_WP | *DailyAlgolia Invbal File | 900 | C | Do
895 | CSH_XTN_WK | Cash Bolt-on file-WKN | 845 | C | Do
468 | OF_EML_CNF | Email Outstndng Confirms | 900 | C | Do
990000000000 | SYSSTPROLL | Dasd plus Rolling Survey | 900 | C | Skip
826 | EMMISSW1 | Email Missing Rtl Sales | 900 | C | Do
985 | EM_SKUADCH | Email Sku Add/Change Data | 900 | C | DO
1056 | CX_MST_WP | *Daily CMIS Master Files | 900 | C | DO
1059 | EM_SLS_PCS | Email SLS Piece Count Rpt | 900 | C | DO
1287 | EM_EP_UNAP | Email Daily Emg Prf UnApr | 900 | C | DO
1159 | OOSLBD15 | Prt Out of Stk Lbl D15 | 900 | C | DO
1266 | SUNIRF_WP | SUNRISE Inv Fresh Sat-Sun | 900 | C | Do
207 | SVC026CL | D*Prt SVS Settlement Rpt | 930 | P | DO
469 | OF_IN_RC | Orcl Reconcil Ttls JDA | 930 | C | Do
902 | MONINVBL1A | INVBAL Refresh to Sunrise | 945 | C | Do
490 | F_XEROXWP | *Send PO Rec RTV Info XRX | 1000 | C | Do
501 | POS_REJECT | reject POS trans report | 1000 | C | Do
697 | SYSSWPAUD | Audit swap profiles | 1000 | C | Skip
990000000000 | SYSBCKPRG | Purge backup audit log | 1000 | C | Skip
829 | BLD_PRXFWK | Bld Program Ref-Wkend | 1000 | C | Skip
846 | CK_E3EOD1A | O*Check E3 EOD(Sun)ASR | 1000 | C | Skip
935 | EM_PMWK | P&M Flash Sales-CPC Email | 1000 | C | Do
968 | F_OS_POTRW | FTP Unrec PO Trf-BTS Wk N | 1000 | C | Do
1227 | SYSCHKLKEY | Check license keys expire | 1000 | C | Skip